## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | From 01st July 2018 to 31st December 2019
| Project Title: | Akamatutu'anga kia Tukatau te Ora'anga I te Pa Enua (PA ENUA ACTION FOR RESILIENT LIVELIHOODS (PEARL)
| Project Summary: | The objective of the programme is to build and implement an integrated approach to further increase the adaptive capacity of remote island communities and ecosystems to disaster risk and climate change impacts through the following: * Strengthening national and local capacity for monitoring and decision making to respond and to reduce risks associated with climate change * Establishing climate resilient water management instruments using integrated and community based approach *Raising awareness and establish a knowledge exchange platform to increase adaptive capacity to revitalise agriculture production systems
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | COK/NIE/Multi/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Finance and Economic Management | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Cook Islands | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Cook Islands / Asia-Pacific | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2018-03-22
IE-AFB Agreement Signature Date: |  | 2018-05-15 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-12-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
2021-12-06
Original Completion Date:
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Mani Mate | Dominican Republic
| Email: | mani.mate@cookislands.gov.ck | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ministry of Foreign Affairs and Immigration | Equatoral Guinea
| Email: | tepaeru.herrmann@cookislands.gov.ck | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ministry of Finance and Economic Management | Fiji
| Email: | mani.mate@cookislands.co.ck | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Climate Change Cook Islands | Georgia
| Email: | melina.tuiravakai@cookislands.gov.ck | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Emergency Management Cook Islands | Grenada
| Email: | timoti.tangiruaine@cookislands.gov.ck | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Infrastructure Cook Islands | Guyana
| Email: | taukea.raui@cookislands.gov.ck | Haiti
| Date: |  | Honduras
| Executing Agency |  | Guinea Bissau
| Name: | Ministry of Agriculture | Guyana
| Email: | takili.tairi@cookislands.gov.ck | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to December 31st 2019 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31st December 2019 | 581595 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Undisbursed amount as at 31st December 2019: US$759,845.00 Some delays were experienced in project implementation under the following components which has impacted on the projected spends in Year 1: Component 1: Undisbursed amount of US$83,783 due to activities under Output 1 and Output 2 not being able to be carried out due to shipping and travel constraints to the Northern Group islands. These activities are scheduled to be conducted in Year 2. Component 2: Undisbursed amount of US$52,870 is due to travel constraints to the Northern Gorup islands to implement activities under Output 1 on the drafting of the water security policy. Furthermore, funds committed under Output 2 for water making desalination is delayed to be able to procure the most suitable plant. Discussions on specifications are ongoing and desalination equipment expected to be procurred in Year 2 or 3. Component 3:The bulk of undisbursed amount of US$343,586 is related to Output 2; Schools gardens for the Northern Group Islands. Shipping and travel constraints have also played a major part in delays to having this project started in the Northern Group. Procurement of equipment for each of the Northern Islands schools have begun however storage space prior to shipment have meant that major equipment cannot be purchased during Year 1. Discussions with Shipping Company is ongoing with the hope that passage to the Northern islands will be available in Year 2 to start the implmentation of this project. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1 | 101314.8557
| Component Administration | 37738.13
| Output 1.1.1 | 33690.6078
| Output 1.1.2 | 268.9521
| Output 1.2.1 | 0
| Output 1.2.2 | 0
| Output 1.2.3 | 0
| Output 1.3.1 | 3152.1286
| Output 1.3.2 | 26465.0372
| Output 1.3.3 | 0
| Component 2 | 116853.9722
| Component Administration | 28611.87
| Output 2.1.1 | 25458.4982
| Output 2.1.2 | 0
| Output 2.1.3 | 48409.0623
| Output 2.2.1 | 0
| Output 2.2.2 | 11443.1742
| Output 2.2.3 | 2657.0875
| Output 2.3.1 | 0
| Output 2.3.2 | 0
| Output 2.3.3 | 274.28
| Output 2.3.4 | 0
| Component 3 | 239658.2274
| Component Administration | 28379.26
| Output 3.1.1 | 8228.4
| Output 3.1.2 | 43473.572
| Output 3.1.3 | 70925.5852
| Output 3.2.1 | 6100.9335
| Output 3.2.2 | 54694.2777
| Output 3.2.3 | 0
| Output 3.3.1 | 5610.3974
| Output 3.3.2 | 7916.2899
| Output 3.3.3 | 0
| Output 3.3.4 | 0
| Output 3.4.1 | 13380.4549
| Output 3.4.2 | 674.7768
| Output 3.5.1 | 0
| Output 3.5.2 | 0
| Output 3.5.3 | 274.28
| Output 3.5.4 | 0
| Component 4 | 123768.49
| Implementing entity oversight cost | 69761.24
| Project Execution Cost | 54007.25
| TOTAL | 581595.5453 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1 | 227353.57
| Component Administration | 30856.5 | 31.12.21
| Output 1.1.1 | 62707.27 | 31.12.21
| Output 1.1.2 | 10491.21 | 31.12.20
| Output 1.2.1 | 0
| Output 1.2.2 | 6857 | 31.12.20
| Output 1.2.3 | 26717.74 | 31.12.21
| Output 1.3.1 | 22628.1 | 30.06.21
| Output 1.3.2 | 40730.58 | 30.06.21
| Output 1.3.3 | 26365.17 | 31.12.20
| Component 2 | 323600.35
| Component Administration | 25782.32 | 31.12.21
| Output 2.1.1 | 30856.5 | 31.12.21
| Output 2.1.2 | 274.28 | 31.12.21
| Output 2.1.3 | 16539.77 | 31.12.21
| Output 2.2.1 | 30493.08 | 31.12.20
| Output 2.2.2 | 7542.7 | 31.12.21
| Output 2.2.3 | 40412.42 | 31.12.21
| Output 2.3.1 | 0
| Output 2.3.2 | 0
| Output 2.3.3 | 274.28 | 31.12.21
| Output 2.3.4 | 171425 | 30.06.21
| Component 3 | 417356.11
| Component Administration | 18513.9 | 31.12.21
| Output 3.1.1 | 8228.4 | 31.12.20
| Output 3.1.2 | 0
| Output 3.1.3 | 62346.59 | 31.12.21
| Output 3.2.1 | 0
| Output 3.2.2 | 0
| Output 3.2.3 | 0
| Output 3.3.1 | 12342.6 | 31.12.21
| Output 3.3.2 | 0
| Output 3.3.3 | 137140 | 31.12.21
| Output 3.3.4 | 68570 | 31.12.21
| Output 3.4.1 | 15313.74 | 30.06.21
| Output 3.4.2 | 5142.75 | 30.06.21
| Output 3.5.1 | 0
| Output 3.5.2 | 0
| Output 3.5.3 | 274.28 | 31.12.21
| Output 3.5.4 | 89483.85 | 31.12.21
| Component 4 | 155356.99
| Implementing entity oversight cost | 73141.56 | 31.01.21
| Project Execution Cost | 82215.43 | 31.01.21
0
| TOTAL | 1123667.02 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Meeting the expectations of the Communities to implement projects but there is insufficient budget | M | Consultation with all impacted communuities and stake holders so that they know what are being planned for implementation and what are not. It is important to explain clearly that all islands will not received the same amout of assistance and that most priority communities will be the focus of the project assistance
Finance personnel is unable to meet financial commitments and targets as defined in the workplan | L | Regular monitoring for financial transactions with monthly bank reconciliation statements completed.
Travel costs exceed the budget to meet Northern Group commitments and activities | H | Cost sharing travelling cost swith other Government Department may be the way to deal with this issue
Economic Resilient and Water Security Fund requests exceed available budget | M | Ensuring that criteria is clearly understood for fund requests to be assessed and decisions provided as soon as they are made.
Disputes during contract execution, e.g. the quality of the work is assessed to be inadequate, or regarding issues related to budget and completion time of work | M | If the Project Manager and or Coordinator cannot resolve the conflict, the matter must be addressed by the NIE; TTV has a mediation process that will be implemented.
The project may not receive the funds on time, or there may be a slow disbursement of funds, which can have a significant impact on implementation and co-financing availability. | M | System to manage this is in place plus forward planning by Outputs
Misappropriation of Project Funds | L | Annual audits as well as spot check audits will be enforced during project implementation.
Not able to contract suitable Project Management team for the PMU | L | Project Management team for the PMU established
Poor collaboration between programme partners | L | Ongoing meetings with keystakeholders are conducted weekly, monthly and quarterly (Platform Meetings)
Island Government disputes the role of the PMU in Rarotonga and declines implementation of activities | L | Ongoing communication with Island Governments and Communities is key.
Disputes over who should drive the projects on island and the competing interests of various stakeholders | L | The project will be driven through the Local Government Channels to avoid local interets groups but if well consulted and issues adressed properly it shoud not be a problem
Limited human resources in Government ministries and agencies to contribute to the activities. | L | We will adress the HR issues island by island depending on the local capabilities and enter into an agreement
The government is no longer supportive, politically and financially, of a cross-sectoral and integrated approach to the management of climate risks and opportunities. | L | This is not a risk at this stage and ongoing communication is key to all stakeholders.
Communication, access and community coordination difficulties delay timely implementation of the planned programme activities at the target community level. Communication costs exceed budget allocation. | L | This is not a risk at this stage and ongoing communication is key to all stakeholders. Communication and Awareness has meet all targets for 2019. Communication Matrix is in place with key target indicators for the year. This has been updated for 2020. Outreach and Awareness with the PEARL Project Champions Stan Walker, Miss Cook Islands Miss World Oceania 2019 to 2020 has seen a huge improvement in marketing and promoting the PEARL projects with feature stories featured and video Link - https://www.youtube.com/watch?v=63uz6DoaGqI (Automatic Weather Stations linages with Traditional Fishing Practices) Link - https://www.facebook.com/climatechangecookislands/notifications/?section=activity_feed&subsection=share&target_story=S%3A_I183463179213%3A10158020874784214&content_id=2803551566354369 Link - https://londonpacificfashion.wordpress.com/2019/12/16/miss-world-oceania-2019-miss-tajiya-eikura-sahay-from-the-cook-islands/
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational - Transportation | On going - only one domestic cargo shipping supplier to Northern Group. | The PMU Coordinator and team continue to have regular meeting with shipping agents to look at ways to improve delivery and avoid delays to projects.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risk - Operational Transportation Risk for Project Equipment/Materials and access to islands. Risk Description - Isolation of Islands and inconsistency of transportation now that there is only one domestic cargo shipping supplier to Northern Group. To avoid delays due to the materials/equipment not being able to reach the islands in projected timeframes. Risk Status - Risk are still ongoing. To avoid delays PMU is working with shipping agents, suppliers and project team to project timeframes/schedules/material availability to minimize possible delays due to changes in shipping schedules. Clear communication with all stakeholders is key to implement and complete projects.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Lack of compliance with local and national laws in project activities. | Management : Through early intervention at the inception phase, the ESS, Gender Specialists and the technical specialists engaged for the water and food security components will confirm all activities for implementation are compliant with existing laws. Avoidance : The Programme has been designed to be in compliance with relevant national laws, regulations and policies. If activities are not compliant, further appropriate actions will be carried to ensure provisions of applicable existing laws are not breached. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The Programme has been designed to be in compliance with relevant national laws, regulations and policies. Compliance with laws and in particular the following key legislations will be monitored during implementation: Environment Act 2003 and Biosecurity Act 2008. There is the likelihood that some activities will be required to comply with existing laws, e.g. Environment Act 2003. | There may be a rare occasion when the programme or sub-projects will not be in compliance with relevant national laws, regulations and policies and in this case the process to be followed are outlined. | none at the moment | none at the moment
2 - Access and equity |  |  | Lack of equity in access to project resources and activities. | Mitigation: Each Pa Enua has in place a grievance mechanism at the Island Government and at the community level. Avoidance: Measures provided in the ESMP is taken into consideration to ensure ES and Gender safeguarding is followed and risks and impacts remains low. Management: The ESS and Gender specialist will monitor and implement measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities; AGIntel database; Geo Portal | The Programme recognises that the Pa Enua communities are small and in close proximity, and therefore sharing of information and benefits through the network of groups should be easier. However, the programme will make sure compliance by describing the process of allocating and distributing programme benefits. It will ensure that there will be neither discrimination nor favoritism in accessing programme benefits. | Due to competing interests and also insufficient funds to meet 100% demand and meet all the community expectations it will be necessary that the communities fully understand the Programme/projects to be implemented. | none at the moment | none at the moment
3 – Marginalized and vulnerable Groups |  |  | Exclusion of marginalised and vulnerable groups from project activities. | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP | Reports of community adaptation action planning processes and consultations with local authorities; AGIntel database; Geo Portal | There are people with disabilities and families living with persons with disability, the elderly, children, women and girls, as well as people with very low income and with limited access to resources to help them in their normal everyday living. The small nature of the communities and their close proximity with each other, marginalised and vulnerable groups are easily recognised and their needs provided at the community and family level. | Specific projects that need to be considered is the siting of water tanks and early warning systems must take into account the need to ensure the marginalised and vulnerable groups are considered in design phase. Agricultural programmes will ensure these groups will have more access to produce as well. | none at the moment | none at the moment
4 – Human rights |  |  | lack of respect and compliance with individual human rights | Management: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP and to address any gaps in the current situation in the Pa Enua Mitigation: The law of the country applies to everyone in the country whether they are resident or visitor. | Reports of community adaptation action planning processes and consultations with local authorities. | The Cook Islands Constitution recognises fundamental human rights and freedom that exist and shall continue to exist without discrimination by reason of race, national origin, colour, religion, opinion, belief, or sex. | This is a cross-cutting principle and all activities will be designed to make sure the rights of every person in the Pa Enua are not infringed upon. The Programme recognises that human right issues whether it is to do with rights to resources, land, training, opportunities, and the right to express one’s opinion and the right to be heard, is considered important in the Pa Enua, the risk and impact assessment depicts a very low risk and minor impact for all project sites on this principle. | none at the moment | none at the moment
5 – Gender equality and women’s empowerment |  |  | Lack of gender equity and women’s empowerment in project implementation and outcomes. | Mitigation: ESS and in particular the Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP for gender safeguarding | Reports of community adaptation action planning processes and consultations with local authorities; AGIntel database; Geo Portal | Gender inequality is highest in the small communities of the Pa Enua. There is a strong but defined roles for women based on church teachings and it does not always support gender balance. | Early consultation during Inception phase should ensure that men and women: 1) have equal opportunities to participate in consultation, training and awareness activities; 2) receive comparable social and economic benefits; and 3) do not suffer disproportionate adverse effects during the development process | none at the moment | none at the moment
6 – Core labour rights |  |  | Lack of compliance with local and national labour laws | Mitigation: ESS and Gender Specialist will monitor those mitigating measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities. | The project has been designed to comply with relevant national laws and policies that govern employment rights and appropriate working conditions in the work place. | All persons employed under this programme will go through contractual arrangement following the CIG Procurement Policy. For agricultural projects that are considered under the Economic Resilience Fund in Component 3, it is important, where a project requires assistance to pay workers that proponents ensure the rights of workers are observed and they are paid according to current income laws and their working conditions in accordance to good employer practice. | none at the moment | none at the moment
7 – Indigenous peoples |  |  | Lack of consideration for indigenous people | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities. | The Cook Island Constitution recognizes people of the Cook Islands as ‘people of Cook Islands decent’ and is the closest we have in classifying people as ‘indigenous people’. There are no separate laws for people of Cook Island descent and other ethnic groups. | The law of the country applies to everyone in the country whether they are residents or visitors. | none at the moment | none at the moment
8 – Involuntary resettlement |  |  | Involuntary resettlement of people from their homes and lands for planting as a result of project activities | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities. | The Programme will focus on lands already used for community water tanks, planting lands that already have access roads and currently used for agriculture purposes and due process will be followed where new lands are identified. | Even though the Programme will be looking at lands already used for public purposes, still, the landowners will be consulted and negotiations as per existing land acquisition processes. The Programme recognises that there will be no requirement for Involuntary resettlement in the Pa Enua | none at the moment | none at the moment
9 – Protection of natural habitats |  |  | Damage and/or degradation to natural habitats as a result of project activities. | Management: Environment Imapct Assessment (EIA) Process; Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; Plan to minimize introduction of invasive species; Agriculture quarantine protocols to be followed | The Programme will focus on lands already used or cleared, existing access roads so the likelihood that natural habitats may be affected is very low. | The Programme recognises current levels of awareness at the national, island and community level where the awareness for protection of biological diversity has been on-going and in some cases conservation areas have been established. Where a new activity such as the construction of a new community concrete water tank or the construction of a new water catchment building on a new site, or the construction of a water reservoir and laying of irrigation lines for agriculture purpose would go ahead, and if these new activities are identified to have the potential to encroach on special natural habitats, through the National Environment Service ESD form check list and risk identification and EIA process, | none at the moment | none at the moment
10 – Conservation of biological diversity |  |  | Biodiversity loss as a result of project activities. | Mitigation: National Environment Service ESD form check list and risk identification and EIA process | Plan to minimize introduction of invasive species Agriculture quarantine protocols to be followed | The Programme will focus on lands already used or cleared, existing access roads so the likelihood that biodiversity may be affected is very low. | The Programme recognises current levels of awareness at the national, island and community level where the protection of biological diversity has been ongoing. Where a new activity such as the construction of a new community concrete water tank or the construction The Programme recognises current levels of awareness at the national, island and community level where the protection of biological diversity has been ongoing. Where a new activity such as the construction of a new community concrete water tank or the construction | none at the moment | none at the moment
11 – Climate change |  |  | Significant or unjustified increase in greenhouse gas emissions or other drivers of climate change. | Management: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The likelihood of increased greenhouse gas or any other cause of climate change is not high. | Relevant to the Programme, impacts such as potential pollution of coastal waters affecting coral growth and the emission of carbon dioxide into the atmosphere as a result of potential burning of cleared vegetation on lands for agriculture purposes, the use of coastal resources for building weakening the capacity of the coast to protect lands behind it from sea surges. Recognising that existing activities on climate change resilient building has been on-going. | none at the moment | none at the moment
12 – Pollution prevention and resource efficiency |  |  | Pollution and lack of efficiency in use of natural resources. | Management: Environment Imapct Assessment (EIA) Process; Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The project has been designed to ensure reduction; in waste production, burning of fossil fuel, and the release of pollutants into the environment is minimal. | The programme recognises current practices and government policies on solar energy and the move to 100% solar energy by 2020. | none at the moment | none at the moment
13 – Public health |  |  | Negative impacts on public health as a result of project activities. | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; Public Health Act 2004; | The Programme has been designed to support Public Health in the Pa Enua. The Programme will support the tutaka programme (regular health inspection of homes and villages) of the Ministry of Health through its communication and Media Specialist and will enhance the supply of clean water for cleaning and drinking in homes. | Public and Health workers on each of the islands ensuring all people have access to quality advice and service, good quality drinking water, households have access to water for cleaning, community and formal education and public awareness programmes on health issues are in place, alternative medicine in the form of traditional medicine is available, and knowledge on useful plants and herbs are available. | none at the moment | none at the moment
14 – Physical and cultural heritage |  |  | Damage to physical and cultural heritage sites | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The project has been designed to ensure no physical and cultural heritage sites are modified. | The programme targets the use of lands already used and altered. | none at the moment | none at the moment
15 – Lands and soil conservation |  |  | Land and soil degradation | Management: Environment Imapct Assessment (EIA) Process; Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | There is likelihood some manageable impacts will arise from modified lands. Where land is to be modified that may cause soil erosion, standards will be followed to maintain the land in its natural state or as close to its natural state as is possible; and, if land is to be converted, it must promote and protect its current function e.g. sloping lands or forest lands. | There will be no changing of soil structure or causing lands and soils to be degraded or values changed. | none at the moment | none at the moment
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Monitoring of ESP risks is ongoing as part of project activities.
Have unanticipated ESP risks been identified during the reporting period? |  | Sub-projects under the Water Security Fund and Economic Resilience Fund will be conducted in Year 2, which will include aspects of identification of environmental and social risks related to these sub-projects
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Regular monitoring and evaluation of implmentation of activities are carried out to ensure that all activities for implementation are compliant with the ESMP.
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements have been effective in the first year of the project
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Component specialists and the technical specialists engaged for each component ensure that activities carried out are checked against the ESMP.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation has been effective in the first year of the project
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The required capacity to carry out the ESMP are filled and effected in both the IE and also the 3 EE's. Technical and advisory committees composing of various agncies identified in the ESMP advice the component specialists of any likely Environment and Social Risks before they arise and helps identify mitigation measures. The roles of the ESS Specialist and Gender Specialist are to be recruited in Year 2 as sub-projects are identified. The specialists will focus on identifying risks in the implmentation of the sub-projects
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | The ESMP will be updated in Year 2 once the sub-projects are identified
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | USPs will be identified and implemented in Year 2. | USPs will be identified and implemented in Year 2. | USPs will be identified and implemented in Year 2. | USPs will be identified and implemented in Year 2. | USPs will be identified and implemented in Year 2. | USPs will be identified and implemented in Year 2. | USPs will be identified and implemented in Year 2.
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Given that the project contains sub-projects, the grievance mechanism will be fully implemented as the sub-projects are identified and implemented. To date no grievences have been received.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Number of Geo Portal Officers trained on each island by Gender | Output | A minimum of one on each island including equal number of women | 0 | 50% | to be measured at end
Develop user and administration manual for the Geo Portal | Output | A minimum of 1 training workshop on each island inclding equal number of women | 0 | 50% | to be measured at end
School gardens for the northern group islands | Output | Number of students by gender taught science, social science and health & wellbeing units using school garden | 0 | 50% | activities under this output programmed to begin in Year 2 of project implementation
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity and Executing Enities, have all made efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the household baseline incorporated sex disaggregated data and gender specific questions. 2 - Encouraging project partners/ executing entities to hold gender sensitive consultations and assessments, for example holding separate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men. 3 - Ensuring that the Inception Workshop and Implmentation related Workshops had participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during workplanning
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements for Gender Policy compliance have been effective. Discussions on gender issues were held during project inception and work planning, with the following outcomes and agreements: 1) all partners to consider the specific needs and constraints of womens participation in project activities; 2) track gender indicators in all activities; 3) aim for equal participation of women in project activities and activity leadership structures; and 4) capture sex-dissagregated data for the baseline and other assessments and activities. This has laid the foundation for effective Gender Policy implementation in the project.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Component 1 - Emergency Management Cook Islands (EMCI) - Geo Portal surveys and mapping has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. Information specific to men and women has been gathered through this method. - Continuous sensitisation on participation of both men and women when identifying participants for project activities; persons attending project related workshops and trainings are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities.
Component 2 - Infrastructure Cook Islands (ICI) - Water Security surveys and mapping has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. Information specific to men and women has been gathered through this method. - Continuous sensitisation on participation of both men and women when identifying participants for project activities; persons attending project related workshops and trainings are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - Ensuring that access to benefits under the Water Security Fund incorporates both women and men
Component 3 - Ministry of Agriculture (MoA) - Participation in agriculture surveys and mapping has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. Information specific to men and women has been gathered through this method. - Continuous sensitisation on participation of both men and women when identifying participants for project activities; persons attending project related workshops and trainings are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - Ensuring that access to benefits under the Economic Resilience Fund incorporates both women and men
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The implementation arrangements for Gender Policy compliance have been effective. Womens participation in project activities, as well as their engagement in leadership and training roles has been strong. In some cases womens participation is higher than the targetted 50%. The effectiveness of the EEs efforts to address gender equality has been steady and activity to activity.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | At the moment no major capacity gaps affecting Gender Policy compliance have been identified at the IE or the EEs. The capacity for adherence to the Gender Policy is adequate among the IE and EEs. The EEs will continue to engage with the stakeholders on the importance of gender issues and the participation of both men and women.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances relating to gender matters have been received in the reporting period. |  | No grievances relating to gender matters have been received in the reporting period.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Prevent new and reduce existing disaster risk through the implementation of integrated and inclusive economic, structural, legal, social health, cultural, educational, environmental, technological and institutional data. |  | Outcome 1 | Integrated data sets inclusive of economic, structural, legal, social health, cultural, educational, environmental, technological and institutional are created at the Pa Enua level and aggregated at the national level |  | * Pa Enua DRM plans currently in process awaiting endorsement from eleven Island Governments (Atiu, Mangaia, Manihiki, Mitiaro, Nassau, Palmerston, Penrhyn, Pukapuka & Rakahanga). Endorsement of DRm plans for Aitutaki and Mauke completed. * Training for GeoPortal officers are ongoing with the islands of Mauke and Aitutaki carried out. This also includes Youth & Community training workshops | S
| Strengthened drinking water security including increased institutional capacity and coordination for integrated water management to reduce risks associated with climate induced socioeconomic and environmental losses |  | Outcome 2 | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought |  | * Implementation is ongoing for this component, the development of drought plans is 50% completed for Mauke. A drought assessment plan for the Northern groups is being planned pending on travel arrangement to the Northern Group to carry this out | MS
|  |  | Outcome 4 | Number of communities that maintain safe drinking water supplies to meet basic needs at all times including during periods of drough |  | * Workshops are ongoing which involves schools and communities on drinking water safety measures. | MS
| Increased island food security resilience and preparedness for disasters |  | Outcome 6 | Number of water efficient irrigation system installed |  | * 80% completed - the islands of Atiu, Mangaia, Mitiaro and Mauke are completed. | S
|  |  |  | Displacement of imported food with island vegetables |  | * Displacement of imported food is ongoing. These are being tracked using AgIntel | MS
|  |  |  | Pa Enua fruit products sold in Rarotonga to meet tourist demand |  | * Ongoing - orchards in the Pa Enua are receiving assistance under Output 3.3.1 | MS
|  |  |  | Improved variety of staple crops that are resilient in the face of increased climate variability and climate change are grown at the Pa Enua level for local consumption |  | * Ongoing - Nursery and farmers in the Pa Enua are receiving assistance under various outputs within Component 3 that will improve the variety of staple crops to ensure more resilient communities in the Pa Enua. Tracking of crops are being carried out using AgIntel | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mani Mate, National Implementing Entity, Development Coordination Division - MFEM
| Email: | mani.mate@cookislands.gov.ck
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The PEARL programme has been progressing well. The PEARL team have carried out Raurau Akamatutu workshopsfor youth and community around Safe Drinking Water practises, food security and climate impacts on the Pa Enua. Extensive DRM surveys have also been conducted on some of the islands to inform the updating of Island DRM Plans, this activity is ongoing.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Prevent new and reduce existing disaster risk through the implementation of integrated and inclusive economic, structural, legal, social health, cultural, educational, environmental, technological and institutional data. |  | Outcome 1 | Integrated data sets inclusive of economic, structural, legal, social health, cultural, educational, environmental, technological and institutional are created at the Pa Enua level and aggregated at the national level |  | Project activities are on task to achieving the Outcome of Reduced exposure to climate related hazards and threats with information gathered and assessments conducted and updated from stakeholders and Pa Enua community. Activity Line 1.0/ 1.1.2 An integrged and inclusive data base is established one year from implementation fo the programme and All 11 Pa Enua with baseline and updated datasets in the Geo Portal - 100% Completed under SRIC-CC and BSRP Projects. The Geo Portal with climate early warning information has been established and can be viewed online at http://www.emci.gov.ck in the Cook Islands; This assignment is managed by the Emergency Management Cook Islands (EMCI) Division at the Office of the Prime Minister. The Geo-Portal will continue to be loaded with information and this information updated annually by the designated staff at EMCI. The information is also to assist EMCI in the assessment of communities in pre and post-disaster situations. This Target is currently being strengthened and updated in the PEARL Project from the DRM Household Surveys/Data from the Pa Enua. CLEWS, DRM Surveys, DRM Plans and MET Drought Reports are assessment dataset in the Geo Portal. Activity Line 1.2.1 Three Management Response tools target is completed with CLEWS, DRM Plans, GEO Portal, MET Services Drought Reports, CSDP, NSDP, JNAP II, Social Media, MET Drought Reports, DRM Household Surveys. Activity Line 1.2.2 /1.2.3 Monthly usage of management tools target completed with MET Services Drought Reports, AWS CLEWS, Social Media, Geo Portal. At least one App is obtaine and used - DRM Survey Tabet Tools Applicaitons to upload information to Geo Portal and AWS Smart App is currently in Beta Testing with MET Services. Activity Line 1.2.4 This activity is projected to be completed in 2020 pending shipping schedules and equipment. Activity Line 1.3.1 All 10 Pa Enua DRM Plans updated to 2017 National DRM Plan. This target is completed as all 11 DRM Plans are updated to 2017. The PEARL Project is currently updating the DRM Plans to 2021 and pending Island Endorsement for Atiu, Mangaia, Manihiki, Mitiaro, Nassau, Palmerston, Penrhyn, Pukapuka, Rakahanga. Activity Line 1.3.2 and 1.3.3 is ongoing with training workshops in the Pa Enua in Aitutaki (13 Participants 5 Males and 8 Females), Mauke and Atiu conducted in 2019. | MS
| Strengthened drinking water security including increased institutional capacity and coordination for integrated water management to reduce risks associated with climate induced socioeconomic and environmental losses |  | Outcome 2 | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought |  | This project activities are on task to achieving the Outcome of Strenghtened capacity of the Pa Enua to withstand conditions resulting from climate change impacts. Communities are engaged in assessments, workshops, plans and testing. This project is tasked to strengthen water security for the communities. Rainwater harvesting and accessing well water is all they have. This project hopes to alleviate water shortage situation by providing more water storage capacity on these islands to mitigate future drought conditions and reduce risks. Activity lines 2.0/2.1.1/2.1.2/2.1.2.3 are ongoing. Activity Line 2.1.4 At least one for Drought Assessment for the North and South to be completed is 50% target achievement wit hte Completition and endorsement of the Mauke Drought Assessment Plan completed in 2019 Activity Line 2.2.1 - At least one for Drought Assessment for the North and South to be completed is 50% target achievement wit hte Completition and endorsement of the Mauke Drought Assessment Plan completed in 2019. | MS
|  |  | Outcome 4 | Number of communities that maintain safe drinking water supplies to meet basic needs at all times including during periods of drough |  | Ongoing. Most vulnerable groups and youth are included in workshops, projects and consulted on all islands. | MS
| Increased island food security resilience and preparedness for disasters |  | Outcome 6 | Number of water efficient irrigation system installed |  | Target has been achieved in supporting the implementation and installation of irrigations in Aitutaki, Atiu, Mauke, Mitiaro and Mangaia. To of 25 farmers have been assisted. To enhance the projects capacity building and strengthening the storage capacity of farmers will be implemented in Year 2 (2020) of this Project. | S
|  |  |  | Displacement of imported food with island vegetables |  | Agriculture Data has shown an increase of farmers by 48% (AgINTEL 2020) from 2018 to 2019 resulting to increased production in 2019 when compared to the previous year of 2017 and 2018. Rakahanga, Pukapuka and Manihiki all have hydorponic systems installed with revolving funds established. Maintance is provided from revenue recieved from sales of vegetables. The islands are now able to eat leafy green vegetables and eat less canned vegetables. This target has been achieved and will be strengthened in 2020 with the installation of hydroponics in remaining islands (Nassau, Palmerston and Penrhyn) in the northern and school gardens. | S
|  |  |  | Pa Enua fruit products sold in Rarotonga to meet tourist demand |  | This target has been achieved and will continue to bestrenghten for sustainability. Farmers on Mauke, Atiu, Mitiaro, Aitutaki and Mangaia are supplying the Rarotonga markets with produce typically imported from overseas and Rarotonga. Niche Produce like Broccoli, Cauliflower, Capsicum, Carrots, Ginger, Tumeric, Lettuce, Pok Choi Mint are now grown on the islands. Islands are also exporting jams and chutney. A cargo freight run has also been established in partnership with Air Rarotonga to assist with transportation of produce to market. | S
|  |  |  | Improved variety of staple crops that are resilient in the face of increased climate variability and climate change are grown at the Pa Enua level for local consumption |  | This target has been achieved in partnership with GEF R2R funded project. Crop banks established one on each of the southern group islands holding 5 tolerant yam varieties, 3 pineapple varieties, 5 banana varieties etc. One island left to receive yams and other drought resistant crops including fruit trees. | S
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Melina Tuiravakai, Project Management Unit, Climate Change Cook Islands - OPM
| Email: | melina.tuiravakai@cookislands.gov.ck
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Rating: Marginally Satisfactory Progress The overall marginally satisfactory rating is accredited to progress made in several areas during this reporting period, namely the successes in Capacity Building with a total of approximately 539 island stakeholders and key players trained in climate and disaster risk assessment with overall project capacity building/workshop/platform participation (57% women and 43% men) in 7 Pa Enua Islands (Aitutaki, Mauke, Atiu, Pukapuka, Penrhyn, Rakahanga & Manihiki) in 2019. Participation in Youth Expos, Surveys and Workshops has enabled youth participation and innovation with the opportunity for them to utilize technology, smart devices, tablets to conduct island wide surveys. These workshops include the Quarterly Platform meetings, National Workshop in Southern and Northern Group, Raurau Akamatutu (Basket of Resilience) Workshop, Youth Career Expos, GEO Portal Taskforce Meetings, Pa Enua Water Security Meetings, Program Steering Group (PSG) Meetings, DRM Household Surveys and Water Security Surveys. A total of 32% (12 of the 37) of the targets have been achieved with partnerships with other projects and stakeholders. Component 1 is currently being strengthened and updated with the DRM Household Surveys/Data from the Pa Enua. The positive direction in addressing the area of GEO Portal/Dataset have been significant with a total of 6 of the 11 targets achieved with partnerships from SRIC-CC/BSRP Programs and key stakeholders. These partnerships will assist in mainstreaming Climate Change in local development planning and decision making. Delays to the installment of the Automatic Weather Station Equipment have been due to procurement challenges. Lesson’s learned from SRIC-CC have assisted in providing interventions/mediations with shipping agents/suppliers and improvement in streamlining procurement processes. Component 2 is on task to achieving its targets in 2020. Partnership with Ministry of Health, GIZ Northern Group Water Security Program, Japanese Grassroots Fund and SPC Water Security Projects will assist the component in achieving targets/outcomes. Component 3 Advancement, was observed during the latter half of this PPR reporting period with procurement processes and equipment purchases. Initially delays were due to procurement challenges, but have now been initiated. A total of 6 of the 16 targets have been achieved in this financial year. Communication, engagement, and awareness-raising efforts using social media, partnerships, traditional/cultural forums, surveys, national radio/television and news print have reached global communities. Outreach with the PEARL Project Champions Stan Walker, Miss Cook Islands Miss World Oceania 2019 to 2020 has seen a huge improvement in marketing and promoting the PEARL projects with feature stories featured and video Link - https://www.youtube.com/watch?v=63uz6DoaGqI (Automatic Weather Stations linages with Traditional Fishing Practices) Link - https://www.facebook.com/climatechangecookislands/notifications/?section=activity_feed&subsection=share&target_story=S%3A_I183463179213%3A10158020874784214&content_id=2803551566354369 Link - https://londonpacificfashion.wordpress.com/2019/12/16/miss-world-oceania-2019-miss-tajiya-eikura-sahay-from-the-cook-islands/ Risks that affected progress One of the key risks that has affected progress has been Operational Delays in procurement due to transportation challenges. During this reporting period some interventions and mediation with shipping agents and suppliers have contributed to minimizing such delays. The Project Steering Group and Stakeholder Platform Meetings has continued quarterly, and effectively provides strategic oversight and coordination support to the Project. The Project team will work towards developing knowledge products that will feature stories of how communities’ climate change vulnerabilities are addressed and resilience are enhanced through the project investments in the communities with partnership with DCD.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | Prevent new and reduce existing disaster risk through the implementation of integrated and inclusive economic, structural, legal, social health, cultural, educational, environmental, technological and institutional data. |  | Outcome 1 | Integrated data sets inclusive of economic, structural, legal, social health, cultural, educational, environmental, technological and institutional are created at the Pa Enua level and aggregated at the national level |  | This Component is currently being strengthened and updated from the DRM Household Surveys/Data from the Pa Enua. CLEWS, DRM Surveys, DRM Plans and MET Drought Reports are assessment dataset in the Geo Portal. Total of 6 of the 11 targets have been achieved with partnerships from SRIC-CC/BSRP Programs and key stakeholders. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Timoti Tangiruaine, Emergency Management Cook Islands - OPM
| Email: | timoti.tangiruaine@cookislands.gov.ck
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Projects are tracking well and are on task to meet target achievement and the overall marginally satisfactory rating is accredited to progress made thus far. Youth participation in Surveys and Workshops has provided them with an opportunity to utilize technology, smart devices, tablets to conduct island wide surveys. Traditional surveys were conducted with paper forms on the islands of Aitutaki, Mauke and Atiu. The project will continue to use smart devices for island wide surveys. In 2020 more emphasis will be placed on capacity and resilient buidling for CC and DRM. One of the key risks that has affected progress has been Operational Delays in procurement due to transportation challenges.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | Strengthened drinking water security including increased institutional capacity and coordination for integrated water management to reduce risks associated with climate induced socioeconomic and environmental losses |  | Outcome 2 | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought |  | Consultation | S
|  |  | Outcome 4 | Number of communities that maintain safe drinking water supplies to meet basic needs at all times including during periods of drough |  | Ongoing | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Taukea Raui, Infrastructure Cook Islands
| Email: | taukea.raui@cookislands gov.ck
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Most of the activities in the first year focusses on the training and community consultation aspects of the project to inform therm of the Climate Change based activties required and their inputs and to get more informaition of the community expectations in water infratsructure repair and improvement options. Risk - No serious risks have affaected the program so far apart for the travelling arrangement due to clash with already planed visists by other agaencise visiting the islands at the same thime
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | Increased island food security resilience and preparedness for disasters |  | Outcome 6 | Number of water efficient irrigation system installed |  | All five islands have received new irrigation systems with training and additional farmers included. Over 25 farmers received and completed the training for new irrigation systems to reduce wastage of water. | HS
|  |  |  | Displacement of imported food with island vegetables |  | Agriculture Data has shown an increase of farmers by 48% (AgINTEL 2020) from 2018 to 2019 resulting in increased production in 2019 when compared to the previous years of 2017 and 2018. There was an increase of 0.5% of local produce within two quaters from 2018 to 2019 in the five Islands and is expected to increase more. | MS
|  |  |  | Pa Enua fruit products sold in Rarotonga to meet tourist demand |  | Inreased number of farmers are now supplying to the Rarotonga market from three islands in 2019 when compared to one island in the previous years. | MS
|  |  |  | Improved variety of staple crops that are resilient in the face of increased climate variability and climate change are grown at the Pa Enua level for local consumption |  | Crop banks have been established on each of the southern group islands holding climate tolerant varieties of yam, pineapple (3), bananas (5) and taro. | HS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Takili Tairi, Ministry of Agriculture
| Email: | takili.tairi@cookislands.gov.ck
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Irrigation systems have been completed and the system has been promoted to the community. Selected farmers received the materials and were trained on its use which they have also promoted to other farmers. Currently they have requested for more assistance in setting up their systems. More farmers have adopted the new irrigation system to help save water and the number is still increasing. A total of 25 farmers were supported by the project on all the five islands, and now more than 20 farmers are convinced and have adopted the system with their own private funds. We have not recieved any negative response on this irrigation system and the team continues to support farmers on advising where to source the irrigation materials from. In addition, agriculture data (AgINTEL database 2020) have shown an increase in local produce on each island which also indicated an increased number of farmers in 2019 when compared to 2018. The project was promoted in 2018 and started in 2019 which we believe made farmers intrested. There were additional training done with the agriculture department in the outer islands, to support the farmers when they have problems with their crops which helps sustain the progress of the project. There was an increase of 0.5% of local produce which includes local root crops, vegetables and fruits on all the five southern group islands and is expected to grow further since data for Qauter 3 and 4 of 2019 is yet to be published (AgINTEL 2020). There are still some areas that needs effort which are the quality check of the produce before it is shipped to Rarotonga and also proper crates for exporting local produce. Futhermore multiple climate tolerance varieties of rootcrops and fruit trees have been sent to each island to be stored in the crop banks, managed by the agriculture department in case one island is hit by a cyclone. There is multiple crop banks now in the southern group to help affected islands to recover planting materials in the recovery stage. These planting materials are planted in the crop banks and is mass produced for farmers to take and plant, and the program is a carry on for the agriculture department to keep on trialling new crops that are climate tolerant. In terms of the project implementation stage, transportation of materials to the outer islands was the biggest contributer in delaying the progress of projects.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Prevent new and reduce existing disaster risk through the implementation of integrated and inclusive economic, structural, legal, social health, cultural, educational, environmental, technological and institutional data. | Integrated data sets inclusive of economic, structural, legal, social health, cultural, educational, environmental, technological and institutional are created at the Pa Enua level and aggregated at the national level | Separate and non-integrated partial data sets | 100% Completed Under BSRP Project. Currently being used to upload/submit DRM Household Surveys/Data from the Pa Enua. | An integrated and inclusive data base is established one year from implementation of the programme
Output 1: Expanded GeoPortal Disaster Risk Management Information System | Number of Pa Enua islands with baseline and updated datasets in the GeoPortal | Nil Pa Enua with baseline and updated datasets in the GeoPortal | Ongoing | All 11 Pa Enua with baseline and updated datasets in the GeoPortal
|  |  | 100% Completed AWS - CLEWS DRM Surveys DRM Plans MET Drought Reports | Three critical high level hazard risk assessment dataset in the GeoPortal
| Formalise the GIS Taskforce Meetings | No GIS Taskforce | Meetings are ongoing and on task. GIS Taskforce has been formalised. | At least 6 meetings per year
Output 2: Management response tools linking hazard risk assessments and the DRM Plans | Number of management response tools/Early Warning Systems | No management response tools | 100% Completed AWS – CLEWS DRM Plans MET Services Drought Reports Social Media CSDP NSDP JNAP II | Three management response tools
| Usage of management response tool/Early Warning System | No Management response tools | 100% Completed AWS – CLEWS DRM Plans MET Services Drought Reports Social Media CSDP NSDP JNAP II | Monthly usage of management tools
| New open source or commercial App obtained for the GeoPortal | No App | 100% Completed Tablet Tools for DRM Surveys AWS Smart App Beta Testing | At least one App is obtained and used
| Climate Early Warning Systems are operating on Nassau and Suwarrow | No Climate Early Warning Systems on Nassau and Suwarrow | Currently in procurement stage. | Climate Early Warning Systems are installed and operating on Nassau and Suwarrow
Output 3: Robust Pa Enua DRM Plans and capacity building | Number of Pa Enua DRM Plans updated to 2017 National DRM Plan | One Pa Enua DRM Plan (Atiu) updated to 2017 National DRM Plan | This is completed and currently being strengthened and updated. | All 10 Pa Enua DRM Plans updated to 2017 National DRM Plan
| Number of Geo Portal Officers trained on each island by Gender | No officers | Training is targeted for 2020 | A minimum of one on each island including equal number of women
| Develop user and administration manual for the GeoPortal | Number already trained – (baseline established at inception) | Workshops have been conducted in Atiutaki, Atiu and Mauke with over 50% participations by women. | A minimum of 1 training workshop on each island including equal number of women
Outcome 2: Strengthened drinking water security including increased institutional capacity and coordination for integrated water management. | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought | Existing Water Capacity for each Island as identified in the Island Profiles | The following number of 45,000 liter water tanks have been repaired on : Penrhyn -8, Palmerston 3, and Nassau 2, a total of 585,000 liters storage capacity on three islands | 20% increase in safe water over Baseline
| Number of communities that maintain safe drinking water supplies to meet basic needs at all times including during periods of drought |  | All 11 inhabited islands maintain safe drinking water systems but these are slowly being improved through the strenghening Public Health monitoring and testing of public drinking water sources on all islands
Output 1:Robust water Monitoring, reporting and assessment systems established and implemented through increased facilitation and the sharing of knowledge | Number of Water Committees | None | The Project have a committee in Rarotonga to over see the project. On the Outer islands the Island Councils is part of the project partners and there members also oversee the water infrastructure in their varios villages and report to Council meeting monthly | Quarterly meetings
| Number of rain gauges, rainfall harvesting surveys, water resources and storage assessments disaggregated by dataset included on the Geo Portal | % water systems complete to date (baseline established at inception) | Raingauge being upgraded on Aitutaki, Rain gauge systems existing on all islands | Quarterly increase for each island
| Number of reports available to decision makers on local monitoring and assessment information | Nil (baseline established at inception) | Draft Drought Plans are available and have been discussed with Communities on Atiu, Mauke as well as the islands communities in the Northern groups | Quarterly increase for each island
| Number of drought assessment methodologies developed and implemented and used | Nil (baseline established at inception) | Drought monitoring activities based on Water tank levels are being implemented all 10 islands. However there is a need to strengthen this area in terms of reporting and tracking consistence and timeliness | At least one for the North and One for the South
Output 2. Water Resilient Plans including drinking water safety practices | Number of these drought assessments methodologies being used to support local drought management plans | Nil (baseline established at inception) | The monitoring plans informs the Local Government of the real time island levels of potable water stock in the communites so it can prepare it self when stock starts to decrease and go down | At least one in the North and One in the south
| Number of communities and agencies trained in coping with future water security threats | Nil (baseline established at inception) | Two island Communities have been trained to cope with water security threats; Mauke and Atiu | Year on Year increase in trained communities and agencies for each island
| Number of community level drinking water safety plans (dwsp) reviewed and updated and implemented | Nil (baseline established at inception) | Aitutakis DWSP is completed. Pa Enua Public Health staff have been trained in Water Safety plan activities. Public health water safety notices are placed outside of water filling stations are common practices implemented around most outer islands | All plans reviewed and updated by Year 3 of the project
| % coverage of Schools and island communities | % existing coverage of schools and communities (baseline established at inception) | Water drinking bottles delivered to schools in Aitutaki, Mauke, Mitiaro, Penrhyn, Atiu, Rakahanga and Mangaia. This is targeted to be completed in 2020. | 100% coverage of Schools and Island Communities by Year 3 of the Project
Output 3. Allocation of Water Security Fund | Number of proposals approved and implemented | Nil | The Water Security Fund will be launched in 2020. | Full utilisation of fund by Year 3 of the programme
Outcome 3: Increased island food security resilience and preparedness for disasters | Number of irrigation system installed | Unknown. A priority for MoA to establish | 100% Completed. 25 Farmers are being supported in the Southern Group. | One farm per island in Southern Group
| Displacement of island vegetables imports | Unknown. A priority for MoA to establish | 100% Achieved with Hydroponics in Manihiki, Pukapuka and Rakahanga. Target to be strengthened to 70% achievement with the establishment of Hydroponis in Nassau, Palmerston and Penrhyn. All islands Hydroponis and Nurserys will have business plans. | 50% of vegetable imports displaced in Northern Group
| Fruit products sold in Rarotonga | Unknown. A priority for MoA to establish | 100% Completed. | 33% rise in fruit products sold from Southern Group
| Improved variety of staple crops | Unknown. A priority for MoA to establish | 100% Completed. | 50% of planted crops have improved variety
Output 1: Island plant and seedling nurseries | Number of operating island nurseries | A priority for MoA to establish the number of existing nurseries? | 6 of the islands have nurseries /hydroponics. (Mangaia, Aitutaki, Mitiaro, Manihiki, Pukapuka, Rakahanga) The remaining 5 islands are on target to upgrade their nurseries, establish hydroponics by the end of 2020. | One per island in the Pa Enua
| Number of nursery business plans | Nil (baseline established at inception) | 4 nurseries are now operating under the island gevernment business plan in partnership with the Ministry of Agriculture. | All nurseries have business plans
| Production capacity utilisation of island nurseries | Unknown. A priority for MoA to establish existing production capacity | 80%of all farmers in the southern group is linked to the Agriculture department nurseries. | 75% production capacity utilised per nursery
| Operating costs recovery | Unknown. A priority for MoA to establish existing operating costs | 100% Achieved. All farmers that books their seedlings at the nursery are required to pay a fee and also for fruit trees | 100% of operating costs recovered
Output 2: School gardens for the northern group islands | Number of operating school gardens | Two | Each Island is yet to receive their materials for the school garden due to transport. | One per school in Northern Group
| Number of students by gender taught science, social science and health & wellbeing units using school garden | Nil (baseline established at inception) | Ongoing. Raurau Akamatutu Workshop has worked with the schools in the Pa Enua in the PEARL Project and will continue to do so in 2020. Under the SRIC-CC Program training was provided to all schools in the Northern and Southern Group. This was extremely successful with several projects implemted by the schools on their islands. TIS conducted Science, Climate Change, Weather and Composting (Worm Farms) training. Under BSRP Au Vaine conducted Science, Climate Change and DRM training in the Schools and Community. Korero o te Orau has conducted scienc, social science, health and wellbeing workshops in the schools and school holiday programs. The PEARL project will build on all this workshops/capacity building for our schools. | 50% of school population annually
Output 3: Tropical orchards technical support for Southern Group islands | Number of orchard with technical support | Two | 16 assisted Orchard in the southern group since 2019, funded by PEARL. | 12 orchards assisted in Southern Group
| Number of community tree management plans implemented | Nil (baseline established at inception) | ongoing | One per island in Southern Group
| Productivity of orchards | Unknown. (baseline established at inception) | 5 orchards supplying Rarotonga market since 2019. | 50% productivity improvement in the Southern Group
Output 4: Pa Enua Agriculture Knowledge Sharing Platform | Number of island integrated in AgIntel | Nil | 5 islands now have AnINTEL in the southern group providing data every quarter (3months) of the year. | 11 islands
| Number of Pa Enua farmers using E-Agriculture information | Nil | Two booklets on crops management developed for farmers and school students. Traditional and modern techniques collected from all southern group islands and will be written before putting it in an electronic system. | 50% of Pa Enua farmers
Output 5: Allocation of Economic Resilience Fund | Number of proposals approved and implemented | Nil | The Economic Resilience Fund will be launched in 2020. | Full utilisation of fund by Year 3 of the programme

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | So far progress have been positive, clear communication of project intension are important for improved delivery.The initial consultation on the project revealed that in terms of water security, safety and drought preparedness, there is a need to increase adoption of the use of Concrete tanks compaired to PE tanks. Anothe important information presented is that the islanders also like the project to consider providing them with Concrete tank moulds, This will allow then to continueing their own tank contruction works after the project is completed a part of their own self help initiatives
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | No delays thus far on implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The flexibility to move and shift the program between different island when one is busy with other commitments also play a part in im proving delivery. The interest shown by the community to the Project training has been overwhelming.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | The current activities like training and awareness raising did not require environmental and social safe quard measures to be implemented
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender consideration are always considered. There are no gender based issues noted during the implementation phase and up to date. Gender participation is critical to have community participation and consultation. Women play an important role in transferring traditional pratices and knowledge. Young women participation has been key to the Island Surveys conducted. There has been over 50% of women participation in workshops and surveys. The project is working with Miss Cook Islands Association, Au Vaine (Cook Islands Women) Association and the Cook Islands Civil Society for inclusion of women in projects/workshops/surveys.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | Adaptation Fund
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | COK/NIE/Multi/2017/1
Implementing Entity | Ministry of Finance and Economic Management
Type of implementing entity | NIE
Country | Cook Islands
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 5000 | 550 | 4450 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Hurricane | 2: Partially effective | Total | 5000 | Hurricane | 3: Moderately effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Water management | Local | 2: Undertaking or updating of assessments in progress | 3 | Water management | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 10 | 2: Monitoring and warning service | Geographical coverage | Regional | 10 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 9 |  |  | Number of municipalities | 12 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 539 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Other | 2: Low capacity | Public | National | Other | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Other | 2: Low capacity | 550 | National | Other | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Other |  | 50 |  | Other
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 550 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 3: Partially aware |  | 2 | 20% to 39% | 3: Partially aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | handbooks | National |  | 10 | Handbooks | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Other | National | 2: Partially responsive (Lacks most elements) |  | Other | National | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Multi-community |  | Water management | 2 | Multi-community |  | Water management
|  | 0 | National |  | Disaster risk reduction | 11 | National |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 1000 | 50% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  |  | 539 | 50% | From 10% to 20% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Multi-sector | Community-based adaptation | 20 | Physical capital | Multi-sector | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 4: Most |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 11 | Other | National | Public policy | 11 | Other | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 11 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 11 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Disaster risk reduction | Undertaking innovative practices | 2: Partially effective | 3 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on I21: Melina Tuiravakai: 50 % of total population (i.e population of 11 Pa Enuas)
Note on K27: Melina Tuiravakai: Raurau Akamatutu Workshop in Atiu, Mauke have incorporated Hurricane Prepareness. Radio, TV and Print Media promote Hurricane Awareness/Prepareness. All Local telephone books include sections on Hurricane Map Tracking and Awareness.Prepareness
Note on H57: Melina Tuiravakai: Components 1/2/3 At least 39 government staff with responsibilities for CCA and DRR in the Pa Enua have received training, consistent with the creation of a learning needs mechanism/process. 500 key stakeholders and community were invovled in the Raurau Akamatutu Workshop/Surveys/Consultations and recieved Resource Kit on Flashdrives on CC and DRM.
Note on H61: Melina Tuiravakai: Civil Societys in the Pa Enua, Island Governments, Schools and community have direct access through Component 1 GEO Portal, Component 2 Water Fund/Water Testing Equipment/Water Bottles Access to Cllean drinking water Component 3 Schools and Economic Resilient Fund (Output 3.5)