## Overview
Programme Performance Report (PPR)
| Period of Report (Dates) | November 1, 2014 - October 31, 2015
| Programme Title: | ENHANCING THE RESILIENCE OF THE AGRICULTURE SECTOR AND COASTAL AREAS TO PROTECT LIVELIHOODS AND IMPROVE FOOD SECURITY
| Programme Summary: | Jamaica is vulnerable to climate related hazards, in particular hurricanes, floods, storm surges and droughts, due largely to its geographical location and the exposure of social and economic assets in coastal areas. This situation is made worse by the country’s low adaptive capacity especially in the climate sensitive sectors of the economy. The agriculture sector and coastal resources are among those at greatest risk, given their significant contribution to the country’s GDP and to the labour force. These two sectors were also highlighted as among the five most vulnerable to climate change in assessments conducted for Jamaica’s Second National Communication (SNC) to the United Nations Framework Convention on Climate Change (UNFCCC). Additionally, Vision 2030 Jamaica – National Development Plan articulates climate change adaptation as a priority for not only a healthy, natural environment, but also for achieving developed country status by 2030. The activities identified in Government of Jamaica Adaptation Fund Programme (GOJ/AFP) are drawn from the adaptation priorities that were identified in the vulnerability and adaptation assessments for the agriculture and coastal resources sectors. The programme focuses on environmental and natural resource management activities; namely, coastal rehabilitation, inland flood and erosion control, and land and water management. The Overall Objective of the GOJ/AFP is to protect livelihoods and food security in vulnerable communities by: • improving land and water management for the agricultural sector • strengthening coastal protection; and • building institutional and local capacity for Climate Change Adaptation and Natural Resources Management
|  | Component 1 - Increasing the climate resilience of the Negril Coastline: Hard engineering structures (breakwaters) will be installed to control coastal erosion in the most vulnerable sections of the Negril coastline to protect the beaches from climate related hazards such as seal-level rise and intense storms. Location: Long Bay, Negril Component 2- Enhancing climate resilience of the agricultural sector by improving water and land management in select communities Location: Manchester, Trelawny, St. Mary, St. Ann, St. Catherine, St. Thomas and Clarendon Component 3 - Improving institutional and local level capacity for coastal and agricultural adaptation and awareness raising for behaviour modification | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | JAM/NIE/Multi/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Planning Institute of Jamaica (PIOJ) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implimenting Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jamaica | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Component 1 - Increasing the climate resilience of the Negril coastline Location: Long Bay, Negril Component 2- Enhancing the climate resilience of the agricultural sector by improving water and land management in select communities Location: Manchester, Trelawny, St. Mary, St. Ann, St. Catherine, St. Thomas and Clarendon Component 3 - Improving institutional and local level capacity for coastal and agricultural adaptation and awareness-raising for behaviour modification Location: Westmoreland/Hanover; target communities in Component 2 | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
| Programme Milestones |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-29
IE-AFB Agreement Signature Date: |  | 2012-07-23 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-02 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | Sept-December 2015
| Terminal Evaluation Date: | 01/03/2016 (original programme end date) Programme extension to be requested by NIE
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Documents/reports/brochures/articles prepared during the reporting period: Fact Sheets/FAQs prepared on all 3 programme components Signage affixed to storage tanks in several parishes/communities - serves to identify AF/partners with on the ground activities Telephone Interview with Gleaner on March 11, 2015. Related article published on March 19, 2015. 1. Dialogue still on about Negril breakwater project – http://jis.gov.jm/dialogue-still-negril-breakwater-project/ Newspaper article on GOJ/AFP support to successful crop yield (Jamaica Observer - March 19, 2015) 2. Agricultural sector benefiting from Adaptation Fund – http://jis.gov.jm/agricultural-sector-benefitting-adaptation-fund/ 3. Adaptation fund programme building climate change resilience - http://jis.gov.jm/adaptation-fund-programme-building-climate-change-resilience/ Agriculture Sector Benefitting from Adaptation Fund (JIS - April 11, 2015) - Partnered with Ministry of Water, Land, Environment and Climate Change (MWLECC) and placed advertorial in the Jamaica Observer World Earth Day supplement April 22,2015 Newspaper Article (Jamaica Gleaner - May 8, 2015) Report on sea-level rise and storm surge modelling; KAP survey Environmental Impact Assessment (EIA) Report; Natural Resources Valuation Report Signs (with AF logo) erected in target communities to identify demonstration plots/ land husbandry activities supported by the GOJ/AFP | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.adaptja.pioj.gov.jm | Democratic Republic of the Congo
Denmark
| Programme contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
Government DA
| Name: | Albert Daley, Climate Change Division, Ministry of Water, Land, Environment & Climate Change
| Email: | a.daley@mwlecc.gov.jm
| Date: | 2014-07-01
| National Implementing Entity |  | El Salvador
| Name: | Shelia McDonald-Miller | Equatoral Guinea
| Email: | smmiller@pioj.gov.jm | Eritrea
| Date: | 2012-12-03 | Estonia
| Executing Agency |  | Ethiopia
| Name: | Ministry of Agriculture and Fisheries | Fiji
| Email: |  | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | National Environment and Planning Agency | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | National Works Agency | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Ministry of Tourism & Entertinment | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D44: Shelia Mcdonald-Miller: Ms. Bernard to confirm date of appointment of Mr. Daley

## FinancialData
Financial information: cumulative from programme start to October 31, 2015
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of October 31, 2015 |  | 1858791
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | Programme Component | ITEM / ACTIVITY / ACTION | AMOUNT | 110
| Component 1: Increasing the climate resilience of the Negril coastline | Installation of breakwater structures (preparatory activities including design and modelling; EIA process) | 4758.3386
|  | Environmental monitoring (NEPA) | 18008.9182
|  | Project Execution (NWA) | 2710.1818
| Total Component 1 |  | 25477.4386
| Component 2: Enhancing the climate resilience of the agricultural sector by improving water and land management in select communities | 2.1 Establishment of Micro-dam | 0
|  | 2.2 Establishment of small scale irrigation facilities | 478391.8
|  | 2.3 Implementation of rainwater harvesting and drip irrigation systems | 8671.5545
|  | 2.4 Establishment and rehabilitation of soil conservation and land husbandry infrastructure | 57106.9455
|  | 2.5 Establishment of Demonstration Plots | 4782.8182
|  | Project Execution | 40266.1818
| Total Component 2 |  | 589219.3
| Component 3: Improving institutional and local level capacity for sustainable management of natural resources and disaster risk reduction in the targeted vulnerable areas | Training of Local Communities in Disaster Risk Reduction and Natural Resources Management | 47798.5636
|  | Development of Climate Risk Atlas | 64851.1364
Development of Adaptation Plans for vulnerable areas along Negril coastline
|  | Establish farmer field schools to develop solutions and demonstrate good practices | 72691.8182
Conducting workshops and farmer training in climate smart agriculture
|  | Climate change awareness and education programmes developed and implemented in project communities | 17250
Project Execution
| Total Component 3 |  | 202591.5182
| Programme Implementation (NIE) |  | 148486.479
|  | TOTAL | 965774.7358
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COSTfor new project year | Est. Completion Date
Component 1
|  | Approval Process for Construction Contractor | 0 | 2016-04-30
|  | Contractor mobilization and Prepation of stockpile site |  | 2016-10-31
|  | Environmental Monitoring |  | 2017-12-31
|  | Contruction of breakwaters |  | 2017-10-31
|  | Project Execution |  | 2017-10-31
|  | Subtotal | 0
Component 2
|  | Implementation of Rain water harvesting and drip irrigation systems | 354909.0909 | 2017-03-31
|  | Small Scale Irrigation and Productivity Schemes | 822727.2727 | 2017-04-30
|  | Land Husbandry Infrastructure in N. Clarendon | 163636.3636 | 2017-05-31
|  | Training in Proper Water and Land Management | 169090.9091 | 2017-06-30
|  | Maintenance of Demonstration Plots in Upper Rio Minho Watershed | 37272.7273 | 2017-07-31
|  | Climate smart Farmer Field School | 36363.6364 | 2017-08-31
|  | Project Execution | 118900 | 2017-09-30
|  | Subtotal | 1702900
Component 3
|  | Training of Communities in DRM | 33309.1091 | 2016-03-31
|  | Development of Guidelines and standards for Beach Restoration | 63636.3636 | 2016-10-31
|  | Adaptation Plans | 67272.7273 | 2016-12-01
|  | Risk Atlas Development/Finalization | 26000 | 2016-07-31
|  | Project Execution | 7181.8182 | 2016-10-01
|  | Subtotal | 190218.2
|  | NIE Fee | 203400 | 2016-10-01
|  | TOTAL | 2096518.2
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | Co-financing is not applicable to this programme
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on F9: Shelia Mcdonald-Miller: includes $23557 PFG
Note on F39: Shelia Mcdonald-Miller: Projected cost dependent on financial proposals expected to be submitted mid-January 2016

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial: budget over-runs/under-spend; mis-use of funds; inflation/ currency depreciation leading to increased costs for goods/services | Low | Budget planning workshops; Regular reviews of EE reports, environmental scanning to keep abreast of latest developments. Comprehensive Memoranda of Understanding (MOU) signed with Executing Entities to establish operational modalities; work plans/budgets must be approved by the NIE/ Programme Steering Committee (PSC) prior to disbursement of funds; The NIE developed financial reporting templates/procedures and provided training to partners in use thereof; convened regular programme review meetings and continued periodic monitoring visits to Executing Entities locations.
Environmental: natural hazards (flood, drought, storms/hurricanes); pests and diseases. | High | Contingency planning; education programmes and pest/disease management Partners and communities are advised to design implementation plans and schedules to take account of the peak 'adverse climatic events' period (June-November). Specialized agencies (ODPEM, MET Service, etc.) provide information on how to respond in the event of such occurrences. Ongoing pest/disease control programmes are carried continuously by the Ministry of Agriculture & Fisheries. Environmental Impact Assessment conducted and NRCA conditions imposed for construction-related environmental issues.
Stakeholder Buy-in | Moderate | Participation of all major stakeholder groupings was secured during the programme development phase and continues to be a high priority during implementation. During the current implementation cycle there has been information, sensitization and mobilization sessions both at the level of the programme team as well as among target communities. Special care is taken to involve local community groups and civil society organisations in programme activities. The programme continues to receive the endorsement and support of the government in general and Climate Change portfolio Ministry. Component 1 continues to require special attention as a group of (mostly) hoteliers prefer the option of sand nourishment and have opposed the construction of the breakwaters. The project received the ‘green light’ from Cabinet and the agencies concerned. Subsequently, the NIE enlisted the services of the Disputes Resolution Foundation to lead the process of mediation and remains committed to deepening stakeholder involvement in the target communities. There is public information dissemination to keep stakeholders informed on a wider level beyond the Executing Entities and target communities. This has been done via interviews with local media houses (print and electronic), production/wide dissemination of brochures; linkages with key national stakeholders and participation in related partner forums to improve understanding and commitment.
Multiple Executing Entities | Low to Moderate | The NIE has signed a MOU with Executing Entities which clearly outlines the roles and responsibilities of the respective parties. Focal points have been identified within each agency to improve the coordination and communication process. The establishment of the Programme Steering Committee (PSC) with regular meetings convened by the NIE ensures that a formal governance structure is in place and fully operational. This allows for the provision of strategic oversight and coordination of interventions at the technical level. Administratively, the PMU continues to successfully organize and coordinate activities involving stakeholders across different components, for example, National Stakeholders Consultations and Team Leaders Meetings. Generally, there is growing inter-agency co-operation among the Executing Entities evidenced by the inclusion of members from other agencies on several project committees to lend their expertise and support.
Procurement Delays | Moderate | In order to expedite the execution of planned activities, the responsibility for procurement has been de-centralized to the respective Executing Entities. The PMU continues to support all Executing Entities in the completion and approval of procurement plans with appropriate templates as per the GOJ Procurement Guidelines. This enables the establishment of realistic lead times and proactive identification of special conditions such as required permits and seasonality of required materials/resources. Early in the start-up phase of implementation, provision was made by the NIE to build the capacity of Executing Entities and partner agencies. To this end, there has been training in the relevant (GOJ) procurement guidelines and procedures aimed at enhancing accountability and institutional strengthening. Generally, there is cross-functional review of TOR development to ensure realistic scope and time alignment, especially for highly technical/specialized procurement. Additionally, there is a 'no-objection' process instituted by the NIE which provides the requisite guidance and oversight thus ensuring that there is minimal delay in complying with relevant procurement guidelines
Implementation/ Operational: Delays in project implementation schedule | Moderate | Implementation planning is coordinated by the PMU annually (with iterations during the year as better information becomes available) in order to meet target dates. Even though stakeholders’ interests are aligned with the objectives of the respective programme components, the NIE has found that the EEs apparently continue to set overly optimistic schedules (based on best case scenarios) which are then difficult to maintain. The PMU therefore continues to work with EEs to: • Establish clear milestones and measurable performance indicators to ensure that staff and consultants meet their obligations on time. • Arrange formal programme reviews on a regular basis (eg., via quarterly PSC meetings) • Set realistic expectations and formulate recovery plans where activity completion is behind schedule.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risks associated with the complexity of maritime works (breakwater structures) | Moderate to High | Proper feasibility, scientific and environmental assessments have been undertaken, including Environental Impact Assessment, Natural Resources Valuation; international procurement conducted to garner the best available expertise. Detailed conditions attached to Beach Licences to mitigate and minimize risks identified during EIA process. National (specialized) agencies to provide technical oversight and environmental monitoring; clear technical specifications included in tender documents for construction; local monitoring committee to be formed to ensure compliance with environmental conditions and building standards.
Low disaster risk perception of some target communities | Low | A mobilization plan was developed and implemented in 2015 leading to improved awareness and more positive responses from the target communities. Increased communication and awareness-raising activities relating to climate change impacts have been undertaken by the programme as well as on a national level and have led to a more informed populace.
Stakeholder resistance against Breakwater | High | Stakeholder consultations continued during the reporting period: - On November 10, 2014 NEPA convened a follow-up public meeting (first one was July 29) at the Negril Community Centre to inform stakeholders of 2 important changes based on their feedback to the EIA report. The changes are (a) the mouth of the river will not be dredged as originally proposed, and (b) the staging area (construction campsite) will be removed following the construction activities. There were 47 persons in attendance and members of the group reportedly expressed their appreciation for the follow-up meeting which showed that their concerns were being taken seriously. - On November 28, 2014, the Natural Resources Conservation Authority (NRCA) Board approved three permits applied for by the National Works Agency after considering all relevant comments from the Negril stakeholders as well as the wider public. The permits included several conditions for addressing the community’s concerns. Key stakeholders were informed via letter in December 2014 and the general public via media releases from NEPA. - February 2015 the NIE team met with (i) Hon. Minister of Finance & Planning, and (ii) number of other public officials including two government ministers (both Members of Parliament for the Negril area) regarding the problems affecting the component. The Director-General of the PIOJ invited the opposing stakeholders to a meeting to discuss their concerns re the project; a reply was received in early March indicating that the proposed dates were not convenient for the Negril team. - Due to the prolonged nature of the protests, the matter was elevated to the level of the Cabinet. A Cabinet Decision was rendered in April 2015 which, inter alia, endorsed the implementation of the project and authorized a timed mediation process with the opposing stakeholders. In our efforts to give effect to the Decision, the NIE wrote to the Dispute Resolution Foundation (DRF), a private voluntary organisation, to enlist their assistance in leading the mediation process with a view to resolving the concerns raised about the project. The DRF wrote to both parties in June, setting out their guidelines for effective mediation and proposing dates of July 16-17 for mediation to begin. The PIOJ accepted the dates; however, the Negril team was reportedly unavailable. In October the DRF made another attempt and proposed 3 sets of dates to begin mediation to which the Negril team responded that none of the dates proposed were convenient and they would not be available before 2016. The NIE has asked the DRF to continue trying for a mutually convenient date. -In April/May 2015 the NIE responded to requests for information from the Office of the Public Defender (OPD) and Office of the Contractor-General (OCG) in relation to complaints made by Negril stakeholders. Later follow-up efforts by the NIE (Oct 2015) with the OCG and OPD yielded the response that their review was still ongoing. In the meantime, PSC members from the community have been requested to share project information with stakeholders to keep them informed.
Executing Entity's readiness to implement, including availability of human resources and capacity for financial management | Low | Following the official launch and inception report, there was significant lag time in actual start-up among the Executing Entities. Accordingly, the NIE continued to provide support to the Executing Entities to ensure the improvements in the implementation framework. Entities have now confirmed the availability of physical facilities and availability of adequate and/or dedicated staff and other necessary resources. Regular meetings and other monitoring activities aimed at minimizing any negative impact on the programme.
Adverse publicity generated from continued push back/media campaign (Component 1) | Moderate | Mitigating measures include: - Media engagement: comprehensive briefing of key opinion leaders and writers in the media on the purposes and achievements of GOJ/AFP. Two editorial roundtables with the national dailies, the Gleaner and the Jamaica Observer. The Jamaica Observer’s lead story on March 3 re the coastal erosion of Negril provided some insights into the proposed GOJ/AFP intervention and the thinking behind it. JIS Think Tank session. NEPA continues to expand the media conversation by providing generic public education information on coastal erosion. The objective is to assist the public in understanding the current and anticipated environmental impacts of CC and the necessity of the proposed interventions in combatting the harmful effects. - Vignette and brochures produced and disseminated with specific information on what the project is about and how it will help -- this information has been widely shared (including print and electronic media) in the hope of raising awareness, enabling objective review and reasoned decision-making. - Attempts made by NIE to directly engage/consult with stakeholders. Every effort is being made to keep the public informed and disseminating the GOJ/AFP message.
Possibility of General Elections in 2016 may affect mobilization/ timing of some activities | Moderate | Contingency planning - try to schedule activities out of the critical period as much as possible.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risk mitigation measures employed all contributed to reducing most of the relevant risks. One notable exception is the continuing opposition to the building of the breakwater structures (Component 1) by a group of stakeholders in Negril – preferring instead the option of beach nourishment. General mitigation measures undertaken included: - Work plans/ budgets developed by Executing Entities and approved by NIE/PSC prior to undertaking activities for respective components - Regular meetings with executing partners (physical and virtual); tiered reporting systems instituted; regular feedback provided re gaps identified in order to facilitate improvements - Engagement of short-term support and adaptive management strategies to minimize implementation delays and assist in achieving planned outputs - Meetings convened by NIE with senior management of Executing Entities to ensure high-level awareness, involvement and assistance in resolving implementation challenges. - Regarding the construction of the breakwater structures: o in November 2014 three permits were issued by the Natural Resources Conservation Authority (NRCA), the local national authority with responsibility for the conservation, protection and proper use of Jamaica’s natural resources. The NRCA attached several conditions to the permits aimed at addressing stakeholders’ concerns identified in the EIA process, and for the protection of the environment during and after the construction phase. Stakeholders were informed via letters as well as public notices disseminated via local media. Compliance with these conditions is to be monitored by NEPA. o In late April 2015 the Cabinet issued a Decision which endorsed the importance of the project to Jamaica’s efforts at shoreline protection and instructed that mediation be conducted with dissenting Negril stakeholders. Since May 2015 the NIE, through the Disputes Resolution Foundation (DRF), has taken steps to initiate the mediation process by issuing invitations to the group. However, to date no meeting has been held as the stakeholders have not been available. As the involvement of key local and national stakeholders is important enhance transparency and secure buy-in, the NIE and DRF will continue efforts to bring the parties to the table. o A local monitoring committee is to be formed to ensure the direct involvement of the community throughout the process Given the experiences of the past years, the EE are now in a better position to perform according to expectations.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Stakeholder Engagement/Consultations |  | Stakeholders Effectively Engaged National Stakeholders Consultation held |  | Stakeholder consultations continued during the reporting period: The PMU attended a meeting of the Negril Resort Board, on November 6,2014 where a report on storm surge modelling and sea level rise scenarios for the Negril Climate Risk Atlas was presented. On November 10, 2014 NEPA convened a follow-up public meeting (first one was July 29) at the Negril Community Centre to inform stakeholders of 2 important changes based on their feedback to the EIA report. The changes are (a) the mouth of the river will not be dredged as originally proposed, and (b) the staging area (construction campsite) will be removed following the construction activities. There were 47 persons in attendance and members of the group reportedly expressed their appreciation for the follow-up meeting which showed that their concerns were being taken seriously. - On November 28, 2014, the Natural Resources Conversation Authority (NRCA) Board approved three permits applied for by the National Works Agency after considering all relevant comments from the Negril stakeholders as well as the wider public. The permits included several conditions for addressing the community’s concerns. Key stakeholders were informed via letter in December 2014 and the general public via media releases from NEPA. In February, the Director-General of the PIOJ invited the stakeholders to a meeting to discuss their concerns re the project; a reply was received in early March indicating that the proposed dates were not convenient for the Negril team. Due to the prolonged nature of the process the matter was elevated to the level of the Cabinet. A Cabinet Decision was rendered in April 2015 which, inter alia, endorsed the implementation of the project and authorized a timed mediation process with the opposing stakeholders. In our efforts to give effect to the Decision, the NIE wrote to the Dispute Resolution Foundation (DRF), a private voluntary organisation, to enlist their assistance in leading the mediation process with a view to resolving the concerns raised about the project. The DRF wrote to both parties and set out their guidelines for effective mediation and has since made attempts to convene meetings. So far, none of the dates proposed have been convenient for the dissenting stakeholders. The NIE remains optimistic that there will be a positive outcome to the mediation process. Brief provided to the Dispute Resolution Foundation regarding mediation process with Negril stakeholders (Component 1). Intensive follow-up activities continued with the Dispute Resolution Foundation re dates for proposed mediation with Negril stakeholders. The Programme collaborated with Friedrich Ebert Stiftung and the UWI Institute of Gender & Development Studies, Mona Unit, to facilitate a teach-in on ‘Gender and Climate Change’ for beneficiaries from target communities in rural Jamaica. An overview of the GOJ/AF Programme was presented by the Programme Manager and key issues relating to climate change adaptation were clarified. The Annual Stakeholders Consultation (NSC) was held at Alhambra Inn, Kingston, on October 23, 2015. The event saw the attendance/participation of more than 70 stakeholders in attendance from parishes of St. Thomas, Clarendon, St. Catherine and St. Ann. The NSC is part of the overall efforts of raising awareness of the stakeholders to the importance of climate change adaptation and fostering a sense of personal responsibility. It also aims to strengthen linkages and an increased sense of ownership among beneficiaries. | S
| Governance and Oversight - Programme Implementation |  | Governance and Oversight Framework established and functioning effectively |  | The Programme Steering Committee (PSC) continued to serve as the main mechanism for the provision of technical advice and oversight during the period under review. Four (4) PSC meetings were convened in 2015 -- three (3) regular and one (1) extra-ordinary. The PSC membership is comprised of persons from a cross-section of stakeholders with technical interest in and knowledge of natural hazards, risk and climate change issues; including community representatives, relevant government Ministries, Departments and Agencies, the Private Sector Organization of Jamaica, Academia, and NGO partners. The PSC has effectively assisted with resolving strategic level issues and addressing risks that have the potential to adversely affect the implementation of the programme. The PMU continued with monitoring visits to all Executing Entities to verify reports submitted by Programme Partners against source documents. Arising from these visits, feedback was provided, including recommendations for improvement, where necessary. Several field visits were undertaken by members of the PMU to meet with existing/proposed beneficiaries in target communities. These visits served to confirm that work (on-the-ground) and results conformed to requirements. The PMU continued the series of regular team meetings (six such meetings during the reporting period) with executing partners to support the implementation process. The meetings provided a platform for knowledge sharing while fostering inter and intra-agency collaboration. • External audit conducted by Ernst & Young, Chartered Accountants (EY), covering the period from programme inception to October 31, 2014. • Mid-Term Review underway; interviews /focus group discussions held with several stakeholders. Draft report being reviewed for finalization. In keeping with the terms of the Memoranda of Understanding between the NIE and Executing Entities, more than 20 ‘no-objection’ requests from partners were processed by the PMU during the period under review. The objective of this review is to ensure that the procurement process is fair and transparent, and complies with the requisite procurement guidelines. In April/May 2015 the NIE responded to requests for information from the Office of the Public Defender (OPD) and Office of the Contractor-General (OCG) in relation to complaints made by Negril stakeholders. Later follow-up efforts by the NIE (Oct 2015) with the OCG and OPD yielded the response that their review is still ongoing. The NIE kept its portfolio Minister as well as the AF Secretariat updated on significant occurrences throughout the project year. | HS
| Awareness Raising and Visibility |  | Engagement of Consultant and Implementation of Communication Plan |  | The NIE sponsored PIOJ’s staff participation in Forest Trek 2015 -- an annual event which aims to bring awareness to the public on proper environmental management. Participated in INMED – Harvest the Future Symposium in Montego Bay, June 2015. A presentation was made by PIOJ’s Director-General on ‘Building Resilience to Climate Change Through Agricultural Innovation’. Harvest the Future is an annual gathering designed as a platform for sharing the latest advancements and initiatives in small scale climate-smart agriculture. Participants included farmers, fisherfolk, schools, youth groups, women-led cooperatives, private- and public-sector leaders and development practitioners. At this very integrated forum, GOJ/AF Programme brochures and other collateral material were distributed, vignettes shared and agricultural produce from AF-supported farmers was on display. The impact of the GOJ/AFP was creatively documented in three film vignettes of the success of individual beneficiaries, communities and in activities on the ground for the respective components, mainly under Component 2 (Agriculture) of the Programme, i.e. ‘Donna’s Hope’; ‘Resilient St. Thomas Farmers’; and ‘Breaking the Tide, Renewing the Land’ corporate. The NIE also participated in the Jamaica Observer’s Editors’ Forum with representatives of Executing Entities on March 2,2015. Other media engagement included telephone interview with Gleaner on March 11, 2015 - a related article was published on March 19, 2015. It is significant to note that GOJ/AFP messaging was carried on over 20 radio stations in Jamaica, as well as on the 3 national-free-to-air TV stations (TVJ, CVM and LOVE TV), and over 40 cable stations arising from Jamaica Information Service (JIS) Think Tank Session on April 2, 2015. There was also pick-up in newspapers and social media channels. The following were produced by the JIS: 3 Print news stories: o Dialogue still on about Negril breakwater project – http://jis.gov.jm/dialogue-still-negril-breakwater-project o Agricultural sector benefiting from Adaptation Fund – http://jis.gov.jm/agricultural-sector-benefitting-adaptation-fund o Adaptation fund programme building climate change resilience - http://jis.gov.jm/adaptation-fund-programme-building-climate-change-resilience Radio: o 1 news story aired on April 13, 2015 on over 17 radio stations in Jamaica. o Two radio features, one aired during Calling Farmers on April 16, 2015, the other aired during the JIS radio programmes on May 21, 2015. See links: http://jis.gov.jm/media/MWLECC-11-20150521.mp3 http://jis.gov.jm/radio_programs/governmentjamaicaadaptation- fund-programme Television: One GOJ/AFP feature was produced and aired on April 16 during the Jamaica Magazine programme aired on TVJ and CVM and other local cable stations during time allotted for government broadcasts – see link to feature: https://www.youtube.com/watch?v=W5qckpy-dj8 Additionally, the tape of the ‘Think Tank’ session was sent to TV stations. Both CVM and TVJ aired stories in their news package on issues arising from the session. The news story was aired on TVJ on April 3, 2015 and CVM on April 4, 2015. The vignettes were also shared at AF NIE Climate Finance Seminar, Washington DC, July 2015. Two members of the PMU -- Director and Programme Manager -- participated in Panos’ case study on July 23, 2015 relating to stakeholder engagement with particular emphasis on Negril. In July/August 2015 the GOJ/AFP supported environmental summer camps for over 40 vulnerable (inner city) youngsters hosted by the Multi-care Foundation. Presentations on climate change adaptation were made by PMU and other PIOJ staff as well as MOAF colleagues. Participated in MWLECC’s pre-COP Public Engagement Sessions in the Corporate Area (Kingston & St. Andrew) and Mandeville in August and September 2015. Partnered with Vision 2030 Secretariat to participate in Jamaica’s first Climate Walk hosted by Environmental Solutions Limited (October 2015). Participated as an Exhibitor in the JAREEACH Climate Change Youth Conference at the Jamaica Conference Centre on September 25, 2015. Programme information was share with approximately 100 students who visited our display. PSC members have distributed project information (including brochures) in target communities. Information has also been shared with the local planning authorities in Negril and the Negril Resort Board (which membership includes the Jamaica Hotel & Tourist Association JHTA). | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shelia McDonald-Miller
| Email: | smmiller@pioj.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Issues of collaboration and capacity constraints among programme partners have improved through the intervention and assistance of the NIE and PSC; this has contributed to the strengthening of project management capacity. Notwithstanding the challenges affecting component 1 (stakeholder dissent) and the prolonged drought which stymied execution of some agriculture-related activities, the pace of implementation has shown encouraging signs of improvement during the period under review. The PIOJ continues to work with our partners to ensure that the overall direction of the programme remains in line with the agreed targets. Dialogue with the respective stakeholders to identify alternative solutions is a regular feature of NIE/EE interaction. The GOJ/AFP continues to establish synergistic relationships with other organisations and initiatives/projects while leveraging existing resources - this has helped to improve the value-added to our beneficiaries. The governance structure remains strong and there is buy-in at the political level. Engagement of the dissenting group is being actively pursued via mediation led by the Disputes Resolution Foundation of Jamaica in the hope that the issues will be satisfactorily addressed. Going forward, the NIE will ensure the implementation of any recommendations for continued improvements which may be identified by the Mid-Term Review currently underway. It will be necessary to seek an extension of time beyond the current expiration date to ensure completion of the programme and attainment of the agreed objectives.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity | Component 1 Increased climate resilience of the Negril coastline |  | Completion of Environmental Impact Assessment. Procurement of consultants and contractor mobilization for construction of breakwaters; environmental monitoring of licenses and permits. |  | Modelling studies were done in December 2013 at the Centre of Applied Coastal Research Ocean Laboratory at the University of Delaware, USA. Based on performance and testing, the 2 proposed breakwaters have been designed to withstand event with 100-year return period The Environmental Impact Assessment (EIA) of the breakwater structures to be built in Negril was published and opened for comments by the public. It involved a survey of 355 stakeholders and 4 focal group meetings in Negril between January-March 2014. Public presentation was convened on July 29, 2014. Following this, the public had a period of 30 days within which to make additional submissions. In November 2014, the NRCA approved three licences to allow for construction of the breakwaters. These permits had conditions attached to address environmental and other concerns identified during the EIA process. Key stakeholders in Negril were informed via letters issued by NEPA; the public was informed via media releases. Source material has been identied; the NWA has since updated the relevant Tender documents to reflect the permit conditions and RFPs have recently been issued to pre-qualified contractors. Due to opposition from a group of stakeholders, the pace of implementation has been negatively impacted, however, efforts are continuing to be made to engage in mediation with the aggrieved stakeholders, in order to negotiate a workable solution. | MU
| Component 2 Enhanced climate resilience of the agricultural sector through improved water and land management in select communities |  | Micro Dam established; land husbandry curriculum developed; demonstration plots established and farmers have access to increased irrigation water and producion schemes |  | All five demonstration plots for land husbandry practices have been substantially (> 90%) established and farmers continue to receive training in soil conservation and other climate-smart agriculture techniques. Approximately 1300 farmers successfully completed training in skills, knowledge and techniques on sustainable land husbandry practices. The draft of the Farmer Field School curriculum has been produced by RADA and plans are in place for training to be accelerated in 2016. Due to land tenure and geo-technical issues and following several attempts to identify potential alternative location sites, there has been a scope change in relation to the establishment of a micro-dam in N. Manchester. Alternatively, several water retention structures have begun to be constructed/rehabilitated to serve the needs of the respective communities. A concrete tank with a capacity of 16000 gallons has been rehabilitated in Bushy Park, Manchester and supplies 15 drip irrigation systems via smaller water tanks. Fourteen (14) systems using roof catchment and tanks have been installed, including several schools which run meal assistance programmes for students. Three (3) rainwater harvesting systems using tanks and catchment have been rehabilitated. 103 gravity drip irrigation systems have been installed in 7 parishes with the direct assistance of the GOJ/AFP; another 107 have been finalized in collaboration with another climate change project. Draft designs have been completed for other water harvesting infrastructure and 1 earthen pond is in an advanced stage of completion. Five Farmer Field Schools (FFS) have been organized. Fourteen (14) farmer/ water users’ groups (WUG) have been mobilized/strengthened. A Rural Sociologist was engaged mid-2015 and has assisted in team building and facilitating the formal registration of the groups. Approximately 5 groups have since been registered with the Department of Cooperatives and Friendly Societies and several others are in various stages of the registration process. One WUG (Yallahs) has received training in conflict resolution and disputes resolution. The capacity of partner agency (RADA) was built significantly with the training of thirty (30) Extension Officers in skills, knowledge and techniques of climate smart agriculture. Positive synergies have been formed, including collaboration with Food for the Poor which provided 22 hand-tractors to farmers, thereby supplementing the resource base of the GOJ/AFP beneficiaries. More than 800 hectares of crops (onions, irish potato, hot peppers, cabbage, pumpkin, etc.) have been established across the target parishes, impacting over 2000 farmers. Significant economic benefits have resulted from these activities with over J$1B earned by beneficiaries. | MS
| Component 3 Improved institutional and local capacity for sustainable management of natural resources and in disaster risk reduction in the targeted vulnerable areas. Raising awareness for behaviour modification |  | Engagement of Training Officer and Development of Training Plan; Increase in number of residents who accept that climate risks are relevant to their community. Procurement of Consultant for Storm Surge Modelling; completion of draft adaptation plans |  | A training officer was engaged by ODPEM and training plan developed and implemented. Increased mobilization efforts helped to combat previous low community support and participation, as well as low disaster risk perception by residents. These efforts were complemented by the operationalization of the GOJ/AFP Communication Strategy and Action Plan in 2015. 50 persons (29 from Hanover and 21 from Westmoreland) were trained in standard First Aid in July 2015. A Natural Resources Management (NRM) consultant engaged and training curriculum is at advanced stage of development. Training of communities in NRM is slated to begin early 2016. Vulnerability Capacity Assessment has been conducted with residents of Hanover and Westmoreland communities in partnership with the Jamaica Red Cross. ODPEM also partnered with the Jamaica Fire Brigade to facilitate disaster risk management and safety wardens training sessions. Initial Damage Assessment (IDA) training was conducted in June 2015 in select communities. A consulting firm was engaged to develop storm surge modelling and sea level rise scenarios. Data collection via bathymetric and topographic (aerial) surveys was done and wave overtopping analysis conducted. The storm surge modelling report was completed and the findings shared withlocal planning authorities, including Parish Disaster Committees and 2 Parish Councils (Westmoreland/Hanover). In relation to the risk atlas, asset-mapping has been completed with ~4700 assets mapped using GPS; digitization of 5 community hazard maps has also been completed and the validation process done. The draft climate risk atlas has been completed. This output will now be reviewed by technical experts as well as shared at various stakeholders consultations (eg. local planning authorities) before finalization. NEPA has re-commenced the procurement process to identify a suitable consultant to undertake work on the guidelines and adaptation plans for beach restoration. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shelia McDonald-Miller
| Email: | smmiller@pioj.gov.jm
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | For the milestones, the rating of MS was assigned because, despite encouraging progress during this reporting period, the pace of implementation over the last 3 years has not kept pace with plan. This can be explained by factors such as changes in key management personnel in some partner agencies which have continued since inception; inadequate understanding of the project leading to continued opposition by some stakeholders in a critical component. In some areas, the procurement process was lengthened due to non-receipt of responses to requests for expressions of interest and/or non-responsive bids. These have necessitated re-tendering exercises and contributed to the schedule delays. Despite the overall rating of MS, the groundwork has definitely been laid and the Executing Entities have begun to demonstrate the capacity to deliver the agreed results. The trend of implementation progress certainly demonstrates improvement overtime. For example expenditure over the last 12 months was approximately US$0.965M compared to US$0.516M for the previous year. This means that the rate of expenditure has increased by >$400,000 or 87% in the current reporting period relative to the previous. This improvement would have been significantly higher had component 1 which accounts for more than 50% of total grant ($5.4M) been able to begin the planned construction; the projected expenditure for component 1 was more than $3M for the year just ended. In relation to Component 1 the rating of MU has been assigned based on the slow pace of implementation for most of the last 2 years. This has been due largely to strong push-back by a group of stakeholders from the target community. Due to the prolonged nature of the protests, the matter was elevated to the Cabinet which endorsed the project and authorized a timed mediation process with the group of stakeholders. As the infrastructure in Negril remains vulnerable to climate change impacts and other projected hazards, the NIE and partners continue to invest much time and high-level interventions in seeking a solution to the impasse. It is very likely that the NIE will seek an extension of the programme in order to achieve all intended outcomes and objectives; the exact duration will be determined in consultation with executing partners and the approval of the Adaptation Fund sought.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT INDICATORS
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Length (m) of breakwater installed | No breakwater | Pre-Construction/design phase Consultants Engaged and drawings, engineering design and modelling studies for breakwater completed - Verification and approval of source material and Material Assessment Report completed Environmental Impact Assessment (EIA) and Natural Resources Valuation completed Several community sensitization meetings/ consultations held Environmental permits and licences issued for construction works; letters sent to key stakeholders while general public notified via press release NWA has completed the Requests for Proposal (RFP) for the Construction Phase; The RFPs have been updated with provisions to allow for satisfaction of the NRCA pre-conditions attached to the Beach Licences Procurement activities in progress for Enforcement Officers (NEPA) to carry out monitoring activities during the construction phase. Tender documents recently issued to pre-qualified contractors. | 990m of breakwater installed
| Number of micro dams constructed in North Manchester | 0 water catchment facility in North Manchester | Several sites in North Manchester visited and evaluated. Land tenure and geo-technical issues have necessitated a review of the proposed output. Based on feasibility assessment, the decision has been taken to replace micro dam with alternative water retention structures and water harvesting systems (scope change) Three small-scale irrigations systems installed | Several water harvesting systems and irrigation infrastructure implemented
| number of irrigation and production schemes established in: St Thomas, St Ann, Trelawny, St Catherine, Clarendon, Manchester, St Mary | 0 irrigation and production schemes in the 21 targeted communities in 6 project parishes | Nineteen (19) of the 24 P & P schemes have been approved and disbursed. Forty-three (43) communities identified and shortlisted; 14 Farmers groups were mobilised for establishment of Irrigation and Production Schemes | 45 schemes installed and operational in 15 communities serving over 750 male and female farmers
| Number of rainwater harvesting and gravity drip irrigation systems installed in: St Thomas, St Ann, Trelawny, St Catherine, St Mary, Clarendon | Inadequate access to irrigation facilities in selected communities in 6 project parishes | Design of irrigation systems completed and necessary permits and/or waivers have been secured. Safety gears and administrative equipment have been procured. Fourteen (14) systems using roof catchment and tanks have been installed, including schools with meal-assistance programmes for students. Three (3) rain water harvesting systems using tanks and catchment were rehabilitated. 210 gravity drip irrigation systems have been installed in 7 parishes: 103 directly with AF resources and an additional 107 in collaboration with another agriculture project. | 30 rainwater harvesting; 20 ponds and springs 210 gravity drip irrigation systems installed and operational and serving 40 male and 20 female farmers directly
| Soil conservation and land husbandry infrastructure in Upper Rio Minho Watershed | Extensive soil erosion due to hillside farming, removal of forest cover and poor farming practices | Five (5) extension areas selected and 5 community sensitization sessions held with stakeholders. The following results have been achieved to date: Hillside Ditch (M) 11975 Individual Basin (#) 11830 Live Barrier (M) 860 Continuous Mound (M) 10397* Water ways (M) 110 Cover crop (H) 1.1 Fruit Forest (H) 0.9 Land Preparation (H) 4.34 Ginger planted (H) 2.52 Yam planted (H) 2.55 Plantain planted (H) 2.1 Banana planted (H) 1.6 Vegetable planted (H) 0.2 *includes both demo plots and grants sub-component | App 18000m diversion /hillside ditches, 24600 individual basins, 3000m of waterway, 1200m continuous mound , 705 check dam/drop structures installed, 18000 m pineapple (vegetable barrier) and 13ha fruit forest and 15ha timber planted impacting 5 Extension Areas
| Number of climate-smart farmer field schools established in select communities | No climate-smart field schools in select communities | Consultations held with land owners to validate participation with the project 5 farmers field schools have been mobilised, namely: 1. Plantain Garden River Farmers Group 2. Yallahs Farmers Group 3. Colbeck 4. Braco 5. Medina Over 1300 (ratio of approx. 26% female/74% male) farmers have been trained in skills, knowledge and techniques for sustainable practices and land husbandry | Ten (10) climate-smart farmer field schools established and 90% farmers (male/female) trained to adopt climate smart agriculture practices
| Number of demonstration plots established in the Upper Rio Minho Watershed | Targeted communities do not have demonstration plots in place | Currently all 5 plots have been established and the land husbandry infrastructure is 80% complete. The communities are Crooked River, Thompson Town, James Hill and Kellits. Two (2) workshops were held in Thompson Town and Crooked River. A land husbandry specialist has been assigned to the project. | Five demonstration plots established imparting skills, knowledge and techniques to 1510 farmers (male, female) who are adopting sustainable practices
| Number of water user groups established | 0 WUG in targeted communities | The target seems set to be exceeded with a total of fourteen (14) groups established/strengthened at mid-term. A Rural Sociologist was engaged in 2015 and has assisted in formalizing the registration of at least 5 groups with the Department of Cooperatives and Friendly Societies. Other groups are in varying stages of the registration process. | At least 15 WUGs established and operational towards sustainable management of water resource
| Number and volume of awareness raising materials (audio visual) targeted to specific age groups, occupation groups, sex and persons with disability | No area specific public education programme | Communication plan and strategy developed spearheaded by the PMU in collaboration with executing partners as part of the information management system. Advertorial placed in two major daily newspapers to provide general information on the programme; FAQs and brochures on each component prepared; 2500 copies printed and disseminated to raise awareness. Fact sheets on all 3 components developed and shared at stakeholder meetings. 3 Vignettes developed showcasing achievements of the beneficiaries. | Full roll out of awareness building programme; 70% of residents sensitized.
| Evidence of documentation and dissemination of best practices | No evidence of documented best practices in project areas | Best practices implemented and documented (from prior initiatives) include the Agro Eco-system Analysis whereby farmers are trained to analyse their farms to determine action threshold before application of integrated pest management strategies. This information is currently disseminated through the RADA network and used by farmers within and outsideof the project areas. | Information made available through virtual networks, RADA, parish libraries, College of Agriculture Science and Education, Jamaica Agriculture Society, Fishermen’s Cooperative, 4H Clubs and schools
| Number of (targeted) training programmes for local entities in DRR, natural resource management | Limited training in DRR for local entities in DRR and natural resource management, except the few hotels that have green certifications. Limited exposure to training with specific focus on climate change | GOJ/AFP programme impact was creatively documented in three film vignettes of the success of beneficiaries and in projects on the ground for the respective components. Three dramatized PSAs were also produced for future use on radio and website promotions. Training Officer employed and community mobilization plan developed KAP Survey completed and provided basis for developing Training Plan. Six (6) sensitization/training sessions conducted in four target communities. Approximately 120 persons were in attendance. Over 130 persons from the parishes of Westmoreland and Hanover have been trained in basic disaster risk management . Other training conducted including hurricane and fire safety, standard First Aid (with certification), and Safety Wardens Training for small hotels (18 persons) in collaboration with the Jamaica Fire Brigade. The community hazard mapping process is a critical output which will support training component of the project by providing information about the respective communities. Information about the particular communities may include areas likely to be affected by various hazards and location of vulnerable elements such as population, buildings, infrastructure, and livelihoods. Additionally these maps will help to minimize potential loss of physical assets, human resources, and environmental capital. Development of NRM training material is advanced and training of communities wil begin early 2016. | Training programmes targeted at fishers (mostly male), male and female youth , micro and small business owners and other groups completed
| Guidelines and standards for beach restoration, shoreline protection for Negril | No specific technical guidelines for Negril | 30% completed. Maps and other outputs recently completed by ODPEM will be used by NEPA for preparation of guidelines for beach restoration and shoreline protection. Procurement process re-started for consultant to undertake development of the outputs | One set of guidelines and standards finalized and shared with community and other stakeholders
| Number of climate risk atlas for storm surge, sea level rise (specific for Negril) | 0 risk atlas information for storm surge and sea-level rise for Negril | Digitization of Hazard Maps completed. Data collection (topographic aerial survey) completed. Report completed on storm surge modelling and sea level rise. Draft climate risk atlas completed and submitted to key stakeholders for technical review. | Climate Risk Atlas reviewed by stakeholders and finalized
| Number of adaptation plans for vulnerable sections of Negril | 0 Plan | Preparatory information completed; procurement process in train for consultant needed to develop the guidelines and standards. NEPA has re-initiated procurement process to identify a suitable consultant. | One adaptation plan completed and in use

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Key lessons include: - Nature and complexity (especially of environmental dynamics) requires a number of scientific studies to be done and this has implications for both cost and time. - The need to address perceived gaps in consultation process on an ongoing basis by strengthening the mechanisms for the engagement of all stakeholders; - The importance of understanding the dynamics of various groups within the community and their influences - The need for clear distillation of the effects of climate change on livelihoods/ businesses before implementation of planned activities can begin successfully. The programme approach is to build partnerships with key national institutions (both State and NGO) in order to facilitate progress towards delivery of outputs and shared objectives. Integration of the Programme Management Team across different agencies via regular team sessions has allowed for strengthening relationships among government institutions as well as providing a platform for coordinated implementation and capacity development. The effective functioning of the PSC allows for transparency and good governance of the implementation process. Adequacy of technical capacity, lack of dedicated resources and competing priorities within Executing Entities continued to stymie progress of implementation in year 3, although to a lesser extent than in the preceding years.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Continuing negative stakeholder perception of and a conflation of a wide range of prior community issues manifested in opposition to the proposed intervention in Component 1. This slowed the rate of progress as significant time and effort has had to be spent addressing the concerns and seeking to allay the fears expressed by the stakeholders. Three Beach Licences (environmental permits) were granted by the NRCA in November 2014; however the construction phase of the breakwaters did not begin as planned due to several factors, including unsuccessful attempts to begin the mediation process. The prolonged dry spell slowed the implementation of the agro-forestry component of the demonstration plots; this was compounded by heavier than anticipated rainfall at the start of the onion season. Procurement delays continued to be experienced in the design and installation of rainwater harvesting system using ponds/ tanks due in part to non-responsive bids; this necessitated re-tendering exercises. To alleviate the capacity constraints within the MOAF project team, a Procurement Officer was engaged on a short term basis. This has contributed to expediting planned procurement activities. The Natural Resources Management (NRM) activities (Component 3) experienced significant delays due to procurement challenges, competing priorities and limitations in partner capacity. Measures taken to address this included procurement support by the PMU. Lack of responses to the initial advertisements for a consultant to undertake work on adaptation plans has slowed progress on this sub-component. This has necessitated a revision of the TORs and initiation of re-tendering process. Generally, there was more direct, deliberate and fruitful interactions between senior management (eg. Permanent Secretaries, CEOs) of partner agencies and the PMU resulting in noticeable implementation gains. The NIE will continue to provide effective support and follow-up at different levels.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The programme engaged a Rural Sociologist under component 2 to assist with formalizing farmers groups and contributing to the sustainability efforts. A Procurement Officer and GIS Analyst were also hired to provide short term technical assistance to implementation efforts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The NIE collaborated with Freidrich Ebert Stiftung and University of the West Indies Institute for Gender and Development Studies in facilitating two workshops during the reporting period. The first was a Teach-in on Gender and Climate Change’ focussed on mainstreaming gender into project implementation, which served as an additional training activity to the gender training provided in early 2014. Twenty (20) beneficiaries of the GOJ/AFP participated. The second collaboration was on ‘A world without Hunger’ project which examined social and structural barriers associated with gender inequality in rural communities as well as agricultural-based sustainable livelihoods. Beneficiaries from the parishes of St. Mary, St. Thomas and Manchester participated. The GOJ/AFP continues to target benefits for both men and women who have benefitted from increased community interventions with the engagement of a Rural Sociologist. Ongoing activities such as workshops, stakeholder sensitization sessions, etc., are planned and executed on select days and during hours which guarantee greater participation of both men and women from the target communities. As a result, both men and women have been actively involved in programme activities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | An important lesson is the need to broaden stakeholder involvement ( segmenting and differentiating groups and related messages) on a continuing basis to prevent misconceptions mushrooming into dissent. It is also critical to establish relationship with community influencers/ gatekeepers/ local champions to enhance local ownership
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | A water storage and drip irrigation system was established in Bushy Park, Manchester. The tank supplied several small reservoirs which were in turn connected to drip irrigation systems. This is a good example of partnership as the costs of the equipment were borne by the programme, however the beneficiaries were responsible for building the base of the tanks. The initiative has helped by extending water availability to the area and to this category of farmers selected from among the most vulnerable. It will also serve as demonstration of best practice which can be replicated by other farmers both within and outside the project area in order to improve productivity in drought-prone areas.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | In the future, a Cost Benefit Analysis (CBA) and Natural Resources Valuation (NRV) could be used in the process of prioritising adaptation measures from a list of possible adaptation options to improve stakeholder confidence and secure greater levels of buy-in
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Development of land husbandry curriculum will allow for replication outside of the programme target areas, as well as application of the farmer field school technology. When developed/finalized, the risk atlas, adaptation plans and guidelines can be used as tools by other coastal communities
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | One of the more successful areas relate to formalization of WUGs under Component 2 which has contributed to greater community cohesion and involvement. On the economic level the involvement of the programme in import-substitution programme via the agro parks (onions and irish potato) which has helped to save foreign exchange for the island as well as promote better food security. Livelihoods have been positively impacted by, inter alia, the establishment of demonstration plots and training in land husbandry techniques. In Thompson Town, Clarendon, for example, twenty-five (25) farmers including several women who are heads of households have pooled their resources to effectively manage the community demonstration plot for skills-building and income generation. More than 800 hectares of crops (onions, irish potato, hot peppers, cabbage, pumpkin, etc.) have been established across the target parishes, impacting over 2000 farmers. Significant economic benefits have resulted from these activities with over J$1B earned by beneficiaries.
What measures are/have been put in place to ensure sustainability of the project/program results? | WUGs for sustainable use of water resources; training of community members in dispute resolution will reduce fractious relationships. Important linkages/partnerships have continued with NGOs, climate change related projects and other community organisations for greater synergy. The education and training in Disaster Risk Reduction will enhance understanding, personal responsibility and hopefully lead to behaviour modification and better environmental stewardship; direct link with national priorities via collaboration with Vision 2030.
What measures are being/could have been put in place to improve project/program results? | Measures put in place include improving the administrative framework among partners. In this regard there have been changes in Memorandum of Understanding (MOU) between the NIE and NEPA; a new MOU has been entered into between the Ministry with responsibility for Climate Change and the Environment (MWLECC) and the PIOJ. This will facilitate the observance of FIDDIC rules during the construction phase and make a clear distinction between regulator and contractor. To improve programme results, meetings were convened by the PMU with heads/senior management personnel of the Executing Entities to make them aware of the continuing delays in execution and solicit their commitment to supporting the GOJ/AFP. The response has been positive Efforts are being pursued to maintain/ improve continuity in visibility and communications for awareness building and to enhance stakeholder engagement. - Collaboration with local organisations and agencies (Food for the Poor, Jamaica Red Cross, FES/AGDS) to engage communities/ individual beneficiaries. This facilitated (i) faster land preparation in a less labour-intensive manner, and (ii) more effective mobilization and increased stakeholder participation. - engagement of short term technical assistance to address adequacy of (human) resources and provide technical expertise to executing entities (MOAF and ODPEM)
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | In the development of the GOJ/AFP the NIE utilized the specific experience of several partners such as the Negril Coral Reef Preservation Society, Panos Caribbean, The Hazard Risk Reduction and Climate Change Adaptation Thematic Working Group, hoteliers, academics and public sector agencies. During implementation, expertise in coastal simulations by the University of Delaware has been employed, and Environmental Impact Assessment study was commissioned and carried out. The EIA study and Natural Resource Valuation (NRV) were prepared by independent consultants and provided objective bases for assessing the proposed interventions against other alternatives. Communities/groups under component 2 were initially identified by the RADA network of extension officers in accordance with the Ministry of Agriculture and Fisheries' (MOAF) plans for food security. During implementation MOAF has continued to utilize information on food security and priority crops to inform the nature and timing of interventions in the target communities. The FFS concept was chosen to provide crop training in a group based, practical setting using the demonstration plots and other fields to improve land and water management. This approach to training helps to maximise the limited resources and the ‘learning by doing’ approach enhances the knowledge transfer for sustainable agricultural practices. Similarly, WUGs bring communities/farmers together to better manage the use of an important, but often limited resource (water). The WUG approach helps to build social capital formation and promotes inclusiveness which facilitates sustainability.
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | JAM/NIE/MULTI/2011/1
Implementing Entity | Planning Institute of Jamaica
Type of implementing entity | NIE
Country | Jamaica
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total | 10032 | 2508 | 7524 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries | 35% | 23.5% | 12% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 4% | 2% | 2% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 30 | Agriculture | 2: Low capacity | Total | 30 | Agriculture | 3: Medium capacity | Total | 30 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 16% |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 30 | 16% | Public |  | 30 | 20% |  |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Agriculture | 2: Low capacity | Public | National | Agriculture | 3: Medium capacity | Public | National | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 25% |  | Multi-sector |  | 60 |  | Multi-sector |  | 45 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 10000 | 30% | 3: Partially aware |  | 3000 | 30% | 4: Mostly aware |  | 2508 | 25% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 3: Moderately responsive (Some defined elements) |  | Multi-sector | National | 4: Mostly responsive (Most defined elements) |  | Multi-sector | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 5: Very effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 16 | ha protected | 5: Very effective | Catchment area/Watershed/Aquifer | 16 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1000 | 20% | 2: Limited improvement |  | 1000 | 25% | 4: High improvement |  | 1000 | 20% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 110 | Adaptation strategies | Agriculture | Irrigation system | 110 | Adaptation strategies | Agriculture | Irrigation system | 108 | Adaptation strategies | Agriculture | Irrigation system
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
[10 empty] | 2400 | Agricultural-related |  | 10000000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Communication & Information policy | 1 | Multi-sector | National | Climate Change Policy | 1 | Multi-sector | National | Climate Change Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.