## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | November 1, 2018 - October 31, 2019
| Project Title: | Enhancing the Resilience of the Agriculture Secture and Coastal Areas to Protect Livelihoods and Improve Food Security
| Project Summary: | Jamaica is vulnerable to climate related hazards, in particular hurricanes, floods, storm surges and droughts, due largely to its geographical location and the exposure of social and economic assets in coastal areas. This situation is made worse by the country’s low adaptive capacity especially in the climate sensitive sectors of the economy. The agriculture sector and coastal resources are among those at greatest risk, given their significant contribution to the country’s GDP and to the labour force. The activities identified in Government of Jamaica Adaptation Fund Programme (GOJ/AFP) are drawn from the adaptation priorities that were identified in the vulnerability and adaptation assessments for the agriculture and coastal resources sectors. The GOJ/AFP focuses on environmental and natural resource management activities; namely, coastal rehabilitation, inland flood and erosion control, and land and water management. The overall objective of the GOJ/AFP is to protect livelihoods and improve food security in vulnerable communities by: • improving land and water management for the agricultural sector • strengthening coastal protection; and • building institutional and local capacity for climate change adaptation and natural resources management
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | JAM/NIE/Multi/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Planning Institute of Jamaica (PIOJ) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity (NIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jamaica | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Component 1 -- Increasing the Climate Resilience of the North Eastern Coastline Location: Annotto Bay (St. Mary), Buff Bay and Orange Bay (Portland) Component 2 -- Enhancing the climate resilience of the agricultural sector by improving water and land management in select communities Location: Manchester, Trelawny, St. Mary, St. Ann, St. Catherine, St. Thomas, Portland and Clarendon Component 3 - Improving institutional and local level capacity for coastal and agricultural adaptation and awareness-raising for behaviour modification Location: Westmoreland/Hanover/St.Mary/Portland; some target communities in Component 2 | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-29
IE-AFB Agreement Signature Date: |  | 2012-07-23 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-02 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2015-08-01
| Original Completion Date: | 2016
Revised Completion Date after approval of |  | 2020-09-01
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Inception Report :submitted December 2012 2. Extension Requests: April 2016, July 2017 and November 2018 3. Mid-Term Report: submitted 2016 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.pioj.gov.jm/programmes/goj-adaptation-fund/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Claire Bernard | Dominican Republic
| Email: | cbernard@pioj.gov.jm | Ecuador
| Date: | 2011-01-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Una May Gordon | Equatoral Guinea
| Email: | unamay.gordon@megjc.gov.jm | Eritrea
| Date: | 2016-08-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Shelia McDonald-Miller | Fiji
| Email: | smmiller@pioj.gov.jm | Finland
| Date: | 2012-12-03
Name:
Email:
| Date: |  | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D26: Shelia Mcdonald-Miller: Material change approved by AFB in 2018. Revised project activities started subsequently

## Financial Data
Financial information PPR 6: cumulative from project start to October 31, 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of October 31, 2019 | 4227924
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 777.5514
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | PROGRAMME COMPONENT | ITEM / ACTIVITY / ACTION | AMOUNT
|  | Preliminaries | 125048.96
| COMPONENT 1 | Coastal Works-Hard Solution a. Land reclamation b. Revetment c. Parapet walls d. Geotexttile
|  | Non-structural(reforestation) a. fruit trees b. timber trees c. non-fruit timmber | 3001.65
| SUB-TOTAL 1 |  | 128050.61
| COMPONENT 2 | 2.2 Establishment of small scale irrigation facilities | 27320.15
|  | 2.3 Implementation of rainwater harvesting and drip irrigation systems | 214542.88
|  | 2.4 Establishment and rehabilitation of soil conservation and land husbandry infrastructure | 17172.76
| SUB-TOTAL 2 |  | 259035.79
| COMPONENT 3 | Development of Adaptation Plans for the targeted areas (north-eastern coastline) | 574.62
|  | Establish farmer field schools to develop solutions and demonstrate good practices | 43073
Conducting workshops and farmer training in climate smart agriculture
| SUB-TOTAL 3 |  | 43647.62
| GRAND TOTAL |  | 430734.02
0
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1 | US$
| Marine Benthic Assessment | 5822.77 | 2020-01-01
| Coastal Works-Hard Solution a. Land reclamation b. Revetment c. Parapet walls d. Geotextile | 1170735 | 2021-09-01
| Non-structural (reforestation) a. fruit trees b. timber trees c. non-fruit timmber | 100000 | December 2020
Component 2
| Completion of Distribution network system including documentation | 41535.6744 | March 2020
Component 3
| Development of adaptation plansfor the targeted areas | 19625.8247 | February 2020
| Capacity building and training in deep sea fishing, business development, natural resources management | 35000 | November2020
| Climate Change awareness and education programmes developed and implemented in project communities | 30000 | December 2020
| TOTAL | 1402719.2691
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial: budget over-runs/under-spend; mis-use of funds; inflation/ currency depreciation leading to increased costs for goods/services | Moderate | As a result of changes to programme outcome, outputs and related indicators, additional resources (over and above the AF grant) have had to be garnered towards Administration activities. This gap has been addressed by GOJ financial support during the reporting period. The NIE developed financial reporting templates/ procedures and provided training to partners in use thereof. Executing Entities (EE) are required to provide monthly/quarterly financial reports. The NIE has implemented a governance framework whereby EE work plans/budgets must be approved by the Programme Steering Committee (PSC) prior to disbursement of funds to respective EE. Periodic monitoring visits continue to be undertaken by the Programme Management Unit (PMU) to EE and beneficiary locations to verify reported expenditure and activities. To increase the value and credibility of the financial statements produced by the GOJ/AFP, two external audits have been undertaken since the inception of the Programme. Financial management procedures are effective and NIE monitoring continues.
Environmental: natural hazards (flood, drought, storms/hurricanes); pests and diseases. | Moderate | The Agriculture Ministry continues to implement the integrated pest management and disease control programme across target parishes while minimizing risks to people and the environment. Because the island is located in the Atlantic hurricane belt, there is inherent risk of 'adverse climatic events' affecting implementation. Therefore, plans and schedules are designed to take account of the official peak period (June-November) each year. Additionally, specialized agencies (ODPEM, Meteorological Service, etc.) continue to provide information to the public on how to respond in the event of such occurrences.
Stakeholder Buy-in | Low | The development of the revised Programme ensured the early involvement of communities and organisations likely to be affected by the various activities. As a result, the GOJ/AFP has gained the cooperation and positive participation of key stakeholders. The NIE remains committed to maintaining proactive communications throughout the programme cycle, thereby deepening stakeholder involvement in the target communities, as well as engaging stakeholders and other partners on a wider level beyond.
Multiple Executing Entities | Low | The NIE has convened meetings with each Executing Entity to confirm their participation and solicited/obtained the commitment of senior management of these organisations. Administratively, the PMU/NIE continues to organize and coordinate activities to improve collaboration among the project teams in the respective entities. This is often an iterative process of consultation, planning and reviewing in order to balance the differing and sometimes competing priorities.
Procurement Delays | High | Procurement has been de-centralized to the respective Executing Entities to increase flexibility; however, this has not worked as effectively as anticipated due in part to limited human resources in Executing Entities as well as some systemic issues such as (a) the length time it takes to receive feedback from the national procurement oversight authority; and (b) the sometimes piecemeal approach for requesting information by some regulatory agencies. These all serve to lengthen the procurement process. The PMU continues to support Executing Entities by providing direct procurement support and procedural review via the 'no-objection' process to minimize .
Implementation/ Operational: delays in programme implementation schedule | High | The need to revise component 1 and related elements has led to the Programme submitting a request for a 3rd extension of the original duration in order to complete revised activities. One of the main risk-drivers identified is in the area of procurement, (Component 1). To improve results on the ground, the PMU continued to provide direct assistance in coordinating/scheduling some critical activities with limited success.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risks associated with the installation of revetments and other structural works | Low | Measures for environmental risks have already been included in the Environmental and Social Management Plan (ESMP). Additionally, an Environmental and Monitoring Plan has been developed by the consultant engineering firm which carried out the design review and value engineering services for the shoreline protection works. Both plans will be utilized as part of the monitoring framework during the construction and post-construction phases.
Low disaster risk perception in some target communities | Low | Increased communication and awareness-raising activities relating to climate change impacts continue to be undertaken by the programme and have led to a more informed populace.
Executing Entities’ readiness to implement, including availability of human resources | Moderate to high | The NIE continued to provide support to the Executing Entities, especially in the area of procurement to foster improvements in the execution framework and to ensure compliance with the Procurement Guidelines. There continues to be regular meetings, technical support and other monitoring activities aimed at minimizing negative impacts on the programme.
Risks associated with changing development landscape with respect to reforestation | Moderate | Since programme design there have been changes in the development landscape. i is important to note that other new projects involved in reforestation have come on stream; this has resulted in a strain on the system to provide seedlings in sufficient quantities and in a timely manner. Additionally, small holders are challenged to put their lands into long term (tree) crops at the expense of cash crops which bring quicker monetary yields to support livelihoods. To address these risks/issues, an inter-cropping strategy is being promoted. Additionally, the NIE and partners have agreed on the expansion of the originally targeted project areas to include other communities while addressing the vulnerabilities identified in the original target areas.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All mitigation steps for the risks identified above were implemented. Most measures were successful in reducing the relevant risks; the area of procurement continues to be challenging due to EE capacity issues. The NIE continues to lend its support to the procurement activities in order to improve the outcomes.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Possible changes to navigation charts based on shoreline changes | Obtain approval of Harbour Master for changes in navigation chart | Harbour Master approval requested/obtained | The Programme is closely aligned to and complies with national policies, laws, plans and priorities for sustainable development and adapting to climate change | The National Environment & Planning Agency has been consulted and their requirements have been complied with.
2 - Access and equity |  |  | Disagreements related to beneficiary selection. Distribution of benefits/selection of geographical area Non-inclusion of persons with disabilities | Develop/apply transparent and objective criteria for selection. Use participatory approach, including awareness building, involving community groups and local authorities. Utilize knowledge of forest wardens and extension officers to identify planters and local forest management committee members. ABCDEA and other community groups requested to help identify individuals using participatory approach for capacity building. | Selection Criteria developed and fairly applied in beneficiary selection. Degree of involvement of local community groups. Evidence of inclusive stakeholder engagement engagement process. Level of integration of forestry mgmt protocols. |  | Inclusive stakeholder engagement process promoted and applied FD staff and RADA extension officers used to identify planters.
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Disproportionately fewer women than men engaged in labour activities. Low female participation in capacity building activities. | Implementation of activities in accordance with the National Gender Policy, 2011 and Gender Mainstreaming Manual, 2016 and with the aid of the NIE Gender Specialist. Partner with local women's organization where feasible; organize gender training; adopt/ build on methodologies previously used by rural sociologist. Special mobilisation of women; advise contractors to give special consideration to female providers of goods/services, where possible. | Gender assessment completed before implementation of project activity. Gender training conducted; project monitoring reports include sex disaggregated information. Evidence of gender requirement in procurement guidance notes; number of female participants in sensitization activities. |  | ESP & Gender sensitization sessions undertaken by NIE with executing partners and Programme Steering C'ttee members. ESP & Gender sensitization conducted with stakeholders in target communities.
6 – Core labour rights |  |  | Unsuitable working conditions | Cite relevant labour laws in contracts; use grievance mechanisms to monitor complaints; provide safety training and protective gear appropriate to work hazards. | No. of work-related incidents due to non-compliance with relevant provisions. No. of safety training conducted; protective gears provided and warning/safety signs posted at work sites.
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Seagrass beds may be disturbed if they exist in project work area. River regime altered by removal of materials for construction; encoachment on coral colony; movement of WADs post-project may contribute to coastal eco-system damage. | Conduct assessments as required by permitting process. Boulders identified from areas which will not significantly alter the river regime; extract material from licensed sites/quarries. Do bathymetric/environmental assessment and develop appropriate protocols. | Compliance with conditions of permits and licenses |  | Marine Benthic Survey conducted as pre-condition to
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Waste material generated; noise and vibrations from construction equipment. Accidental spills during transportation of material. | Implement Waste Management Plan Establish and publicize a Stakeholder Engagement Plan that includes a grievance redress mechanis Conduct health and safety awareness training for workers and target community Contractor required to design/implement workplace safety procedures in line with standard industrial practices and regulations | Traffice Managementand Waste Management Plans Number of Stakeholder Engagement sessions; number of complaints received and addressed Saftey standards appropriately displayed at work sites |  | Detailed environmental management plan developed by design consultant for monitoring when shoreline works begin. Consultants are explicitly required to comply with local environmental legislation, the Environment and Social Policy and Gender Policy of the Adaptation Fund and internationally agreed core labour standards, e.g. the ILO core labour standards, conventions on freedom of association and collective bargaining, elimination of forced and compulsory labour, elimination of discrimination in respect of employment and occupation, and the abolition of child labour.
13 – Public health |  |  | Increased respiratory/occular irritation Traffic congestion due to movement of raw materials | provision of protective gear (eg. dust masks, gloves, goggles, helmets etc.) to workers. Preparation of appropriate plans including, traffic management and occupational health and safety standards. Compliance with applicable environmental standards | Occupational health and safety reports; evidence of gears distributed/used Dust suppression techniques in place Number of plans/implemented |  | The programme team worked closely with the local Municipal Corporation which has responsbility for public health, sanitation and safety in the target parish.
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Risk monitoring is performed according to the ESMP
Have unanticipated ESP risks been identified during the reporting period? |  | No unexpected risks have been identified during the reporting period
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Meetings were convened with all Executing Entities to review ESP and GP requirements. Details of ESMP shared and clarifications provided. Executing Entities are required to screen their project activities against the list of ESPs. The Programme Steering Committe was sensitized to the ESMP requirements in order to provide effective oversight. The National Environment & Planning Agency (NEPA) is a member of the PSC; NEPA has responsibility for protection of the environment and ensuring that local development complies with relevant statutory and regulatory requirements and international standards. Continuous monitoring is done by the NIE for ongoing activities.
Have the implementation arrangements been effective during the reporting period? |  | Yes. Measures to minimize negative environmental and social impacts continue to be an important feature of the GOJ/AFP
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Yes, as outlined in the ESMP. Coordination with relevant municipal authorities and local environmental NGOs to ensure compliance during execution of project activities.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. Measures to minimize negative environmental and social impacts continue to be an important feature of the GOJ/AFP
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None received during reporting period
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | A baseline for gender-specific targetting of beneficiaries was not done during the preparation of the first full programme proposal. Please note, however, that general knowledge of the gender landscape was used in programme design/revision and so the programme targets both male and female beneficiaries within the respective components.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, there are indicators at outcome level.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Farmers (male/female) with increased access to irrigation water and production schemes | Outcome | Number of farmers (male/female) with increased access to irrigation water and production schemes | small % of residents (male/female) with water storage or distribution facilities | 1000+ farmers (male/female) in 21 communities have access to irrigation water and production schemes | satisfactory
Male and female farmers employing good practices | Outcome | Change in agricultural output of project communities | physical evidence of land degradation, soil erosion due to removal of trees | At least 50% of farmers (male/female) employing good practices | good
Male/female residents more aware of Climate Change Adaptation and DRR issues | Outcome | % residents (male/female) in project communities more aware/knowledgeable of CCA and DRR issues for their communities | Majority (approx 90%) of residents surveyed islandwide (male/female) believe CC risks more relevant and are willing to accept primary responsibility for adaptation | At least 75% of residents In project communities believe that climate risks are relevant to their communities/are willing to accept primary responsibility for adaptation | satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Three sensitization sessions were convened with Executing Entities and partner agencies to review the GP and ESPs. Project are urged to take into account the specific needs/constraints which would prevent women's participation During the procurement process for coastal works, a pre-bid meeting was held with potential contractors who were advised of the need to maintain gender balance for all activities under the Programme. ToRs for consultants also include the provisions for compliance with the relevant guidelines, including the AF Gender Policy. The Programme Steering Committee which meets quarterly generally has equal female/male attendance and participation in decision making. The NIE has ensured that all stakeholder consultations have seen active participation of both men and women. Reporting templates provided by the NIE include provision for capturing gender-related information.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. Females have had good representation and participation in activities across the Programme.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Component 1: Participatory approach used in relation to activities involving community groups (eg. stakeholder consultations) to minimize low participation of women. Implementation of activities is in accordance with the National Gender Policy (2011) and the AF Gender Policy.
Component 2: activities relate primarily to the agriculture sector and therefore this component targets farmers as a group. The activities benefit both men and women by using a participatory approach to ensure equitable involvement of both males and females; farmers field school (FFS) groups incorporate both men and women. Meeting registers collect sex disaggregated information; also the relatively recent engagement of a Rural sociologist by the Ministry of Agriculture ensures that community and water users groups continue to count with active participation of women. Implementation of activities is in accordance with the National Gender Policy.
Component 3: Capacity building and dissemination of knowledge is the primary objective of this component, and to this end gender training was previously provided to all EEs and other key stakeholders to ensure that non-discrimination is a guiding principle throughout implementation. Contracts provisions now explicitly require compliance with the Environment and Social Policy and Gender Policy of the Adaptation Fund. Implementation of activities have been proceeding in accordance with the National Gender Policy (2011) AF Gender Policy and Gender mainstreaming manual (2016) with the aid of the NIE gender specialist
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The arrangements have been effective, with general acknowledgement and encouragement of women's participation in different project acitvities.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Notwithstanding the efforts at sensitization, there remains somewhat inadequate capacity in the extension services (RADA) to undertake sex differentiated analysis in this traditionally male-dominated (agriculture) sector. A Rural Sociologist was engaged in mid-2019 by the Ministry of Agriculture and is working with the respective groups. It is proposed to provide additional climate change and gender exposure to improve effectiveness of the incumbent in these areas.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | none received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Governance and Oversight to Programme Implementation |  | Outcome 2 | 4 quarterly PSC meetings convened |  | 4 PSC meetings convened; technical assistance provided to support project execution | S
| Monitoring of Programme Execution |  | Outcome 2 | 10 monitoring visits conducted; oversight to/support for procurement activities |  | 15 monitoring visits conducted; direct assistance provided to executing entities/partners in procurement activities | HS
| Information, Education and Communication |  | Outcome 3 | Quarterly stakeholders consultations; strategic participation in partner events towards improving awareness and ownership of adaptation and climate risk reduction processes at the local/community/individual levels. |  | stakeholder consultations held quarterly; participated in 12 partner events; distributed 300 brocures and shared information on the GOJ/AFP | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Claire Bernard
| Email: | cbernard@pioj.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Overall Programme Implementation progress is rated as Marginally Satisfactory. Major activities planned for current reporting period were progressing on track to achieve relevant outputs. In relation to the coastal works and reforestation (Components 1 and 3) there have been significant, unforeseen procurement delays relating to a combination of capacity / systemic and scoping issues. To mitigate against this, steps were taken/are currently underway by the NIE, including the provision of direct procurement support to the respective executing and partner agencies whose internal resources have been stretched by competing priorities. In relation to the reforestation sub-component, the uptake of seedlings for planting has been impacted by a number of factors: first by drought and then by (relatively small ) size of most farmers' holdings and thirdly by other competing projects. Improvements are expected in this are for the upcoming reporting period due to change in strategy to promote inter-cropping for small holders, as well as increase the number of communities involved.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Change in coastal protection infrastructure (Component 1) (Executing Entity: National Works Agency) |  | Outcome 4 | Preliminary designs updated; tendering process completed and works underway |  | preliminary design has been updated; relevant environmental assessments completed Tendering process commenced but experienced some setbacks | MS
| Change in vegetative cover in select communities (Component 1) Executing Partners: RADA, Forestry Dept |  | Outcome 5 | 6000 trees planted |  | 2687 trees planted | MU
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shelie McDonald-Miller
| Email: | smmiller@pioj.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Project actions/activities planned for current reporting period were progressing on track to achieve relevant outcomes/outputs; however, in relation to the coastal works under Components 1 and 3, there have been significant, unforeseen procurement delays relating to a combination of capacity / systemic and scoping issues. These delays have affected the original completion timelines for Component 1 as well as expected expenditure. The NIE is actively pursuing remedial strategies to address the resource constraints/competing priorities negatively affecting programme performance In relation to the reforestation sub-component, the uptake of seedlings for planting has been impacted by a number of factors: first by drought and then by (relatively small ) size of most farmers' holdings and thirdly by other competing projects. Improvements are expected in this are for the upcoming reporting period due to change in strategy to promote inter-cropping for small holders, as well as increase the number of communities involved.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | number of farmers with access to rainwater harvesting and drip irrigation systems (Component 2) |  | Outcome 6 | 30 rainwater systems installed and equip with distribution network |  | 30 rainwater systems installed; distribution network substantially completed (some documentation lagging) | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | I.W. Wilson
| Email: | iwwilson@micaf.gov.jm
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | All physical targets and the majority of outcomes (for Component 2) were achieved within the project year. However the associated contract took much longer to be completed as the contractor experienced challenges executing the scope of contract within the stipulated contract period. Additionally, some stakeholders were not in the required state of readiness to facilitate the work of the contractor in a timely manner. MICAF and RADA were able to partner to improve coordination among the contractor and farming entities involved.
| AF Outcomes |  | The Project deliverable haver been achieved hover, the contr |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Output | Length (m) of hard structures installed | No revetment No artificial reef | No revetment No artificial reef | Procurement process to engage pre-construction/design phase Consultants completed. Coastal engineering firm engaged and conceptual designs reviewed and updated; Site and Needs Assement conducted; Engineers' estimate done for scope of works to facilitate tender process. A Marine Benthic Survey has commenced as requested by the National Environment & Planning Agency. Eight (8) NCC registered contractors prequalified to participate in tender process for shoreline protection works. Terms of reference have been prepared for Technical Officers (NEPA) to carry out monitoring activities during the construction phase. | 600m of revetment installed 300 m of artificial reef installed 18,000 m2 of reclaimed shoreline
Output/outcome | change of land cover |  | High level of deforestation; badly denuded slopes | Meetings held with community as well as organizational stakeholders to engender buy-in. RADA and Forestry Department senior management engaged; preliminary species list for timber and fruit trees defined by Agronomist 2687 plants procured, distributed and planted | 30,000 trees planted
Output | Number of micro dams constructed in North Manchester |  | 0 water catchment facility in North Manchester | Based on the results of a feasibility assessment, the decision was taken, in consultation with relevant stakeholders, to replace micro dam with alternative water retention structures and water harvesting systems (scope change). Three (3) small-scale irrigations and water catchment systems have been installed in Manchester ( Weir Pen and Medina x2) 19 roof-to-tank systems were implemented to compensate for the change in activity due to technical infeasibility (absence of the micro dam) 90,000 gal capacity concrete tank has been rehabilitated in Medina, Manchester | one micro dam fully installed and operational (this target has been revised…no micro dam will be built)
Output/outcome | Number of irrigation and production schemes established in: St Thomas, St Ann, Trelawny, St Catherine, Clarendon, Manchester, St Mary |  | 0 irrigation and production schemes in the 21 targeted communities in 6 project parishes small percentage of residents with water storage/ distribution facilities | Over 1900 farmers have been trained in skills, knowledge and techniques for sustainable practices and improved land husbandry | 1000+ farmers (male/female) in 21 communities have access to irrigation water and production schemes 63 schemes installed and operational in 21 communities serving over 1000 male and female farmers
Output/outcome | Number of rainwater harvesting and gravity drip irrigation systems installed in: St Thomas, St Ann, Trelawny, St Catherine, St Mary, Clarendon number of farmers having access to rainwater harvesting and drip irrigation systems |  | Inadequate access to irrigation facilities in selected communities in 6 project parishes | Forty (40) systems using roof catchment and tanks have been installed, including at 16 schools with meal-assistance programmes for students. Twenty (20) rainwater harvesting systems using ponds and catchment were rehabilitated. Eleven (11) rainwater harvesting /gravity drip irrigation systems implemented across the parishes of St. Thomas, Manchester and St. Ann. 224 gravity drip irrigation systems have been installed across 7 parishes: 117 entirely with AF resources and an additional 107 in collaboration with another agriculture project. | 30 rainwater harvesting 20 ponds and springs 60 gravity drip irrigation systems installed and operational and serving 40 male and 20 female farmers directly 60 farmers (40 male/20 female) in 6 parishes have access to irrigation water and production schemes
output | Soil conservation and land husbandry infrastructure installed in Upper Rio Minho Watershed |  | Extensive soil erosion due to hillside farming, removal of forest cover and poor farming practices | Five (5) extension areas selected and 5 community sensitization sessions held with stakeholders. The following results have been achieved to date: Hillside Ditch (M) 17234 Individual Basin (#) 18822 Live Barrier (M) 4218 Continuous Mound (M) 27147* Water ways (M) 416.5 Check-dams (each) (M) 52.25 Drop Structure (M3) 32 Cover crop (H) 2 Fruit Forest (H) 108 Timber Forest (H) 0.109 Land Preparation (H) 8.68 Ginger planted (H) 5.04 Yam planted (H) 5.1 Plantain planted (H) 4.3 Banana planted (H) 3 Vegetable planted (H) 0.2 *includes both demo plots and grants sub-component | App 18000m diversion /hillside ditches, 24600 individual basins, 3000m of waterway, 1200m continuous mound , 705 check dam/drop structures installed, 18000 m pineapple (vegetable barrier) and 13ha fruit forest and 15ha timber planted impacting 5 Extension Areas
Ouptut | Number of climate-smart farmer field schools established in select communities |  | No climate-smart field schools in select communities | Target has been exceeded: Eleven (11) climate-smart farmers field schools have been established, namely:- 1. Plantain Garden River Farmers Group, St Thomas 2. Yallahs Farmers Group, St Thomas 3. Colbeck, St Catherine 4. Braco, Trelawny 5. Medina, Manchester 6. Moffat, St Thomas 7. Woodside, St. Mary 8. Kentish, St Catherine 9. Cowley, St Ann 10. Bryce, Manchester 11. Lowe River, Trelawny Over 1900 farmers have been trained in skills, knowledge and techniques for sustainable practices and improved land husbandry | Seven climate-smart farmer field schools established and 90% farmers (male/female) trained to adopt climate smart agriculture practices
Output | Number of demonstration plots established in the Upper Rio Minho Watershed |  | Targeted communities do not have demonstration plots in place | Five (5) plots have been established in the Upper Rio Minho Watershed . A land husbandry specialist (RADA) was assigned to the project to provide support to the target communities. | Five demonstration plots established imparting skills, knowledge and techniques to 1510 farmers (male, female) who are adopting sustainable practices
Output | Number of water user groups established |  | 0 WUG in targeted communities | Target exceeded; twenty-one(21) groups have been established/strengthened and are functioning effectively; 14 of these groups formalized (attained legal status) as a result of the intervention of the Programme. A Rural Sociologist was engaged in 2015 and assisted in formalizing the registration of 8 groups with the Department of Cooperatives and Friendly Societies. The Ministry of Agriculture recently engaged the services of another Rural Sociologist to continue supporting the WUGs. | At least 15 WUGs established and operational towards sustainable management of water resource
Output | Number and volume of awareness raising materials (audio visual) targeted to specific age groups, occupation groups, sex and persons with disability |  | No area specific public education programme | Communication plan and strategy developed spearheaded by the PMU in collaboration with executing partners. Advertorial placed in two major daily newspapers to provide specific information on the programme; FAQs and corporate brochure prepared and disseminated to raise awareness of climate change adaptation and disaser risk reduction; Fact sheets on all 3 components developed and shared at stakeholder meetings. Three vignettes were produced highlighting the Programme’s impact on small farmers, women in agriculture and providing general programme information. The vignettes have been shared with stakeholders, including at the AF International Finance Seminar for NIEs and INMED Symposium. A video feature was produced in 2016 by the Jamaica Information Service (JIS) with a focus on how the programme is making water available to rural farming communities. Youth brochure titled "Building Climate Change Champions" was developed and shared at various forums. Engagement / awareness-raising of 400 students at the Jamaica Library Service and Multi-Care Environmental summer camps; and 300 students at the Jamaica 4-H Clubs National Achievement Expo at Denbigh. Visibility of the programme was boosted by it being featured, on the UN Sustainable Development Knowledge Platform. (https://sustainabledevelopment.un.org/content/documents/19481Facing_Climate_Change_Jamaicas_Journey_with_the_Adaptation_Fund.pdf) The Programme also mounted exhibitions at various fora including the Regional Consultations on the Sustainable Development Goals (SDGs) for Eastern and Southern regions of the Island (parishes of St. Thomas and Manchester). o A story map was developed to provide and hosted on the programme’s webpage http://adaptja.pioj.gov.jm to highlight several significant elements of the GOJ/AFP. | Programme adjusted based on feedback mechanism Full roll out of awareness building programme 70% of residents sensitized
Output | Evidence of documentation and dissemination of best practices |  | No evidence of documented best practices in project areas | Developed and distributed 30 copies of a manual on Land Husbandry/ Farmer Field School Approach for use in the training of beneficiaries. Re-printed and distributed 17 Flip Charts on 'Climate Smart and Land Husbandry in Jamaica: Good Practices for Farmers' which is being used by RADA as an extension teaching aid. (The flip chart was originally developed by FAO). The GOJ/AFP continues to disseminate information through the PMU/NIE and MICAF by making presentations to several schools which are supported by the Programme. Partnerships with the Jamaica Library Service and the Jamaica 4-H Clubs have also advanced the dissemination and education objectives. Best practices implemented and documented (from prior initiatives) include the Agro Eco-system Analysis whereby farmers are trained to analyse their farms to determine action threshold before application of integrated pest management strategies. This information is currently disseminated through the RADA network and used by farmers within and outside of the project areas. | Information made available through virtual networks, RADA, parish libraries, College of Agriculture Science and Education, Jamaica Agriculture Society, Fishermen’s Cooperative, 4H Clubs and schools
Output | Number of (targeted) training programmes for local entities in DRR, natural resource management |  | Limited training in DRR for local entities in DRR and natural resource management, except the few hotels that have green certifications. Limited exposure to training with specific focus on climate change | 35 Small business owners/operators were trained in Business Continuity Planning (March 2016) to strengthen the capacity of these stakeholders to respond to their own risks and vulnerabilities. Training was facilitated by the Office of Disaster Preparedness and Emergency Management (ODPEM). Training Officer employed and community mobilization plan developed and executed. Six (6) sensitization/training sessions conducted in four target communities. KAP Survey completed. 150 community members trained in disaster risk management techniques. The community hazard mapping process completed -- this is a critical output which will support training component of the project by providing information about the respective communities. Vulnerability Capacity Assessment have been conducted with residents of Westmoreland and Hanover communities in partnership with the Jamaica Red Cross. Partnered with the Jamaica Fire Brigade to facilitate Disaster Risk Management and Safety Warden training workshops. | Training programmes targeted at fishers (mostly male), male and female youth , micro and small business owners and other groups completed
Output | Number of climate risk atlas for storm surge, sea level rise (specific for Negril) |  | 0 risk atlas information for storm surge and sea-level rise for Negril | Climate Risk Atlas completed and presented to stakeholders, including the local planning authorities and hoteliers Copies disseminated to key stakeholders and is available at the NIE Library as a resource for internal and external stakeholders | Climate Risk Atlas completed, tested and in use
Output | Number of adaptation plans for vulnerable sections of north-eastern coast |  | 0 Plan | Sensitization sessions conducted with ODPEM re AF Environmental and Social Policy and Gender Policy to govern implementation Consultant engaged to undertake community consultations and develop Climate Change Adaptation Plan for Annotto Bay community Stakeholder consultations ongoing; stakeholder validation of draft plan will be undertaken | One Adaptation Plan completed and in use
Outcome | Number of farmers benefiting from soil conservation and land husbandry infrastructure (Upper Rio Minho watershed) |  | TBD | Five (5) demonstration plots established, imparting skills, knowledge and techniques directly to 1510 farmers (male, female) who are adopting sustainable practices. Please note that the impact extends beyond those farmers and communities directly involved in the programme. More than 100 farmer field schools established across the parish of Clarendon; farmers reported improved environmental resilience during flood rains - the improvements are due to the land husbandry treatments implemented under the programme. | Approximately 70000 residents (male/female) in 31 communities experience improved environmental conditions due to establishment of economic live barriers, fruit trees
Outcome | Change in availability (number)and quality of local planning toolks, eg. climate risk atlas, adaptation plans and extent to which climate resilient planning is adopted |  | Development planning tools not climate smart/standardized zero community adaptation plans available for project communities | Draft risk atlas developed, tested and validated consultant engaged for development of adaptation plan Risk atlas finalized and in use | Climate smart guidelines for assessing development applications institutionalized and in use in at least 50% of development applications Climate risk information integrated into development planning CCA and DRR integrated into community plans and activities beach restoration guided by standardized approach

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive lessons included: The approach taken by the Programme is to build partnerships with key national institutions (both State and NGO) as well as local communities, in order to facilitate progress towards delivery of outputs and attainment of shared objectives. This has had positive impact and led to increased stakeholder buy-in. The continued effective functioning of the Programme Steering Committee has allowed for transparency and good governance of the implementation process. On the negative side: adequacy of technical capacity, procurement lapses, lack of dedicated resources and competing priorities within Executing Entities continued to stymie progress of implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Implementation delays continued on Component 1, mainly due to procurement challenges experienced by the Executing Entity. While the design review phase has been successfully concluded, the next step of engaging suitable contractors for the shoreline works hit a snag. To reduce further delays the NIE is providing procurement support to the EE. Several stakeholder discussions have been held and procurement activities have re-started to identify suitable consultants to begin execution of scope of work. Procurement delays also continued to be experienced in the design and installation of rainwater harvesting system using ponds/ tanks (Component 2). The contractor was eventually engaged in August 2018 to complete work on the distribution systems; however there were several missed deadlines. Tripartite meetings were held with representatives of the NIE, senior management of the EE and the contractor to broker resolution, with limited success. Other implementation delays resulted from the absence of dedicated personnel for project execution and competing priorities within partner agencies. Measures implemented were the engagement of short-term staff and reallocation of human resources within Executing Entities; the PMU/NIE also continued to provide direct procurement support to EE. A significant amount of development assistance goes to agriculture adaptation, the paradox is that this can have the effect of dispersing the energy and attention of the actors in the sector. For the period under review, the NIE has sought to enlist the support of senior management within partner agencies and will continue to provide the requisite support to our partners.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | To improve results, the NIE undertook procurement activities and worked closely with ODPEM towards the engagement of a consultant to develop climate change adaptation plans. The consultant is onboard and work is proceeding apace. In relation to the reforestation element, there was direct engagement with nurseries to procure plants and close collaboration with RADA and the Forestry Department in relation to distribution and planting. Increased frequency of monitoring visits by the PMU ensured improved stakeholder engagement.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. In compliance with the legal requirements, the relevant permits/licenses have been applied for re shoreline protection work. A marine benthic assessment has also been carried out to determine the potential impact of activities within the project footprint. From a social standpoint, the NIE and partners continue to regularly consult with/inform the stakeholders of the ESP requirements and obtain their feedback.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Executing Entities, partner agencies and the Programme Steering Committee have been made aware/reminded of AF Gender Policy and its applicability during the programme cycle. Workshops, stakeholder sensitization sessions, etc., are planned and executed on select days and during hours which guarantee greater participation of both men and women from the target communities. As a result, both men and women continue to be actively involved in programme activities. The NIE had earlier provided training to our partners and will continue to emphasize gender mainstreaming throughout the programme cycle.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | JAM/NIE/MULTI/2011/1
Implementing Entity | Planning Institute of Jamaica
Type of implementing entity | NIE
Country | Jamaica
Region | Latin America and Caribbean
Sector | Coastal management
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 12000 |  |  | Total |  | 12000 |  | Total | 10032 | 2508 | 7524 | Total
|  | % of female beneficiaries | 50.8% |  |  | % of female beneficiaries |  | 50.8% |  | % of female beneficiaries | 35% | 23.5% | 12% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 4% | 2% | 2% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 30 | Agriculture | 2: Low capacity | Total | 30 | Agriculture | 3: Medium capacity | Total | 30 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 16% |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 30 | 16% | Public |  | 30 | 20% | Public |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 3: Medium capacity | Public | National | Agriculture | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 6 | National | Multi-sector | 2: Low capacity | 6 | National | Multi-sector | 2: Low capacity | 6 | National | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 25% |  | Multi-sector |  | 60 |  | Multi-sector |  | 45 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 10000 | 30% | 3: Partially aware |  | 3000 | 35% | 4: Mostly aware |  | 2508 | 25% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | National | 3: Moderately responsive (Some defined elements) |  | Multi-sector | National | 3: Moderately responsive (Some defined elements) |  | Multi-sector | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target Performance at Completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 5: Very effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 2 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 16 | ha protected | 4: Effective | Cultivated land/Agricultural land | 16 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1000 | 20% | 2: Limited improvement |  | 1000 | 25% | 4: High improvement |  | 1000 | 20% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 10 | Adaptation strategies | Agriculture | Strengthening infrastructure | 110 | Adaptation strategies | Agriculture | Strengthening infrastructure | 108 | Adaptation strategies | Agriculture | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 401 | Agricultural-related |  | 7800 | 2700 | Agricultural-related |  | 12000000 | 2400 | Agricultural-related |  | 1000000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Communication & Information policy | 1 | Multi-sector | National | Communication & Information policy | 1 | Multi-sector | National | Climate Change Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
[6 empty] | Food Security | National | Innovation scaled-up |  | Food Security | National | Innovation replicated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
[6 empty] | 1 | Disaster risk reduction | Undertaking innovative practices | 5: Very effective | 1 | Disaster risk reduction | Undertaking innovative practices | 4: Effective
[6 empty] | 1 | Food Security | Undertaking innovative practices | 5: Very effective | 1 | Food Security | Undertaking innovative practices | 5: Very effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on D62: Shelia Mcdonald-Miller: Ees, ODPEM, RADA, etc.
Note on I95: Shelia Mcdonald-Miller: 1. Change in vegetative cover in Pencar/Buff Bay watershed; 2. change in land/water mgmt practices in agri sector.