## 1. Front Page
Updated | ICP 2011 TIMETABLE |  |  | 2010 |  |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014
2010-10-12 |  |  |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | MANAGEMENT, FUND RAISING, AND ADVOCACY
1.1 |  | Planning and monitoring progress (with Regional Coordinators)
1.2 |  | Budget monitoring, fund raising activities, and grants to regions
1.3 |  | Global outreach activities
1.4 |  | Building partnerships with programs and organizations | bar: 2010 Oct to 2010 Dec
1.5 |  | Mobilizing experts in various fields/ Maintaining a database of experts | bar: 2010 Oct to 2010 Dec
2 | MEETINGS
2.1 |  | Executive Board | bar: 2010 Oct; 2011 Feb; 2011 Sep; 2012 Feb; 2012 Sep; 2013 Feb; 2013 Sep
2.2 |  | Regional Coordinators | bar: 2010 Oct; 2011 Apr; 2011 Oct; 2012 Apr; 2012 Oct; 2013 Apr; 2013 Oct
2.3 |  | Technical Advisory Group | bar: 2010 Oct; 2011 Apr; 2011 Oct; 2012 Apr; 2012 Oct; 2013 Apr; 2013 Oct
2.4 |  | Users Conference | bar: 2010 Oct
2.5 |  | Regional Workshops / Technical meetings | bar: 2010 Oct to 2013 Oct
2.5.1 |  |  | ICP-Africa | bar: 2011 Jun; 2011 Nov; 2012 Jun; 2012 Dec; 2013 Mar; 2013 Oct
2.5.2 |  |  | ICP-Asia | bar: 2010 Oct to 2011 Jun; 2011 Aug; 2011 Nov; 2012 Feb; 2012 Apr; 2012 Jul
2.5.3 |  |  | ICP-CIS | bar: 2010 Oct to 2011 Mar; 2011 Jul to 2011 Sep; 2012 Oct; 2012 Dec; 2013 May
2.5.4 |  |  | ICP-LAC | bar: 2011 Jan; 2011 Apr; 2011 Jul; 2011 Oct
2.5.5 |  |  | ICP-Caribbean | bar: 2010 Oct; 2011 Jan; 2012 Jan; 2012 Apr; 2012 Jul; 2012 Oct
2.5.6 |  |  | ICP-Western Asia | bar: 2010 Oct to 2010 Nov; 2011 May to 2011 Jun; 2011 Aug; 2011 Nov; 2012 Feb; 2012 Jul; 2012 Nov to 2012 Dec; 2013 Mar
3 | CAPACITY BUILDING, DOCUMENTATION, QUALITY AND SOFTWARE
3.1 |  | Global capacity building activities | bar: 2010 Oct to 2012 Dec
3.2 |  | Quality Assessment Framework/ Checklists formulation and implementation | bar: 2010 Dec; 2011 Jun; 2011 Dec; 2012 Jun; 2012 Dec to 2013 Jan; 2013 Jun to 2013 Jul; 2013 Dec
3.3 |  | ICP Book and documentation of PPP computations
3.4 |  | Software development, deployment, and support | bar: 2010 Oct to 2013 Jun
4 | METHODOLOGY
4.1 | P | National Accounts
4.2 | P | Survey Frameworks & Importance
4.3 | P | Housing
4.4 | P | Government
4.5 |  | Equipment | bar: 2010 Oct
4.6 |  | Construction | bar: 2010 Oct
4.7 |  | Education | bar: 2010 Oct to 2010 Dec
4.8 |  | Health | bar: 2010 Oct to 2010 Dec
4.9 |  | Aggregation & Linking Issues | bar: 2010 Oct to 2011 Dec
4.1 |  | Extrapolating PPPs & Estimation of PPPs | bar: 2010 Oct to 2011 Dec
4.11 |  | Sub-National PPPs | bar: 2010 Oct to 2011 Dec
4.12 |  | PPP-based poverty analysis | bar: 2010 Oct to 2011 Dec
4.13 | P | Financial Services, Exports & Imports, & Net Purchases Abroad
4.14 |  | Other areas (energy, water, transport, etc) | bar: 2010 Oct
5 | PRICE SURVEY PREPARATIONS
5.1 | P | Global core product lists (HHC and other GDP components)
5.2 |  | Amalgamated product lists | bar: 2010 Oct to 2011 Mar
5.2.1 |  |  | ICP-Africa | bar: 2010 Oct to 2010 Nov
5.2.2 |  |  | ICP-Asia | bar: 2010 Oct to 2010 Nov
5.2.3 |  |  | ICP-CIS | bar: 2010 Oct to 2010 Dec
5.2.4 |  |  | ICP-LAC | bar: 2010 Oct to 2010 Nov
5.2.5 |  |  | ICP-Caribbean | bar: 2011 Jan to 2011 Mar
5.2.6 |  |  | ICP-Western Asia | bar: 2010 Oct to 2010 Nov
5.3 |  | Survey design | bar: 2010 Oct to 2010 Dec
5.3.1 |  |  | ICP-Africa | bar: 2010 Oct to 2010 Nov
5.3.2 |  |  | ICP-Asia | bar: 2010 Oct to 2010 Nov
5.3.3 |  |  | ICP-CIS | bar: 2010 Oct to 2010 Nov
5.3.4 |  |  | ICP-LAC | bar: 2010 Oct to 2010 Nov
5.3.5 |  |  | ICP-Caribbean | bar: 2010 Oct to 2010 Dec
5.3.6 |  |  | ICP-Western Asia
5.4 |  | Price survey data collection forms | bar: 2010 Oct to 2011 Mar
|  |  | GO timeline | 2010 Nov: Suggested timeline
|  |  | Regionally set timeline (aggregate) | 2010 Oct: P; 2010 Nov: Completed items; 2013 Dec: Page 1
Regionally set timeline (each region)

## 2. Back Page
Updated | ICP 2011 TIMETABLE |  |  | 2010 |  |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014
2010-10-12 |  |  |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
6 | PRICE DATA COLLECTION, VALIDATION AND TRANSMISSION
6.1 |  | Pilot data collection | bar: 2010 Oct to 2011 Mar
6.2 |  | Data collection | bar: 2011 Jan to 2012 Dec
6.2.1 |  |  | ICP-Africa | bar: 2011 Jan to 2012 Jun
6.2.2 |  |  | ICP-Asia | bar: 2011 Jan to 2012 May
6.2.3 |  |  | ICP-CIS | bar: 2011 Jan to 2011 Dec
6.2.4 |  |  | ICP-LAC | bar: 2011 Jan to 2011 Dec
6.2.5 |  |  | ICP-Caribbean | bar: 2011 Sep to 2012 Dec
6.2.6 |  |  | ICP-Western Asia | bar: 2011 Jan to 2011 Dec
6.2.7 |  |  | ICP-Pacific Islands | bar: 2011 Oct to 2012 Sep
6.3 |  | Data validation (intra-country and regional) | bar: 2011 Feb to 2013 Mar
6.3.1 |  |  | ICP-Africa | bar: 2011 Feb to 2012 Jul
6.3.2 |  |  | ICP-Asia | bar: 2011 Feb to 2012 Jul
6.3.3 |  |  | ICP-CIS | bar: 2011 Apr to 2012 Mar
6.3.4 |  |  | ICP-LAC | bar: 2011 Apr to 2012 Mar
6.3.5 |  |  | ICP-Caribbean | bar: 2012 Jan to 2013 Mar
6.3.6 |  |  | ICP-Western Asia | bar: 2011 Apr to 2012 Apr
6.4 |  | Calculation of National Annual Average | bar: 2012 Mar to 2012 Oct
6.4.1 |  |  | ICP-Africa | bar: 2012 Apr to 2012 Aug
6.4.2 |  |  | ICP-Asia | bar: 2012 Apr to 2012 Aug
6.4.3 |  |  | ICP-CIS | bar: 2012 Mar to 2012 Apr
6.4.4 |  |  | ICP-LAC | bar: 2012 Apr to 2012 Aug
6.4.5 |  |  | ICP-Caribbean | bar: 2012 Apr to 2012 Aug
6.4.6 |  |  | ICP-Western Asia | bar: 2012 Jul to 2012 Oct
6.5 |  | Transmission of final validated price data to the GO | bar: 2012 Aug to 2013 Mar
7 | NATIONAL ACCOUNTS IMPLEMENTATION FOR ICP
7.1 |  | Compilation of GDP expenditures | bar: 2010 Oct to 2013 Jun
7.1.1 |  |  | ICP-Africa | bar: 2010 Oct to 2012 Sep
7.1.2 |  |  | ICP-Asia | bar: 2010 Oct to 2012 Sep
7.1.3 |  |  | ICP-CIS | bar: 2010 Oct to 2013 Jun
7.1.4 |  |  | ICP-LAC | bar: 2010 Oct to 2012 Dec
7.1.5 |  |  | ICP-Caribbean | bar: 2010 Oct to 2013 Mar
7.1.6 |  |  | ICP-Western Asia | bar: 2010 Oct to 2012 Sep
7.2 |  | Transmission of preliminary major aggregates for latest year to the Global Office | bar: 2011 Nov
7.3 |  | Transmission of preliminary basic headings for 2011 to the Global Office | bar: 2011 Nov
7.4 |  | Validation of preliminary GDP expenditures | bar: 2011 Sep to 2013 Apr
7.4.1 |  |  | ICP-Africa | bar: 2012 Jul to 2013 Apr
7.4.2 |  |  | ICP-Asia | bar: 2011 Sep to 2013 Apr
7.4.3 |  |  | ICP-CIS | bar: 2013 Jul to 2013 Dec
7.4.4 |  |  | ICP-LAC | bar: 2012 Jul to 2013 Apr
7.4.5 |  |  | ICP-Caribbean | bar: 2012 Oct to 2013 Apr
7.4.6 |  |  | ICP-Western Asia | bar: 2012 Aug to 2013 Apr
7.5 |  | Transmission of final major aggregates for 2011 to the Global Office | bar: 2013 May
7.6 |  | Transmission of final basic headings for 2011 to the Global Office | bar: 2013 May
7.7 |  | Reconciliation of inconcistencies, if any | bar: 2013 Jun to 2013 Jul
8 | PREPARATION OF REGIONAL AND GLOBAL RESULTS
8.1 |  | Regional results computation and publication | bar: 2012 Apr to 2013 Dec
8.1.1 |  |  | ICP-Africa | bar: 2013 Jan to 2013 Dec
8.1.2 |  |  | ICP-Asia | bar: 2012 May to 2013 Jul
8.1.3 |  |  | ICP-CIS | bar: 2012 Apr to 2013 Jun; 2013 Oct to 2013 Dec
8.1.4 |  |  | ICP-LAC | bar: 2013 Jan to 2013 Sep
8.1.5 |  |  | ICP-Caribbean | bar: 2013 Jan to 2013 Sep
8.1.6 |  |  | ICP-Western Asia | bar: 2013 Jan to 2013 Apr
8.2 |  | OECD/Eurostat PPP program results | bar: 2012 Dec; 2013 Dec
8.3 |  | Global results computation and validation | bar: 2013 Jun to 2013 Dec
8.4 |  | 2011 ICP results released | bar: 2013 Dec
8.5 |  | Preparation and publicaton of final ICP report | bar: 2014 Jan to 2014 Mar
|  |  | GO timeline | 2010 Nov: Suggested timeline
|  |  | Regionally set timeline (aggregate) | 2010 Oct: P; 2010 Nov: Completed items
|  |  | Regionally set timeline (each region) | 2013 Dec: Page 2