## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | March 2018 to 31 March 2019
| Project Title: | Enhancing the Climate Change Resilience of the Vulnerable Island Communities in Federated States of Micronesia (Project ID: FSM/RIE/Coastal/2015/1)
| Project Summary: | Disasters, climate and weather extremes and projected changes in climate, are increasingly recognized as a core development challenge, as they adversely impact lives and livelihoods, social and economic development. To address these challenges, the Secretariat of the Pacific Regional Environment Program (SPREP) in close collaboration with the Department of Environment, Climate Change and Emergency Management (DECEM) and in consultation with the National Government and State level departments, municipalities and communities, developed a proposal to the Adaptation Fund to support the implementation of the Project “Enhancing the climate change resilience of vulnerable island communities in FSM”.
|  | The overall goal of the project is to build social, ecological and economic resilience of the target island communities of the Federated States of Micronesia and reduce their vulnerabilities to extreme drought, sea level rise and other climate risks through water resource management, coastal resource and development planning, and by promoting gender perspectives and ecologically sound climate resilient livelihoods. | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | The project aims at reducing the vulnerability of the selected communities to risks of water shortage and increase adaptive capacity of communities living in Woleai, Eauripik, Satawan, Lukunor, Kapingamarangi, Nukuoro, Utwe, Malem to drought and flood-related climate and disaster risks. The objectives of the project are: 1. Prepare the necessary institutional and regulatory frameworks, policies, guidance and tools to help deliver a climate resilient FSM. 2. Strengthen water and livelihood security measures to help 6 outer atoll islands adapt to impacts of climate change related to water, health and sanitation. 3. Provide communities with climate resilient infrastructure to help relocate from high risk coastal inundation sites. 4. Capture and share the local knowledge produced on climate change adaptation and accelerate the understanding about the kinds of interventions that work in island environments in FSM. All four State Governments of FSM – Chuuk, Kosrae, Pohnpei and Yap - will also receive development planning tools and institutional frameworks to help coastal communities prepare and adapt for higher sea levels and adverse and frequent changes in extreme weather and climate events. With various initiatives underway and emerging issues, the project will work with local implementing partners that have experience in working with communities to deliver on-ground actions and build appropriate junctures to build on and utilize their experience. For instance, engaging relevant local NGOs to deliver relevant activities in coordination with the state and municipal governments. | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Secretary of the Pacific Regional Environment Program (SPREP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Federated States of Micronesia (FSM) | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The FSM is located near the equator about 4,000 km southwest of the Hawaiian Islands in the Western Pacific Ocean and within the Caroline Islands group. It is a group of approximately 607 islands covering 2,736 square kilometers in the western Pacific Ocean. The land area totals 704.6 square kilometers, with 7, 192 square kilometers of lagoon area. The islands vary from small islands to atolls and large volcanic islands with land area of more than 80 square kilometers. Approximately 65 of the islands are inhabited. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | June 22, 2017
IE-AFB Agreement Signature Date: |  | 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | March 13, 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | May 2021
| Terminal Evaluation Date: | December 2022
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. FSM AF National Inception Workshop | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://decem.gov.fm/adaptation-fund/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Richard Moufa | Dominican Republic
| Email: | richard.moufa@gov.fm | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Andrew Yatilman | Equatoral Guinea
| Email: | decem.fsm@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Secretariat of the Pacific Regional Environment Program (SPREP) | Fiji
| Email: | melaniek@sprep.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | FSM Department of Climate Change, Environment and Emergency Management | Georgia
| Email: | decem.fsm@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Cumulative from project start to 31 DECEMBER 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of December 2018 | 200000
Add any comments on AF Grant Funds. (word limit=200) | Executing Entity: Disbursed Funds to EE: $200,000 Undisbursed funds to EE: $950,678 Implementing Entity: IA Fee Disbursement #1: $97,807.60 Cumulative Expenditure $17,152.62 Unexpended IA fee $80,654.98
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 22500
| Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 0
| Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 0
| Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 0
| Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 45000
| Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 0
Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side
Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands
Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions
| Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 25500
| Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 0
| Output 3.3: State support program to access land in upland areas established | 0
| Output 3.4: Community-based ecosystem management strengthened | 0
| Output 3.5: Develop state program to assist access to finance for vulnerable households established | 0
| Output 4.1: Community resilient (municipality) development plans developed and communicated | 0
| Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 20000
| Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 30000
| Output 5.1: Project Execution Costs | 57000
| TOTAL (EE) | 200000
| Implementing Entity Fee (salaries, legal, financial services) | 17152.62
| TOTAL | 217152.62
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 45000 | March 2019
| Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 52500 | March 2019
| Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 38400 | March 2019
| Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 94392 | March 2019
| Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 28523 | March 2019
| Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 104464 | March 2019
| Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | 73298 | March 2019
| Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands | 26005 | March 2019
| Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions | 15631 | March 2019
| Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 901642 | March 2019
| Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 94500 | March 2019
| Output 3.3: State support program to access land in upland areas established | 16500 | March 2019
| Output 3.4: Community-based ecosystem management strengthened | 31500 | March 2019
| Output 3.5: Develop state program to assist access to finance for vulnerable households established | 12000 | March 2019
| Output 4.1: Community resilient (municipality) development plans developed and communicated | 41067 | March 2019
| Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 47879 | March 2019
| Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 59059 | March 2019
| Output 5.1: Project Execution Costs | 160963 | December 2019
| TOTAL (EE) | 1843323
| Implementing Entity Fee (salaries, legal, financial services) | 156674.99 | December 2019
| TOTAL | 1999997.99
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Nil
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Limited or no buy-in from national and state government stakeholders | Low risk | The inception workshops at both levels of government (national and state) have gained stakeholders supports for the project with clear understanding of respective stakeholders role in project's implementations.
Lack of capacity within executing agencies cause delay or insufficient level of implementation | Low risk | Although it took more that six (6) months to hire all the required staff for the project, the project management unit (PMU) was able to hired all 13 project staff at national, state and community levels. Once staff were on board, the PMU sped up orientation of the project's components with the staff to comprehend the crucial objectives, goals and activities. With the full understanding of the project, the staff were able to carry out the inception workshop and initiate advocacy work to stakeholders
Extreme natural disasters affect the implementation of the project | Medium risk | Currently there is a post-disaster activities undertaken on the two target communities of Satawan and Lekinioch, before the relief activities commenced the AF Project communicated to AF staff on ground to coordinate their tasks with the relief team to support in their assessment of the damage caused by the natural disaster so the project can work on changing the time frame of implementation of activities on the target islands.
Climate hazards are more severe than anticipated leading to higher climate-proofing related costs for building the inland road | Medium risk | The project is working closely with the State of Kosrae coastal engineer on the best design of coastal protection to prevent the strong water surge and high tide from reaching the coastal road, which has been severely damaged and eroded.
Logistical/transport problems and/or prohibitive costs leading to delays in arrival of people and/or materials | Medium risk | The project PMU is seeking update from the shipping agency for a weekly update on schedule of boats traveling to the target communities. The schedules are flexible and can be changed on a last minute basis.
Traditional values and governing structures restrict the participation of women | Medium risk | The inception workshops invited women group to participated and many women were active in the discussions. It is also planned for the community inception to include traditional leaders and seek their inputs on the project implementaiton plan. It is also recommended to have seperate women meeting from men during consultations for the women to free exprees their viewpoints on the project's activities.
Limited or no buy-in from communities or island council | Low risk | The national and state inception workshop involved members of the target communities and seeked their support. The communities expressed their support by accepting to office the community coordinators in their municipal offices. Currently the six community coordinators are working out from the municapal offices.
Theft of assets from the water systems | Low risk | The project is workinig with the municpal and national governments to treat any infrastructure build by the AF project to be considered national property for the duration of the project, thus, any damage to the infrastructure will be considered a national offense. In addition, the community coordinator role will be to make sure the infrastructure are secured and well protected and well managed.
Delays in expediting funds to state and community project units to execute project activities | Low risk | It has been decided for all funds to be manage at the national level for any procurement. The project is working with the state project unit to submit any request or plan of action so procuring processes can me expedited to cover the cost of activities.
Delays in acquitting funds | Low risk | It is important for a quarterly reporting on finacnes and regular update between the executing and implementing entities to know the financial status of the project so necessasry plans can be in place for the project to compliment other related projects that are having the same activities and objective as the AF project in the event the fund is not spend.
State run ships to outer islands are unreliable and very slow to get to many outer islands, and only stay on island for half a day (on average). | Medium risk | The PMU has introduced the project to the State run ship management and have come to an agreement that the project can request for the boat to stay a little longer at the target communities if the project requests. It is also agreed that the project can charter the boats.
Team/ island communication difficulties (e.g., only have shortwave radio) | Low risk | Agreement have been in place between the project and the relevant State agencies for the project officers at the state level to utilize their SSB radio to communicate to the community coordinator on the outer islands/ target communities. In addition, it is the duty of the state officers to communicate on a regular basis with the communities to share updates with each other.
Difficult to reach out and train teachers in Outer Island schools | Medium risk | The project is workiing with the national Department of Education for possible budgetary arrangment to invest in a climat change program to be integrated in the educational system. Project has requested for the Department of Education to develop a system on Climate change.
Land issues (disagreement/conflicts over access of land for installation tanks/reserves) | Medium risk | The project and the state are arranging for a requirement for easement to be signed by all land owners whose lands will be used to install the project infrastructures/ technlogies. The Kosrae State project officer is working closely with relevant department to have all the easement signs for the construction of the inland road. The State of Kosrae is exploring ways to contact the land owners that are living out of the state of Kosrae.
Unsuitable infrastructure (e.g., house roofs can’t support catchment systems) | Medium risk | The project has identified the government engineering agency to be the technical adisor on installation and repair of infrastructures.
Agreement cannot be reached with all landowners on easements required for building the inland road | Medium risk | Project is revisitng the agreements between the state and the landowners to see if any land owners has not signed the agreement
Phase II (upgrade to hot-mix asphalt pavement) starts during implementation of AF project | High risk | The project and the state of Kosrae is exploring other resources to finance the phase II. In addition, the project has incorporated the design of road to support the Phase II
Implementing partner has inadequate capacity | Medium risk | The project requires any activities to be implemented needs to be bidded out publicly so the most qualified implementing partners can be identified and selected to implement the activities.
Locally available printing, video and audio production capacity | Low risk | The project will seek printing companies and communication companies locally to support the project. In addtion, project will source outside the Federated States of Micronesia for pinting and communication services if services is limited locally.
There is no capacity on island to carry out needed trainings | Medium risk | The project has identified NGO and implementing partners that can carry out trainings in the target communities to enhance population's capacity on the project activities.
There is no political will and commitment from island leaders, and municipal government | Low risk | The project inception workshops have secured the political support the project needed.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Not at this stage
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Not at this stage

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | n/a
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Gender is not mainstreamed into the Framework for National Water and Sanitation Policy for the FSM Gender issues are not addressed in the National Water & Sanitation Policy, National Water Outlook Program (activity 1.4.1) and the Water Sector Investment | • Hire a gender specialist to undertake a gender-sensitive review of the policy framework • Ensure specialist refers to experiences and tools from previous CCA projects, e.g., PACC, GCCA, IWRM, Pacific Gender & Climate Change Toolkit • Use findings from the review to inform and strengthen the water and sanitation policy, national water outlook program and water sector investment plan | tbc
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Habitat destruction, including removal of any large tree species particularly endemic species such as Nunu (Horsfieldia) | Road placement will avoid the need to remove large, mature trees and avoid clearing of slopes greater than 30%
|  |  | Spread of invasive species | All machinery and equipment to be cleaned before and after transporting it to or from the development site
|  |  | Road construction directly impacts on mangrove or wetland ecosystems | • Ensure no part of the road and easement is below the 4m contour. • Refer to Erosion and Sediment Control Plan in ESMP Annex 1
|  |  | Coastal revetment may directly impact on mangrove stands | No heavy equipment to encroach close to or impact on the root system of the mangrove stands
10 – Conservation of biological diversity |  |  | Increase sediment run- off and siltation impacting on down stream ecosystems including streams, wetlands, mangrove & coastal areas | • Implementation and enforcement of Erosion and Sediment Control Plan • Community planting of riparian and buffer zones
|  |  | Potential increase in localized suspended sediment in the water column at high tide as a result of removal of the existing emergency armour material and regrading the underlying beach, impacting on the beach and coastal ecosystems | • Adopt a staged approve to remove the existing armour layer, reprofile the underlying beach, lay the geotextile filter layer and replace the concrete slab/bock and rock armour layer. This will ensure that there is a minimal length of beach exposed at any time reducing the potential for increased suspended sediments at high tide. • Stockpiles of beach sand, coral rubble or rock armour will not be located where material can be washed in to a drain, stream or wetland area, including on a road pavement, on an overland flow path or within 15 m of a stream bank, wetland or mangrove. • Implementation and enforcement of Erosion and Sediment Control Plan
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Minimal material wastes generated that will include left over timber other materials generated from construction work | Waste materials generated are properly stored and if used by communities, are well aware of the safety and storage procedures.
|  |  | There is potential for surface and groundwater contamination from release or spills of fuel and lubricants during fuelling and maintenance of construction equipment. Waste materials generated include cleared vegetation, topsoil and geotextile materials | • Safely store, control and dispose of any oil, lubricants or other materials associated with equipment operation and construction, in line with advice from KIRMA. Oil, lubricants and other materials to be stored in approved containers that are properly labelled, at a site approved by KIRMA, and in accord with any specific directions provided by KIRMA. Approval will be sought from KIRMA before disposing of oil, lubricants and other materials at an approved disposal site. • Place all non-hazardous, non-recyclable solid waste in containers and empty and dispose of to a permitted landfill site regularly. • Care will be taken to prevent any releases or spills of fuel and lubricants during fuelling and maintenance of construction equipment. To prevent the substances from entering the ground, drainage areas or water courses, appropriate storage containers and bunds will be used. • Recover any oily debris and contaminated soils and dispose of as directed by KIRMA. • Provide adequate sanitary convenience that meets public health and environmental requirements, for construction staff on site • On completion of the works, remove all surplus materials and construction debris and recycle or dispose of in an appropriate manner. • Reinstate and revegetate any remaining exposed earth surfaces to match the surrounding topography and vegetation.
|  |  | There is potential for beach contamination from release or spills of fuel and lubricants during fuelling and maintenance of construction equipment. Waste materials generated include cleared vegetation, topsoil (including natural sand, gravel and coral rubble material) and geotextile materials | • Store, control and dispose of any oil or other materials associated with equipment operation and construction • Place all nonhazardous, non-recyclable waste in containers and empty and dispose of to a permitted landfill site regularly. • Store lubricants and used oil in approved containers and promptly remove from site and dispose of as directed by KIRMA. • Care will be taken to prevent any releases or spills of fuel and lubricants during fuelling and maintenance of construction equipment and prevent from entering the ground, drainage areas or water courses by using appropriate containers and bunds. No such activities will be undertaken within at least 15 m of the coast. • Recover any oily debris and contaminated soils and dispose of as directed by KIRMA. • Provide adequate sanitary convenience that meets public health and environmental requirements, for construction staff on site • On completion of the works, remove all surplus materials and construction debris and recycle or dispose of in an appropriate manner • Reinstate and revegetate any remaining exposed earth surfaces to match the surrounding topography and vegetation. • Comply with permit conditions per Permit issued by KIRMA Board on 15 September 2016 (Annex 10)
13 – Public health |  |  | Injury to the community / public from construction works • Contamination of water sources | • Post signs on construction area to keep people out • Check that area is secure each morning prior to construction and equipment moving • Ensure appropriate hygienic and sanitation practices are followed
|  |  | Injury to the community / public from construction works • Contamination of water sources | • Post signs on construction area to keep people out • Check that area is secure each morning prior to construction and equipment moving • Ensure appropriate hygienic and sanitation practices are followed
|  |  | Injury to the community/ public from construction works Public health disease out break | • Post signs on construction area to keep people out • Check that area is secure each morning prior to construction and equipment moving • Training workshops on construction will be carried out as required • Ensure Basic Water, Sanitation and Health (WASH) practices are followed • Ensure water conservation awareness sessions conducted
|  |  | Disturbance to community activities from noise | • Construction work will only be carried out during normal business hours • Regular inspection of machinery to ensure it is in good working order
|  |  | Injury to the community/public from construction works | • Install appropriate signage, fencing and lighting around the development site prior to construction commencing • Check that the area is secure each morning prior to construction and equipment moving • Assign personnel to manage traffic movement and safety, as required
14 – Physical and cultural heritage |  |  | Possible destruction to cultural and historic sites | • Immediately stop construction activities and notify the relevant agencies, if any historic resources are found. • Activities will not resume until permission is granted by the Historic Preservation Office • Minor shifts in the road alignment to avoid destruction of cultural and historic sites
15 – Lands and soil conservation |  |  | Potential for catchment drainage pathways to be impacted from changes to drainage alignment Increase erosion of cleared / exposed soils and sediment run off / high turbidity in waterways during construction | • Bridge and culvert design are based on the most recent extreme rainfall intensity amounts available for Kosrae (ADB, 2005) and shown in Figure 25. • Design bridges and culverts to accommodate a 25 year return period flow. • Design bridge and culvert wing walls to avoid bank erosion immediately upstream/downstream of each structure. • Rock mattresses or equivalent installed to prevent any erosion of either the upstream or downstream water course (where necessary) • Energy dissipation measures installed to minimise downstream erosion. • Refer to Erosion and Sediment Control Plan (Annex I of the ESMP)
|  |  | Increase in storm water runoff and surface erosion | • Align the road to minimise long sloping sections by having shorter steep sections interspersed with flatter sections that follow the topographical contours. • Construct in- or out-sloping road surfaces to encourage greater lateral flow. • Intercept longitudinal water movements with dips or cross drains. • Construct regular check dams along sloping sections of the road using graded rock. • Use sandbags as a temporary measure until the rock check dams are installed.
|  |  | Increased suspended sediments in the nearshore water column and the potential for exacerbated erosion along adjacent (downdrift) sections of coast. | • No burning of ground cover for clearing • No removal of vegetation from the shoreline berm beyond the southern extent of the proposed defences at Paal and Mosral. • Stockpiles of beach sand, coral rubble or rock armour will not be located where material can be washed in to a drain, stream or wetland area, including on a road pavement, on an overland flow path or within 15 m of a stream bank, wetland or mangrove. • All rock used in the construction of the defenses will be volcanic in origin, and come from licensed quarry sites All rock used in the construction will be clean and free from silt and other loose terrestrial material. • Adopt a staged approach in removing the existing armour layer, re-profiling the underlying beach and lay the geotextile filter layer to replace the concrete slab/bock and rock armour layer.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No - the Project Manager only commenced in October 2018 and the project is still undergoing establishment during the reporting period. Monitoring will commence in the 2019 calendar year.
Have unanticipated ESP risks been identified during the reporting period? |  | n/a
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE presented the ESSMP to participants at the Inception Workshop and facilitated a discussion around all aspects of the plan. There were no comments or concerns about the ESMP and it was reaffirmed that the KIRMA and other project stakeholders have a key role in supporting the implementation of the ESMP. The approval of any changes to the ESMP as well as monitoring compliance would be integrated into the National Level Project Steering Committee ToR.
Have the implementation arrangements been effective during the reporting period? |  | During the reporting period the IE undertook an internal assessment of its ESS capacity and implementation procedures since the endorsement of its ESS Policy in 2017. Following this an external audit of SPREPs ESS Policy and procedures has been planned for mid 2019 to build on and enhance current policy and practice. As part of this, key projects currently under implementation have had or have scheduled a review of its ESMP and implementation capacity by external ESS experts that SPREP has procured through request for quotes (3) and selected on a Quality Cost Based basis. This includes a review for the FSM project which is scheduled for June 2019 and will include training for project staff.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The construction part of the project has not started yet, however, the EE has identified relevant officers who will be trained on the ESP safeguard measures, which is planned for June2019.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Project activities affecting the environment has not commenced
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The Projects ESMP clearly indicates who is responsible for specific actions to mitigate risk. Stakeholders at the inception workshop, such as Kosrae Island Resource Management Authority (KIRMA), understood the importance of ESMP and the project team that subsequently came on board express awareness of ESMP. As there were delays in recruitment no major activity occurred during the reporting period. SPREP has scheduled an external review of the ESMP and implementation for June 2019 and to ensure people are aware of their roles and responsibilities including the monitoring and reporting on ESS . The review is to occur ahead of any construction work on the road relocation.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | An external ESS expert will be reviewing the project's ESMP and project developments to date in June 2019. She will work with the project team in country to identify an USPs of which the ESMP will be updated and reported to the AF.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None received during reporting period
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | NO
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | NO
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.3 National Water and Sanitation Policy endorsed with climate and disaster risks and resilience, and gender mainstreamed |  | Number of women, men, and youth participating in gender and climate change trainings, meetings and public awareness activities
|  | A gender-focused policy on water and sanitation | No gender-focused policy on water and sanitation | NWSP with climate risks and resilience, and gender incorporated, is endorsed and adopted by a resolution of the President and Government of FSM (Four state endorsement)
Output 2.2 Water Harvesting and Storage System installed in 6 atoll islands |  | Number of women, men and youth with access to water from WHSS systems installed at household and community level (church, school and community halls) | Water systems and tanks exist on the islands in poor conditions (leakage, contaminated), including poor guttering and down piping | 100% of target population have access to enough potable water from WHSS; At least 20% members of the island council and women, men, and youth community groups trained in maintenance of community water harvesting and storage systems.
Output 2.4 3,253 people trained on water conservation and management including coastal protection and livelihods in 6 outer islands |  | Number of women, men, youth trained in water conservation and management methods and practices | Limited awareness about climate change impacts on water use and water resources on low-lying island environments and communities | By the end of the project, at least 80% of targeted women, men and youth trained in water conservation and management methods and technology
Number of women, men, youth trained in water data collection and quality testing
Most significant understanding gained by youth, women, and men through climate change adaptation training
Number of women, men and youth carrying out survey of potable and non-potable water needs, water use, storage, sanitation, conservation methods, practices
Outcome 4: Capacity and knowledge enhance and developed to improve management of water and coastal sectors to adapt to climate change |  | Number of men, women and youth participating in trainings and planning meetings | There is a lack of gender sensitized management and execution of climate related projects and programs | At least 50% of perception responses (at least 50% are from women) to significant level of awareness and acknowledgement of gender and climate change benefits-compliance with natural resources management and gender dimensions of climate change
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
During the State inception workshops, there were fewer women participants than anticipated. It is hopeful that for the community inception workshop there will be more women participants since there will be a separate meeting specifically for the women. |  | poor
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | An overview of the Adaption Fund, and SPREP Gender Policies were provided to the Inception workshop. The National Gender Focal Point also provided a detailed overview of the National Gender Policy. After some plenary discussion, participants were asked to break into State based groups to discuss how gender could be an issue in the design and delivery of activities, before then presenting back to the workshop.
Have the implementation arrangements at the IE been effective during the reporting period? |  | • It was agreed that Gender be incorporated into the Project Steering Committee ToR as a basis for ensuring that gender considerations are discussed as part of the annual work planning process. • Further, the DECEM project team was encouraged to explore how they could actively support delivery of the National Gender Policy, through delivery of the project. • The National Gender Focal Point is to be included in the Steering Committee Membership
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The Executing Entity has coordinate with the national Gender program focal point to localize or find the best and appropriate usage of the SPREP's Pacific Gender and Climate Change Toolkit in advocating climate change and its impact on women and disadvantage group in the target communities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | The activity requiring the arrangement has not commenced yet during the reporting period.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The activity requiring the arrangement has not commenced yet during the reporting period.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8] |  | A mechanism was established and agreed in the Environment and Social Management Plan-FSM Adaptation Fund Project.
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1. Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level |  | Not applicable at this time of the project |  | N/A
| Output 1.2. State regulations for development projects amended to consider climate change risks and resilience measures |  | Not applicable at this time of the project |  | N/A
| Output 1.3. National Water and Sanitation Policy endorsed with climate and disaster risks and resilience, and gender mainstreamed |  | Not applicable at this time of the project |  | N/A
| Output 1.4. National Water Outlook and Water Sector Investment Plan developed and implemented |  | Not applicable at this time of the project |  | N/A
| Output 2.1. Outer Island communities orientated to CC, SLR and adaptive capacity measures involving water, health, sanitation and environment |  | Not applicable at this time of the project |  | N/A
| Output 2.2. Water Harvesting and Storage System (WHSS) installed in 6 atoll islands |  | Not applicable at this time of the project |  | N/A
| Output 2.3. Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side |  | Not applicable at this time of the project |  | N/A
| Output 2.4. 3,253 people trained on water conservation and management including coastal protection and livelihoods in 6 outer islands |  | Not applicable at this time of the project |  | N/A
| Output 2.5. Teacher’s Guide on Climate Change developed to improve climate change learning in FSM schools and training institutions |  | Not applicable at this time of the project |  | N/A
| Output 3.1. 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to an unsealed rural road standard for future relocation |  | Not applicable at this time of the project |  | N/A
| Output 3.2. Transitional coast protection at Mosral and Paal upgraded for immediate coastal protection |  | Not applicable at this time of the project |  | N/A
| Output 3.3. State support program to access land in upland areas established |  | Not applicable at this time of the project |  | N/A
| Output 3.4. Community-Based Ecosystem Management strengthened |  | Not applicable at this time of the project |  | N/A
| Output 3.5. State support program to assist access to finance for vulnerable households established |  | Not applicable at this time of the project |  | N/A
| Output 4.1. Climate resilient municipality development plans developed and communicated |  | Not applicable at this time of the project |  | N/A
| Output 4.2. Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders |  | Not applicable at this time of the project |  | N/A
| Output 4.3. Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change |  | Not applicable at this time of the project |  | N/A
| Project Management |  | The Project Management Unit established and fully staffed |  | The Project Management Unit is established and the Project Manager appointed in October 2018. Recruitment is underway for the full contingent of PMU staff. | S
|  |  | a. The National Steering Committee to be established b. National and State level inception workshops held |  | a. The National Steering Committee was established and endorsed the 2019 workplan b. Members were updated on project progress | S
|  |  | Staff to coordinate activities within respective jurisdictions |  | State Stakeholders have been made aware of the Project and proposed activities | S
|  |  | Inception workshops at the National and State level to be undertaken (12 in total) |  | The National Workshop was held XXX (refer attached report). During this reporting period three (3) State level inception workshops have been held | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Richard Moufa
| Email: | richard.moufa@gov.fm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Given the delays in the establishment of the Project Management Unit and the recruitment of staffing, the PMU has only been operational since October 2018 - five months of the reporting period. Selecting the qualified officers for the required positions for the project was difficult since limited qualified persons are available in the country. It took more that six months to filled all the positions. Once the positions are filled, orientation for the staff and planning for inception workshop was undertaken with communication through emails and telephone calls, since face to face meeting was not possible due to the distance between national and the states. A second key area of focus during the limited timeframe was the establishment of the National AF Steering Committee. This was a difficult task since the national government has limited staff with busy schedules, and there is difficulty in obtaining commitment to the Steering Committee membership. However, with detailed coordination, the project was able to get the relevant Departments on board and assigned respective staff to be formal member of the Committee. In addition, the Committee's first meeting was called and was provided with great support from members on the expected outcomes of the project with its proposed activities and workplan.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management policy and regulatory frameworks |  | Project commenced March 2018, therefore no progress expected during reporting period |  | n/a | n/a
| Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones |  | Project commenced March 2018, therefore no progress expected during reporting period |  | n/a | n/a
| Outcome 2b: Increased awareness of climate change through formal climate education |  | Project commenced March 2018, therefore no progress expected during reporting period |  | n/a | n/a
| Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change |  | Project commenced March 2018, therefore no progress expected during reporting period |  | The PMU has commenced the Kosrae road construction activity in identifying the road design firm through a tender procurement process | n/a
| Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change |  | Project commenced March 2018, therefore no progress expected during reporting period |  | n/a | n/a
| Project Management |  | a. Establish Project Management Unit b. Undertake Inception Workshops |  | The Project Manager has been recruited, and ongoing recruitment to fulfill the PMU roles is continuing. Overall, the EA/PMU is in startup mode during the reporting period. Inception workshops at the national level and within some States has occurred | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Melanie King, Manager (Project Coordination Unit)
| Email: | melaniek@sprep.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Implementing Agency Comments: The project has had a delayed start with the Project Manager only recruited in October 2018 and final PMU staffing completed in 2019. Since this time, the Executing Agency has made efforts to recruit staff members, undertake State level inception workshops and commence ToR and contracting for the Kosrae road design. Given the delays, it is not possible to rate the project for the reporting period, however, it is expected the 2019 PPR will demonstrate significant progress.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management policy and regulatory frameworks | Number of national and state level stakeholders participating in EPA, R&D, NWTF meetings, planning and implementation of activities. Number of relevant sector and community based consultations carried out to identify institutional capacity gaps and capacity needs Number of staff across sectors trained and build their awareness on the new regulations enforcement Number of regulatory framework drafts developed for development projects regulations at state level | FSM regulations for development projects does not consider climate risks and resilience, with the exception of the Kosrae State Regulations for Development Projects 2014 Existing policy lacks consideration of existing climate change risk and disaster risk and projected risks A framework for developing a water and sanitation policy, water outlook, and water sector investment plan exists but no plans that integrate climate risks and consider gender-sensitive approaches | Gather existing legislation and policies at national level; drafting of required Consultant Terms of Reference to undertake activity. Announcement of Expression of Interest for Consultancy will be advertised in November 2018. The ToR for the activity has been shared with local NGOs and regional agencies and consultant firms to see if they have capacity.All are interested and will submit EOI. AF PMU is drafting the EOI for announcment and sharing ToR with DECEM for comments and approval. The ToR for needed consultant is still reviewed by SPREP for apporoval before it is announced for interested parties. It is aimed to be announced in May, 2019 | At least two relevant regulatory frameworks endorsed and adapted to guide and support development of regulations on development projects at national and state level. Climate change is mainstreamed into the FSM National Water & Sanitation Policy, Water Outlook Program, Water Sector Investment Plan, national and state development projects.
Output 1.1 Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | Number of stakeholder organizations participating in legal and regulatory assessment meetings Number of regulation, policy and guidance documents drafted at national level | No current and future climate risks mainstreamed into current legislation, regulation, policy and guidance documents for development projects in FSM | This consultation will be packaged with Consultation activity in Activity 1.1.1 (Output 1.1); Consultancy Terms of Reference is in drafting process; The set of activities under this Output 1.2 will be done in parrellel with activities under Output 1.1 | A legislative framework to guide national level regulation of climate resilient coastal and marine resource management at national level A national level regulation for development projects with climate risks and resilience incorporated developed, endorsed and adopted
Output 1.2 State regulations for development projects amended to consider climate change risks and resilience measures | Number of stakeholder organizations participating regulatory framework workshops at state level Number of regulation, policy and guidance documents drafted at state level | No current and future climate risks mainstreamed into current legislation, regulation, policy and guidance documents for development projects in Yap, Chuuk and Pohnpei States | This consultation will be packaged with Consultation activity in Activity 1.1.1 (Output 1.1); Consultancy Terms of Reference is in drafting process; The set of activities under this Output 1.2 will be done in parrellel with activities under Output 1.1 | At least one state has endorsed and adopted changes to its state regulation for development project that consider climate risks and resilience
Output 1.3 National Water and Sanitation Policy endorsed with climate and disaster risks and resilience, and gender mainstreamed | Number of stakeholders participating in NWTF meetings, planning and implementation of activities Number of women, men, and youth participating in gender and climate change trainings, meetings and public awareness activities Number of stakeholders (organizations) participating in NWSP awareness activities | No national climate resilient water and sanitation policy No gender-focused policy on water and sanitation | Gather required water policies, regulation and water resource frameworks along with Gender Policies. At the same time, drafting of Terms of Reference for the team of consultant (expert on water resources) to undertake the task of reviewing policies and integrate gender component it the water and sanitation policies. The advertisement of consultancy will be announced in November 2018. This activity will be undertaking after Activity 1.3.1. The AF PMU has been in dicussion with relevant national department to revise and update the existing draft policy, including the NWTF. Department is looking forward to work on the policy in 2019.Pohnpei State is the only state that has a water management policy and AF PMU is in discussion with local NGO who develop the policy for the possibility to replicate such work with the other 3 states. The relevant NGO is pleased to carry out the same policy for the other FSM States. However, they are also aware of the procurement process of such consultancy. The official EOI will be publicly announced in May, 2019 | NWSP with climate risks and resilience, and gender incorporated, is endorsed and adopted by a resolution of the President and Government of FSM (Four state endorsement)
Output 1.4 National Water Outlook and Water Sector Investment Plan developed and implemented | Number of women, men and youth and stakeholder organizations participating in NWTF meetings, planning and implementation of activities Number of stakeholder organizations participating and implementing water outlook programs Number of partnerships strengthened under the water sector investment plan | No water and sanitation policy Limited emphasis on the importance of social roles and responsibilities of women, men and youth in water, sanitation and climate change policies | In discussion with relevant National Department and stakeholders and members of the National Water Task Force to revive the program. Advocating and anticipate for reactivation of the task force in December 2018. The national water task force has not been active since 2011. The Dept. of R&D is considering seeking President few on which department will be the leading entity. Although so far the President has not make any decision on which leading agency, the Dept. of R&D is looking into initiate the work on reviving the Water Task Force and collaborating with other relevant national department to move foreward on the water program. In consultation with the FSM Meteorology Service on the required activities and supports for Terms of Reference for consultants or team of experts to undertake the development of the Water and Sanitation Investment Plan (WSIP). The National weather office (NOAA) has agreed to support the project in the Climate Change awareness and water outlook, plus it has assigned two of its staff to work with AF PMU. Aiming for February to sit down with staff and go over and map out a activity plan. The respective OFO at each of the states have been instructed to meet with each of the NOAA offices in their states on this project and see how best to approach collaboration effort. | NWSP with climate risks and resilience, and gender incorporated, is endorsed and adopted by a resolution of the President and Government of FSM (Four state endorsement) National Water Outlook Program endorsed adopted and implemented National Water Sector Investment Plan endorsed, adopted and implemented
Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones | Available capacity (volume in cubic litres) of water per person per day Storage capacity for potable and grey water at household and community level Rainfall data collected on a monthly basis used to provide advice on water conservation practices and advice on other development sectors (farming, fishing, etc.). | Poorly maintained traditional water harvesting and conservation infrastructure and technology available. It cannot cope with the dry seasons. No monitoring stations on island to collect and monitor rainfall data to advice on water conservation practices including advice on other sectors |  | By end of project, at least 80% of households have collected enough water to respond to drought events By end of project, at least five project islands and its communities have increased storage capacity to store potable and grey water. By end of project, women, men, and youth know how to use and read rain gauges
Output 2.1 Outer Island communities orientated to CC, SLR and adaptive capacity measures involving water, health, sanitation and environment | Number of men and women in six outer islands trained in CC, SLR and adaptive capacity measures for water, health, sanitation and environment | The six island sites have limited understanding of the impacts of climate change and sea level rise on the water, health, sanitation and environment sectors Limited knowledge and experience in the application of climate change information to adaptation planning in outer islands | AF Project is in discussion with relevant National Departments for their respective areas for support of specific activities (Health, Resources and Development and Dept. of Infrastructure) during community based inception workshop and awareness of project. Initiate discussion with mayors from project sites for assessment of existing water catchments. AF PMU has already obtain designs from the FSM TC&I for a 5000 gallons tank that is gender friendly with estimated costs. As a result of various consultations with member of communities and outcome of the inception workshops, it has been agreed that an assessment for status and conditions and preference of tanks need to be undertaken. Work with relevant national and state departments and NGOs for ground truthing assessment expert for such task. Project will work with relevant agencies for ToR of consultancy to carry out the activity. Few NGO partners and consultant have discussed their capability to carry out such activity, with different mapping designs. Pohnpei EPA claims its staff can carry out the activity for Pohnpei. PMU is working on ToR for expert. AF PMU has initiated discussion with local leaders to identify resource persons on traditional knowledge on water resource management. AF PMU will wait for R&D for update on this. AF PMU has initiated discussion with local leaders to identify resource persons on traditional knowledge on water resource management. AF PMU will wait for R&D for update on this. | At least 60% of the community population in the six outer islands (of which close to 50% are women) are educated on the impacts of CC and SLR on water, health, sanitation and the environment, and have their capacity enhanced to develop adaptation measures to address these impacts At least 80% of those that participate in the above capacity building activities have acquired knowledge and skills to develop and implement adaptation plans and actions
Output 2.2 Water Harvesting and Storage System (WHSS) installed in 6 atoll islands | Number of WHSS installed in 6 islands Capacity of storage water (in m3 and ft3) constructed / maintained, per household and per community Number of women, men and youth with access to water from WHSS systems installed at household and community level (church, school, community halls) Agreed maintenance schedules for installed WHSS | Water cisterns and tanks exist on the islands in poor conditions (leakages, contaminated), including poor guttering and down piping There is no culture of maintenance of water harvesting systems at community level due to lack of specialised equipment and maintenance planning. Very limited awareness of WASH techniques useful for application during drought periods and post-typhoon situations | This activity will commence in early 2019 after OFO and Community Coordinators are on board. Selection process is currently ongoing. Assignment for assessment of water resources have been given out to the newly hired community coordinators. PMU is also working with existing water project from SPC on their assessment on target sites. SPC has two project similar to AF: RENI and ASCE. Discussion on complementing each other is positive. The AF, RENI and ASCE have already worked together in shareing information, contacts, newtwork and supporting each project on their activities. AF PMU is working with SPC on finding our what they have provided/ supplies to the target sites, Satawan, Lekinioch and Kapingamarangi. Mostly fiber glass and Plastic tanks. The inception workshops have shown the community might require more capacity of tanks. The SPC project does not provide sufficient tanks that can sustain the community for two weeks time without rain. Working with NGO's if already have documents or guidelines for such activities. The process will go through the procurement processes. | 100% of target population have access to enough potable water from the WHSS At least 20% members of the island council and women, men, and youth community groups trained in maintenance of community water harvesting and storage systems
Output 2.3 Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | Number of SCT units constructed and in working condition Changes in level of nutrients in soil and groundwater Percentage of change in dissolved oxygen in the lagoon levels | Currently the majority of people use the lagoon for toileting. The existing water-flushed toilets or pit-latrine toilets are in poor condition, with leakage into soil and lagoon. Contamination / eutrophication of lagoon from excessive nutrient input from human waste | AF PMU is working with relevant agencies and entities to share designs, plans and guidelines for self-composting waterless toilets. The designs and plans will be shared with communities for feedbacks during inception workshops. SPC has shared designs and booklet on their similar project. During the inception workshop, the participants liked the design and the concept. This activity will commence in early 2019 after OFOs and Community Coordinators are on board. Selection process is currently ongoing. For the state of Pohnpei, the inception workshop have recommend that a prototype be built on the main island of Pohnpei to train the relevant stakeholders on the construction, usage and awareness to assist when advocating such technology to the target community. They are aiming for it to happen in June, 2019.AF PMU is in consultation with DOE, MOH and relevant NGO on the suitable and appropriate WASH program in target site schools and target communities. AF PMU has consulted in country UNICEF office for an approach in consolitating all WASH program by NGO's to be standardized and approve by nationat Dept. of Health. UNICEF is agrees with the approach and will plan for a WASH summit this year. The goal is to have standardize awareness and messages. The AF PMU continues to work with DOH and UNICEF for standardizing the WASH model for FSM. It has been planned by DOH that a summit will be held in October 2019 to establish a national WASH framework. | By the end of the soil quality and lagoon water quality have improved as a result of reduced leakage from toilets
Output 2.4 3, 253 people trained on water conservation and management including coastal protection and livelihoods in 6 outer islands | Number of women , men, youth trained in demonstration of water harvesting and storage systems Number of women, men, youth trained in water data collection and quality testing Number of women, men and youth carrying out survey of potable and non-potable water needs, water use (quality & quantity), storage capacity, sanitation, conservation methods, practices Most significant understandings gained by youth, women and men through climate change adaptation training | Business as usual knowledge exists on water conservation and management methods and practices Limited awareness about climate change impacts on water use and water resources on low-lying island environments and communities | Initiate working discussion with SPC on previous data collection on the target areas; identifying implementing partners for the training component on water management training and collection of data. Data has been shared by SPC on the same target sites and will look into providing technical assistance where available. Each of the FSM States EPA has the cacpacity to carry out the survey, however, requires support in procurement of testing kits. | By the end of the project, at least 80% of targeted women men and youth trained in water conservation and management methods and technology
Outcome 2b: Increased awareness of climate change through formal climate education | Number of schools with climate education curriculum introduced Level of awareness of climate education in schools at different elementary and all grades Number of teachers trained in climate education at elementary and all grade schools | Climate education materials are available Lack of systematic training on climate education for teachers | Please refer to Output 2.5 | By end of project, at least two schools participated in the development of the curriculum plan At least 60% of teachers trained on climate education under the new climate education curriculum. At least 80% of students enrolled and taken climate education have a pass rate of 65%
Output 2.5: Teacher’s Guide on Climate Change developed to improve climate change learning in FSM schools and training institutions | Number of climate change education planning workshops carried out to identify tailored education resources to enhance learning about climate change in schools and training institutions Number of State-specific versions that is culturally relevant to teachers and students distributed to schools, providers of technical and vocational education and training (TVET) and libraries in FSM. | There are very few educational resources that address adaptation measures that are specific to FSM. Learning about climate change the Pacific way: A guide for Pacific teachers exists and has been applied in Fiji, Kiribati, Samoa, Tonga and Vanuatu. | AF PMU has initiated discussion on having climate change subject be thought in the target site's school. Discussion is with national DOE and state DOE. Project is also seeking support from SPREP or other regional partners on existing good practice on Climate Change curriculum in other PICs.The AF PMU has been approached by Pacific Resources for Education and Learning (PREP) to informed me that they are working with nationala and state DOE on curriculum that include Climate Change subjects. AF PMU will continue follow up with PREP and DOE on the progress of this program. | By the end of the project, at least 80% of teachers employed in all schools of the targeted six islands have access to the correct specific version of the Guide. By the end of the project, at least 25% of schools in the six targeted islands and 50% of targeted training institutions have used and applied the guide to enhance climate change learning
Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change | Number of women, men and youth benefitting from the access provided by inland road Quality condition of road after extreme rainfall event | Malem-Utwe coastal road highly exposed to severe coastal erosion and is in high risk of being washed away within the next 10 -30 years Unsealed inner road limits access of communities inland | Program is still in development stage | At least 1,476 inhabitants of Malem and Utwe have increased coastal resilience to inundation and erosion. At least one landslide, flooding or agriculture-related risk management response has been implemented by Malem and/or Utwe By the end of the project replication and up-scaling activities are explicitly informed by lessons learned and good practices relating to gender in Kosrae Targeted beneficiaries are the 2,283 people resident in the Malem and Utwe municipalities. Indirect beneficiaries include 4,333 residents of other Kosrae Municipalities
Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to an unsealed rural road standard for future relocation | Number of road easements obtained against number of road easements required Number of kilometers of inland road constructed to an unsealed rural road standard Length of new and re-lay water mains along Malem - Yeseng - Mosral - Kuplu section installed and connected to existing water supply at Malem and Finfokoa. Length of new power line along entire length of inland road from Malem to Utwe via Kuplu Wan installed Length of new tele- communication lines along entire length of inland road from Malem to Utwe via Kuplu Wan installed | Current inland road (1.5 km) is gravel only, in poor condition, and does not meet climate resilience standards No water mains are connected from Malem and Utwe except old water mains. No power lines and telecommunication lines from Malem to Utwe via Kuplu Wan | AF PMU has finalize the Terms of Refence for the required civil engineer who will undertake the task of road design, survey, select construction company and monitor and report progress of work. The advertisement of Expression of Interest is scheduled to be publicly announced in November until December 07, 2018. With the support and advice from FSM TC&I, AF PMU has selected an engineering company with its Fee Proposal and now DECEM has designated a negotiating team to negotiate with the company for a more reasonable fee. The negotiation will commence late Jan. or early Feb. The Project as selected a Guam base engineering consultant company, EMSPCO, to undertakent the design work. The company is planning to hire a local surveyor to commence the survey once the contract is finalized by the national government. It is aimed that the contract will be finalized in May 2019. | Approximately 8.5 km of inland road of the Malem-Utwe road constructed to climate resilient unsealed rural road standard with access routes to the two villages Water running through connected and completed mains for the Malem – Yeseng – Mosral – Kuplu section New power and telecommunication lines installed along the entire length of the inland from Malem to Utwe via Kuplu Wan
Output 3.2: Transitional coast protection at Mosral and Paal upgraded for immediate coastal protection | Length (in metres/miles) of coastline revetted | Ineffective loose boulder defences at Mosral and Paal patched only after extreme events | Kosrae state has initiated portion of the Coastal Protection work with their own design and cost. The AF PMU is working closely with Kosrae's project focal point to monitor the work to be in the same scope of design with the project. AF PMU is working on the ToRs for the engineer who will undertake the coastal protection work. With advice from FSM TC&I, this particular component has been assign to Kosrae DTI to undertake the design and bidding process for contractor. The status as of Jan. is Kosrae will wait for the new administration to be in place. The new administration has just swore in in January.The new administration is in place. Portion of the coastal was upgraded using government fund. However, the work was not done properly, thus the water surge and strong wave during hight tide still reaches the road and erosion of coastal still happening. The AF might look into elevating the now completed work to a higher level. The Kosrae government is working on design to compliment what it has just newly constructed. | Mosral and Paal coastline revetted in the order of 2.5 km or 1.6 miles
Output 3.3: State support program to access land in upland areas established | Percentage of household without land inland who accessed land inland Area (m2) of safe land inland identified for access | No state government program to assist access land in upland for those without land | This activity will take research and coolaboration within the Kosrae government departments and community leaders. The AF OFO will undertake the initiative arrange meeting among stakeholders for the initiation of the activity. The AF PMU is still in hiring process/ selection process for the Kosrae base OFO. The OFO will be onboard by November 2018. Kosrae OFO has not been hired yet due to difficulty to assemble the steering committee and the new administration is not fully in place. AF PMU is still waiting for Kosrae to provide necessary documents that were claimed be available and critical to be available to us during the negotiation process with the engineering company. Such documents are geological survey reports, topographic survey..etc. The Kosrae OFO was hired in March. He has not been following up on easement paperwork and planning for community awareness. Finalizing the easements is the crucial part of the work. More that 80% has been signed. | At least 30% of the household in the coastal hazard zone with no land inland access land (18 HH in Malem; 9 in Utwe)
Output 3.4: Community-Based Ecosystem Management strengthened | Number of women, men and youth trained on community-based ecosystem management tools Number of women, men and youth participating in planning and consultation meetings on rehabilitation of streams through community and school-led stream health monitoring programs Number of women, men and youth participating in planning meetings, implementation and monitoring of Malem and Utwe watershed management strategies | No watershed managements strategies and municipal government policies to guide community-based and community-led ecosystem management programs | AF PMU is in discussion with the Kosrae Conservation Society on the possibility for the NGO to be the implementing partner and to take lead on the activity. The KCSO is well experienced and qualified to undertake the task. KCSO has agreed to undertake the activity and is now in process of drafting a proposal of activities.AF PMU is working on the EOI for this particular activity. | At least 90% of the 1,476 inhabitants (50%) are women) of Malem and Utwe community participated in community-based ecosystem management planning meetings, implementation and monitoring activities At least one landslide, flooding or agriculture-related risk management response has been implemented by Malem and/or Utwe By the end of the project replication and up-scaling activities are explicitly informed by lessons learned and good practices relating to gender in Kosrae Malem and Utwe Watershed Management strategies developed, endorsed by Municipal Government Council and adopted for implementation and monitored
Output 3.5 State support program to assist access to finance for vulnerable households established | Number of stakeholder organizations (including development banking institutions) participating in planning meetings of the adapted finance mechanisms, implementation and monitoring Number of women, men and youth participating in community consultations on the state program No. of people who have used the adapted finance mechanism Existing housing finance mechanisms adapted Recommendations are produced by a review of programs and practices in Kosrae and other Pacific Island Countries | Existing loan mechanisms are offered by Kosrae Housing Authority and FSM Development Bank Most applicants for the FSM Development Bank loans do not meet eligibility criteria; Kosrae Housing Authority loan sizes ae small relative to home construction costs | AF PMU is seeking support from SPREP to assist with the Terms of Reference for finance consultant to undertake the task to work with the financial institution in Kosrae for the establishment of the climate change financial scheme for vulnerable residents. AF PMU has just found out that Kosrae steering committee appointed an agency called Housing and Rural Development Authority to undertake the the activity. The HRDA has already gone out to two communities to introduce the project. However, proper documentation/ or approval for HRDA to implement is missing for PMU to process reimbursments. PMU is requesting for a detail proposal from HRDA on its plan activities. In additioin, PMU has requested the support from FSM Banking Board for a possible work to seek support from GCF with coordination with Bank of FSM to apply for grant to support loan for climate change impacted communities and individual. The bankig board might also be able to seek consultant to work on banking assessment and financial mechanism. The AF PMU along with the FSM Banking Board has called a meeting with the financial institution in Pohnpei (national branches) and introduced the AF project and the relocation and financial component of it. The banking institutions are keen to help. However, they do need financial support from government as collateral for them to be able to lower the rate. The PMU is encouraging them to look into the Green Climate Fund. In addition, the banking board is reaching out to SPREP to share if there has been any example of such scheme in the region for FSM to review. | At least 20% of people enrolled and participated in consultations (50% are women) have used the adapted finance mechanism At least 1 existing program is adapted to improve affordability of finance for house construction inland Recommendations address affordability of finance Recommendations identify ways to serve needs of vulnerable household in coastal risk zones
Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change | Awareness materials on CC, SLR, Vulnerability and Adaptive capacity, and about the project is prepared in local language and distributed to community and other stakeholders Number of success stories developed and shared on briefs, brochures, pamphlets, posters prepared and distributed Number of men, women and youth participating in trainings and planning meetings | Programs carried out by various stakeholders (government, private sectors, and academic institutions) in the Outer Islands are not consolidated and implemented under island development plans that exist. No systematic approach to awareness of opportunities and issues around climate change in outer islands and community / municipal government levels There is lack of gender-sensitized management and execution of climate-related projects and programs. The approaches with existing projects are only in pilot and in silo approaches without integration across program planning | The communication has been onboard and now working on and finalizing the communication strategy plan. PMU is looking into working with DECEM's Institutional Strengthening Adaptation to Resilience to Vulnerable Islands for Climate Change (ISACC) project its to publish awareness products on climate change. The activity has been rewarded to a local NGO to undertake the task of creating the awareness materials. At the same time, PMU is also seeking on its own for consultants or agency like NOAA to come support the project with its awareness materials and training materials. The ISACC project is creating a video and AF communication officer is working with ISACC on adding on climate change component in the video. | At least eight (50%) success stories, or knowledge products generated on lessons learned and best practices have been produced, published and shared with targeted stakeholders each project year At least 50% of perception responses (at least 50% are from women) to significant level of awareness and acknowledgement of gender and climate change benefits – compliance with natural resource management and gender dimensions of climate change
Output 4.1: climate resilient municipality development plans developed and communicated | Number of women, men and youth participating in development and review of existing island / municipal government development plans Number of meetings and workshops held Number of brochures and pamphlets prepared and distributed | Existing island and municipal government development plans have not mainstreamed climate risks and resilience | This has been packeged with Output 1. | Climate change (including risks and resilience factors) are mainstreamed into Island and Municipal Government Development Plans Development plans are printed and disseminated to various stakeholders
Output 4.2 Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | Number of knowledge products (training materials, etc.) generated on lessons learned and best practices published and shared Percentage of women and men staff trained on the various technical and skill-building trainings | 0 awareness materials available and no resources to distribute | The project Communication Officer will be on board at the end of January 2019. The officer will work on this component. The communication has been onboard and now working on the communication strategy plan. PMU is looking into working with DECEM's Institutional Strengthening Adaptation to Resilience to Vulnerable Islands for Climate Change (ISACC) project its to publish awareness products on climate change. The activity has been rewarded to a local NGO to undertake the task of creating the awareness materials. At the same time, PMU is also seeking on its own for consultants or agency like NOAA to come support the project with its awareness materials and training materials. The ISACC project is creating a video and AF communication officer is working with ISACC on adding on climate change component in the video. | By the end of the project, at least 60 awareness materials and knowledge management products on the project results, on CC, V&A results, gender-based results are produced and disseminated to all relevant key stakeholders.
Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | Number of trainings, workshops and learning programs developed and carried out on CC, V&A, gender, coastal, water, project management, and climate education Number of women, men, youth trained at national, state and community level | 0 workshops organized on CC, SLR, vulnerability to CC and CC adaptive capacity 0 trained or aware of gender and CC, CC adaptation techniques on the environment, water resources and coastal rehabilitation | This activity is still in the planning stage for implementation. | 13 training and learning workshops, 8 at community level (municipality, outer island), one each at state and one national At least 1 inter-state experience exchange on lessons learned and best practices on practical and concrete island intervention At least 2 learning course programs targeting environment champions /ambassadors on CC, water resource management, or integrated coastal management course At least 1 Participatory 3D Mapping & Community Workshop

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Hiring of qualified staff was a major delay in the initial phase of the project
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The processes of contract for the hired staff contribute to the hiring processes. Constant follow up in relevant department processing the contract was a method to reduce delay.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Request support from state offices and municipal offices for project officers to utilize their SSB radios as a means to communicate project progress and issues.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | During the inception workshops, it has been stongly recommended that there should be separate meeting of women during the community inception workshops. In addition, the national gender policy was also presented in national inception workshop.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | FSM/RIE/Coastal/2015/1
Implementing Entity | Secretariat of the Pacific Regional Environment Program
Type of implementing entity | RIE
Country | Micronesia, Fed. States of
Region | Asia-Pacific
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 102844 |  |  | Total | 9869 | 5536 | 4333 | Total | 4934 | 2768 | 2166 | Total
|  | % of female beneficiaries | 49% |  |  | % of female beneficiaries | 99.6% | 50.6% | 49% | % of female beneficiaries | 50% | 25% | 25% | % of female beneficiaries
|  | % of Youth beneficiaries | 35% |  |  | % of Youth beneficiaries | 40% | 20% | 20% | % of Youth beneficiaries | 20% | 10% | 10% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 328 | 20% | Public |  | 164 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 80% |  | Coastal management |  | 80 |  | Coastal management |  | 40 |  | Coastal management
|  | 80% |  | Water management |  | 80 |  | Water management |  | 40 |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 5: Highly responsive (All defined elements ) |  | Water management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Multi-community |  | Water management | 3 | Multi-community |  | Water management | 2 | Multi-community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Water management | National | Water policy | 4 | Water management | National | Water Policy | 2 | Water management | National | Water Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 4 | 4: Enforced (Most elements implemented) |  | 4: Effective | 2 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.