## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01.04.2017 - 31.03.2018
| Project Title: | Building adaptive capacities of livelihoods, communities and ecological security in the Kanha-Pench Corridor in Madhya Pradesh.
| Project Summary: | Being one of the most crucial conservation units of the flagship species - Tiger, the Kanha-Pench Corridor (KPC) supports rich biodiversity and provides important ecosystem services like regulating hydrology and sequestering carbon. Besides its ecological functions, the landscape supports a substantial human population, mostly indigenous, who are extremely vulnerable to climate change impacts. In the last few decades, the KPC has faced severe degradation caused by anthropogenic pressures and climate change, which has reduced its ability to perform important ecological functions. The project aims to restore the corridor’s functionality by building and enhancing the adaptive capacities of its communities, livelihoods and landscape. It aims to do so by adopting a holistic approach of Ecosystem Conservation, Institutional Development, and Promotion of Climate Resilient Livelihoods.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Forests/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank of Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Direct Access | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Balaghat, Mandla and Seoni districts located in the South Eastern part of the Central Indian State of Madhya Pradesh. The important water bodies include the Wainganga, Pench and Banjar rivers. Other important areas are - Kanha Tiger Reserve and Pench Tiger Reserve. The National Highway 7 runs through the landscape. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone | Baseline data collection through Focussed Group Discussion (FGD/ Participatory Rural Appraisal (PRA)/ Geogrphical Information Services (GIS) data and baseline report preparation: 0-6 months Creation of 56 village development plans: 0-6 months Formation and strengthening of village level community institutions & capacity building: 3-36 months Participatory impact monitoring: 18-24 months, 37-48 months Implementing livelihood activities: 7-42 months Entry point activities (water related): 0-6 months Installation of agromet stations: 0- 12 months Watershed improvement, efficient irrigation mechanisms: 4-42 months Development of design of knowledge material: 7-24 months Workshops, Awareness sessions: 10-48 months Monitoring: 3-50 months Evaluation: 23 month (midterm) 45 month(final) | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 06.10.2016
IE-AFB Agreement Signature Date: |  | 22.11.2016 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 01.04.2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 31.03.2019
| Terminal Evaluation Date: | 31.03.2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - Project Inception report - Baseline report (draft) - Minutes of the Project Steering Committee - Knowledge Management Framework (draft) - Audited Financials for FY 17-18 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | - Website of the project is work in progress, expected to be completed in Y II | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatoral Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 15.05.2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Shri Shankar A Pande(CGM) National Bank for Agriculture and Rural Development | Fiji
| Email: | fspd@nabard.org, climate.change@nabard.org | Finland
| Date: | 15.05.2018 | France
| Executing Agency |  | Gambia
| Name: | RBS Foundation India | Georgia
| Email: | n.sunil.kumar@rbs.com | Germany
| Date: | 01.04.2017 | Ghana
| Executing Agency |  | Greece
| Name: | RBS Foundation India | Grenada
| Email: | abhinav.sen@rbs.com | Guatemala
| Date: | 01.04.2017 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Chief Wildlife Warden and Princical Chief Conservator of Forests - Wildlife, Madhya Pradesh | Guyana
| Email: | pccfwl@mp.gov.in | Haiti
| Date: | 01.04.2017 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31.03.2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? 1 USD = INR 65
Estimated cumulative total disbursement as of [09.05.2018] |  | 651012
Add any comments on AF Grant Funds. (word limit=200) |  | Amount is received in 2 installments 1st installment - 22.05.2017 - USD 170,763 2nd installment - 18.04.2018 - USD 480,249
INVESTMENT INCOME |  | USD 739 ( as on 31.03.2018)
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT (USD)
| Component 1: Integrated socio - economic and ecological assessment and planning | 1.1 Socio economic baseline report with village level detailed analysis in the project villages | 14502.4
|  | 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. | 4119.6154
| Component 2: Community mobilization for building adaptive capacities | 2.1 Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster / district / landscape level on issues of conservation, climate change, gender and development. | 28789.0462
|  | 2.2 Participatory Impact monitoring | 0
| Component 3: Integrated approach for ecosystem resilience and sustainable livelihoods as a means for adaptation | 3.1 Adoption of climate resilient agricultural practices by 5,000 households | 107975.1846
|  | 3.2 Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households. | 11093.4
|  | 3.3 Enhanced vocational skills in 500 individuals. | 48.4308
|  | 3.4 Adoption of energy efficient mechanisms by households to reduce fuel wood dependency and drudgery amongst women. | 3425.2308
|  | 4.1 Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC | 5066.4769
|  | 4.2 Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. | 0
|  | 4.3 Local and National Level Campaigns/Workshops for dissemination | 0
|  | 5. Management costs | 33995.0154
0
|  | TOTAL | 209014.8
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date
|  | 1.1 Socio economic baseline report with village level detailed analysis in the project villages | 9230.7692 | 31.03.2019
|  | 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. | 5230.7692 | 31.03.2019
|  | 2.1 Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster / district / landscape level on issues of conservation, climate change, gender and development. | 100000 | 31.03.2019
|  | 2.2 Participatory Impact monitoring | 19384.6154 | 31.03.2019
|  | 3.1 Adoption of climate resilient agricultural practices by 5,000 households | 384615.3846 | 31.03.2019
|  | 3.2 Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households. | 76923.0769 | 31.03.2019
|  | 3.3 Enhanced vocational skills in 500 individuals. | 61538.4615 | 31.03.2019
|  | 3.4 Adoption of energy efficient mechanisms by households to reduce fuel wood dependency and drudgery amongst women. | 46153.8462 | 31.03.2019
|  | 4.1 Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC | 1076.9231 | 31.03.2019
|  | 4.2 Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. | 46153.8462 | 31.03.2019
|  | 4.3 Local and National Level Campaigns/Workshops for dissemination | 30769.2308 | 31.03.2019
|  | TOTAL | 781076.9231 | 31.03.2019
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk | Category of Risk
Failure in Community Mobilization to undertake the activities of building adaptive capacities of the community residing in the landscape. | Community has been sensitized and mobilization to undertake project activities is ongoing. | Local resource persons have been selected as community mobilizers. Regular awareness building workshops, training sessions and exposure visits are being conducted for the community. | Medium
All stakeholders may not take part in the process as the individuals' capacity and commitment vary. There can be resistance from some stakeholders in adopting the suggested measures on account of perceptional differences. | All stakeholders are working together (including community, forest department, government line department and local CSOs) | The project has adopted a consultative and inclusive approach since inception. Regular interactions with the stakeholders is maintained through verbal and written updates about the project. The team is working in consonance with the roles and responsibilities of all the stakeholders. Additionally, the Village development plans and wealth ranking process which was done in participatory mode has ensured that the most vulnerable are benefitted of the project interventions. | Low
Slow progress in implementation of the interventions due to unfavourable climatic factors and location accessibility issues | Watershed structures were damaged due to high intensity rainfall in the project area. | Redesigning of structures is requierd in such landscapes where ridge area is largely covered by forest and therefore watershed treatment starts from mid-ridge. The project team has identified this as a operational problem in similar landscapes and is undertaking a research study on how mid-ridge structures should be designed to minimize damage. Excavation of a Staggered Contour Trench (for e.g., 2 Mtr X 2 Mtr X 2 Mtr dimensions) on the upstream side of the mid-ridge is one option. | Medium
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project. | Late onset of monsoon, dry spells during monsoon period, less rainfall during crop growth period has caused loss in agriculture production systems. | Demonstrations of improved rainfed agriculture practices is being provided to the farmers through experienced professionals. Adpative Soil and water management practices, Nutrient management and Pest management are being promoted. A shift from traditional farming practices is seen and the community is responding well to the measures promoted. | Medium
Limited capacity/expertise of partner organisations to deliver project outputs. | Partner organizations are capacitated to deliver project outcomes successfully. | Cross learning sessions are being organized regularly between the project implementing partners leading to transfer of knowledge and capacity building of the project staff. | High
Failure to create ownership of the project at the local level. | Project is accepted by the community and stakeholders at the local level. | An inclusive approach has been adopted since project inception with focus on developing robust community based institutions in each of the project villages. | Medium
Financial mismanagement | Financial practices are transparent, consistent and backed by evidence. | Strong systems of financial reporting have been developed in the project. | High
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Category >50%
State elections and General elections. | State elections in Madhya pradesh in November 18 and General elections in India in 2019 might delay project activities. | Activity Execution Plan was drawn keeping in view the likely Election schedule and also the impact the elections might have on the stakeholders and the community. | Medium
Risk Category up to 50%
Changes in forest department staff | Frequent changes in the forest officials in the project area leading to delays | Regular meeting with forest department at the state level and at the district level is being undertaken. Monthly updates are being provided to the forest department to ensure continuity of information. | Medium
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1 Socio economic baseline report with village level detailed analysis in the project villages. |  | Completed Socio Economic Assessment of the Project villages. |  | Socio-economic profile of project villages through Foccused group discussion has been created. Wealth Ranking and Village Development plans have been completed. The project team is fine tuning the report by undertaking a Household - Economic Analysis which will be incorporated in the Socio - Economic analysis/ Basline report. This is expected to be completed by June 2018. Final Baseline reports will be printed and circulated post findings from Households Economic Analysis are captured. | S
| Output 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. |  | GIS mapping and analysis for KPC landscape has been completed. Landsat imagery is captured and initial analysis of the same is completed. |  | Landsat imagery using GIS has been created for the landscape and initial analysis of the same is completed. The findings endorse that assumptions made in the proposal like degradation/ reduction of edge density of fringe forests. Annual change assesment to measure changes to the village woodlots/surrounding forests is ongoing and will be incorporated in the Final Baseline report. Comprehensive set of maps that outline the natural resources in the 56 project villages at baseline have been created too. | S
| Output 2.1 Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster /district / landscap level on issues of conservation, climate change, gender and development. |  | Creation of new/ Strengthening of existing village level/ gender centric institutions is completed. Participation of 70% households is achieved in institutions in all the project villages. A dialogue is initiated with the communty that promotes conservation and protection of natural resources. |  | Village institutions have been created in all the project villages, however the level of mobilization and participation rates are lacking in 6-7 villages. Gender neutrality in institutions is also not achieved, but the project team is confident that both indicators will improve during Y 2 of implementation. Self Help Groups (SHGs) mobilization also took time to catch momentum and is now being undertaken in partnership with National Rural Livelihoods Mission(NRLM). Further, through exposure visits, meetings and classroom trainings the community has been constantly exposed to issues related to resource extraction, conservation and protection. Process of creating Byelaws around resource extraction/ protection, Net planning for development of common and private lands have been initiated in 20-22 village institutions. | S
| Output 2.2 Participatory impact monitoring. |  | Not in plan for Y1 |  | NA | S
| Output 3.1: Adoption of climate resilient agricultural practices by 5,000 households. |  | 1,000 farmers are sensitised and mobilzed for action on improved and climate resilient agricultural practices. Water-related entry point activities are completed in all the project villages and Land Development/ Restoration activities are completed on 540 hectares. |  | The project has reached out to over 800 farmers in YI through demonstrations, exposure visits, classroom trainings and input support. The farmers are trained and handholding support given to adapt improved practices like SRI, Organic farming, Indigenous seed/ improved seed, bio-pesticides etc. Four(4) Agromet stations out of the planned 5 have been installed and weather advisories are being issued to the farmers regularly. Promotion of micro irrigation mechanisms will be initiated in Y2. Beneficiary selection is in progress. Entry point activities have been completed in all the project villages. While the initial plan was to undertake EPAs which are water centric, based on community demand as ascertained during the initial meetings, there have been modifications accordingly. Land restoration activities through eradication of invasive species / Net planning for development of commons and private lands has been initiated and will gain momemtum in Year 2. The community is slowly opening up and accepting the interventions through exposure visits, classroom trainings and meetings. | HS
| Output 3.2 Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households. |  | 400 alternative enterprises are established and 100 youths are imparted skill trainings. |  | Beneficiary selection has been completed in 50% villages. 70 alternative enterprises have been initiated. 3 youths have been imparted skill training and linked with Larsen and Tubro in Hyderabad. This will gain momentum in Y2. | S
| Output 3.3 Enhanced vocational skills in 500 individuals. |  | 100 youths are provided with skill development training. |  | Benficiary selection is ongoing, this will intensify in Y2 and Y3. 3 youths have been trained. | MS
| Output 3.4 Adoption of energy efficient mechanisms by 1,000 households to reduce fuel wood dependency and drudgery amongst women. |  | 120 household level efficient cook stoves and solar charging stations, 20 commercial level cook stoves. |  | 20 Household level cook stoves, 7 commercial level cook stoves, and 126 solar lanterns have been provided to the beneficiaries. Project team is being cautious on distribution of cook stoves, due to increasing outreach of the Government Scheme - Ujjawla (which provides for subsidised LPG cylinder). | S
| Output 4.1 Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC. |  | Finalization of the Knowledge Management Framework. Implementation of KM. |  | Consultative workshops have been held for finalization of the KM framework. Initiation of KM framework has been initiated and work as to development of an audio-visual, coffee table book is in progress. The delays are primarily due to explorations of vendors/ partners who will support implementation of the KM component. This is expected to be on track in Y2. | MS
| Output 4.2 Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. |  | Development of knowledge material - including one audio visual for the KPC. |  | Vendor has been identified and work has been initiated on the audio-visual. To be completed in Y2 | S
| Output 4.3 Local and National Level Campaigns/Workshops for dissemination |  | Not in plan for Y1 |  | NA | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Abhinav Sen
| Email: | abhinav.sen@rbs.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
1) The project team has adopted a cautious apprpoach towards community mobilization/ institution building. While this has resulted in a reduced spent of especially in Component 3, it has created a solid foundation to intensify project activities in the coming years. There are positive trend sees in interventions of Land restoration - Lantana Eradication for eg. has created multiple benefits like - reduced man-animal conflicts; improved regeneration, created grazing areas, reduced dependence of livestock on forests. Community is gradually opening up tpo project interventions on Protection/Conservation of commons and surrounding forests. There are positive trends noticed in adoption of improved farming practices - over 800 farmers have completely moved to cultivating method - SRI, using improved seeds and bio-pesticides. 2) The critical risk that we identified during the project development stage was non-representation of marginalized sections in the village planning/ decision making. While the project team is constantly working to mitigate these risks, it will take a much longer time to eliminate age-old social barriers in the landscape. However, Village development plans and Wealth ranking exervise have provided us visibility to prioritize household level interventions to marginalized sections. This is expected to improve participation in village level institutions too. 3) Mid term review is planned for Y2 end 4)The project delivery has been satisfactory on most of the components. The project activities will gain momentum in Y2 and are expected to catch up on the defined targets and intensity by March 19. On two parameters, Vocational skills promotion among youth and Knowledge Management component the rating was Marginally satisfactory, due to delays caused in identification of youth, selection of vendors/partners to support delivery of the component. This is expected to be resolved too by end of Mar 19.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Socio Economic Assessment of 56 Project Villages |  | Completed Socio Economic Assessment of the Project villages and Ecological mapping and analysis of the KPC landscape through GIS |  | Socio-economic profile of project villages through Foccused group discussion has been created. Wealth Ranking and Village Development plans have been completed. The project team is fine tuning the report by undertaking a Household - Economic Analysis which will be incorporated in the Socio - Economic analysis/ Basline report. This is expected to be completed by June 2018. Final Baseline reports will be printed and circulated post findings from Households Economic Analysis are captured. | S
| Ecological mapping and analysis of KPC landscape |  | GIS mapping and analysis for KPC landscape has been completed. Landsat imagery is captured and initial analysis of the same is completed |  | Landsat imagery using GIS has been created for the landscape and initial analysis of the same is completed. The findings endorse that assumptions made in the proposal like degradation/ reduction of edge density of fringe forests. Annual change assesment to measure changes to the village woodlots/surrounding forests is ongoing and will be incorporated in the Final Baseline report. Comprehensive set of maps that outline the natural resources in the 56 project villages at baseline have been created too. | S
| Community mobilisation and Institution Building in 56 villages |  | Creation of new/ Strengthening of existing village level/ gender centric institutions is completed. Participation of 70% households is achieved in institutions in all the project villages. A dialogue is initiated with the communty that promotes conservation and protection of natural resources |  | Village institutions have been created in all the project villages, however the level of mobilization and participation rates are lacking in 6-7 villages. Gender neutrality in institutions is also not achieved, but the project team is confident that both indicators will improve during Y 2 of implementation. Self Help Groups (SHGs) mobilization also took time to catch momentum and is now being undertaken in partnership with National Rural Livelihoods Mission(NRLM). Further, through exposure visits, meetings and classroom trainings the community has been constantly exposed to issues related to resource extraction, conservation and protection. Process of creating Byelaws around resource extraction/ protection, Net planning for development of common and private lands have been initiated in 20-22 village institutions. | S
| Entry point and Land Development activities |  | Water-related entry point activities are completed in all the project villages and Land Development/ Restoration activities are completed on 540 hectares. |  | Entry point activities have been completed in all the project villages. While the initial plan was to undertake EPAs which are water centric, due to community demands ascertained during initial meetings, these have been modified in a few villages. Land restoration activities through eradication of invasive species / Net planning for development of commons and private lands has been initiated and will gain momemtum in Year 2. The community is slowly opening up to its benefits through exposure visits, classroom trainings and meetings. | S
| Climate Resilient Agriculture practices |  | 1,000 farmers are mobilzed on improved/ climate resilient agricultural practices. |  | The project has reached out to over 800 farmers in YI through demonstrations, exposure visits, classroom trainings and input support. The farmers are trained and handholding support given to adapt improved practices like SRI, Organic farming, Indigenous seed/ improved seed, bio-pesticides etc. Four(4) Agromet stations out of the planned 5 have been installed and weather advisories are being issued to the farmers regularly. Promotion of micro irrigation mechanisms will be initiated in Y2. Beneficiary selection is in progress. | S
| Alternative livelihoods and skill development |  | 400 alternative enterprises are established and 100 youths are imparted skill trainings |  | Beneficiary selection has been completed in 50% villages. 70 alternative enterprises have been initiated. 3 youths have been imparted skill training and linked with Larsen and Tubro in Hyderabad. This will gain momentum in Y2. | S
| Energy Efficient Practices |  | 120 household level efficient cook stoves and solar charging stations, 20 commercial level cook stoves |  | 20 Household level cook stoves, 7 commercial level cook stoves, and 126 solar lanterns have been provided to the beneficiaries. Project team is being cautious on distribution of cook stoves, due to increasing outreach of the Government Scheme - Ujjawla (which provides for subsidised LPG cylinder). | S
| Knowledge Management |  | Finalization of the Knowledge Management Framework. Implementaion of KM |  | Consultative workshops have been held for finalization of the KM framework. Initiation of KM framework has been initiated and work as to development of an audio-visual, coffee table book is in progress. The delays are primarily due to explorations of vendors/ partners who will support implementation of the KM component. This is expected to be on track in Y2. | MS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | T.Prakash
| Email: | t.prakash@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other |  |  | NIL
NIL
NIL
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | 1) Out of the EE's planned expenditure of Rs.4.34 crore during 2017-18, the EE has expended Rs.1.35 crore as on 31.3.2018. However, The amount released as on 31.3.2018 was Rs.1.10 crore against Rs.4.34 crore released to NABARD by AFD. Offices have been set up in 3 districts viz. Baihar (Balaghat), Kurai (Seoni) and Mocha (Mandla).Collection of primary data, baseline report preparation, GIS mapping & analysis is complete in respect of 56 villages in 3 districts. Community awareness, sensitisation and mobilisation is complete in 42 villagaes. Formation of community institutions is completed in 53 of the 56 villages. Gender focussed activities are ongoing and has benefitted 898 beneficiaries. Demonstration of adapative agriculture crops and paractices through farmer field school, supply agrl inputs & implements and promotion of organic farming. Application of efficient irrigation systems/ mechanisms and improvement of watershed, installation of agro-met stations and dissemination of weather specific agricultural practices and other activities. 2)No critical risks have been reported by the EE. 3) Mid Term Review (MTR) was undertaken as on 31.12.2018. Relese of II instalment of Rs.3.12 crore on 18.4.2018 was based on satisfactory mid-term review. 4) Component I, 2 and 3 are rated as Satisfactory. However, component 4 (Knowledge Management) is rated as MS.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Build adaptive capacities of communities, livelihoods and ecosystem resilience in the KPC | Number of households covered under village level plans for conservational and developmental activities. | Village level/ special purpose institutions exist in all villages but are defunct and ineffective | Village institutions have been revived in the project villages. Around 2,500 households have been covered. A dialogue on conservation and development activities aligned to the project components have been initiated. . This will intensify in the coming months with incresed household interventions. | 5,000 households
| Number of households have access to diversified and improved livelihoods that increases resilience to climate change and reduce forest dependency | Communities in project villages are primarily dependent on rainfed agriculture, forest resources, and migration for livelihoods. | The project has provided 1,068 households access to livelihoods which have resulted in improved resource utilization and climate resilience. While the project has met its targets in numbers, the intensity of benefits is not high, this will improve in the subsequent years of project implementation | 5,000 households
| Number of hectares of forest under community conservation (atleast 3,000 ha); Number of hectares of area treated with watershed activities (atleast 1,800 ha) | Common resources, including village woodlots are degraded due to no governance. Private lands (especially uplands) are left idle, and encroached by invasive flora | The project team has initiated a dialogue with the community to improve governance of commons. The institutions are being capacitated to develop byelaws and control mechanisms, to ensure protection measures adopted have high effectivess. Community conservation of village woodlots has been initiated on around 240 hectares. Private and common lands around 251 hectares where Lantana encroachment is seen, have being cleared, resulting in multiple benefits including - improved regenration, reduced man-animal conflicts, higher income amongst others. Additionally, watershed development activities have been undertaken on 100 hectares. Total 400 hectares have been improved. | 4,800 hectares
Outcome 1: Improved understanding of prevalent dynamics and changes in area of interventions | Number of village level meetings conducted | Meetings conducted were scattered and had little effectiveness in providing solution to inter/ intra community conflicts. There was poor representation of the marginalized communities too. | Monthly meetings are being conducted in project villages. Meeting agenda is foccusing on ongoing developmental and conservational issues. Presently, paraworkers are ensuring meetings are conducted regularly, but will slowly start putting the onus on village leaders for the same. Around 600 meetings have been done during Y I. | Monthly meetings are conducted independently.
| % of village households represented in meetings | Meetings conducted were scattered and had little effectiveness in providing solution to inter/ intra community conflicts. There was poor representation of the marginalized communities too. | At the project level the average representation of households is around 25-30%. In some villages its more than 50% whereas in some its as low as 15%. The project team is confident that - with increase in intensity of the project interventions, at the village and households level, this will rise during Y 2. | 70%
| Number of men and women participants | Participation in village meetings limited to few village leaders, with no or handful women participants | Mobilization of 2,500 men and 1,500 women is ongoing under the project. Participations levels and involvement at institutions have also increased. | 70%
| Number of village development plans prepared | 0 | 56 village development plans have been prepared. Implementation base of project activities has been created and execution will intensify in Y II. | 56 Plans
| Number of SHGs active with credit linkage | 0 | 53 SHGs have been formed/ revived in the project villages. The groups have started making regular savings, which is a prerequisite for credit linkage. | 150 SHGs
Outcome 2: Enhanced capability of the community to take collective action, practice adaptive livelihoods and conservation | Number of robust community institutions in the project villages. | Institutions exist but are defunct, ineffective and have low participation levels. Marginalized populations are excluded. | Institutions have been formed in all the 56 project villages, the project team is working on sensitization/ mobilization of members through regular interactions, exposure visits and classroom trainings. | 56 village level institutions
| Regular meetings, trainings and exposure visits attended by institution members. | Irregular meetings were held. Institutions had no access to capacity building trainings. | Regular monthly meetings of Village Development committees are ongoing. Besides regular interactions with project teams, 14 exposure visits and 102 classroom trainings have been completed. | Monthly meetings in all the 56 villages and requisite exposure visitsand trainings.
| % of women participants in village meetings/ trainings | The minimum desired rate of women participation (30%), in village institutions is not in place. | Through Gender foccused exposure visits and trainings of the VDCs, the project team is working towards ensuring higher participation of women. The present rate is around 20%. | 30%
| % of participants involved in the decision making process | 0 | 100% of participating households are involved in the decision making process. A democratic approach has been adopted in finalizing the developmental plans and undertaking wealth ranking. Beneficiairy selection is also being done by the VDCs collectively. | 100%
| Amount of convergence achieved with existing government schemes | 0 | No formal convergence has been done. | 0
| Forest Area brought under community management/ protection. | 0 | 240 hectares of village woodlots have been brought under community conservation. VDCs are in the process of creating bye-laws for additional 2,500 hectares of village woodlot protection and conservation. | 3,000 hectares
| Number of village conflicts addressed by the institution | 0 | Multiple conflicts are noticed as institutions have started talking openly about resource sharing and optimization. One such conflict on grazing has been resolved independently by the village institition. | NA
Outcome 3: Improved adaptive capacity of the community and landscape | % of households having capacity, access to inputs and mechanisms to implement sustainable and adaptive livelihood techniques. | 0 | As on 31.03.18 around 2,500 households have been provided with capacity building trainings on improved/ climate resilient livelihoods. Around 500 households have received direct support on inputs, alternative livelihoods and skill development. This is expected to intensify in Y II. | 70% (around 5,000 households)
| % increase in gross income of households | 0 | This information is not available at this time. A household economic analysis is ongoing and will provide information to report under MTR. | 15-20%
| % increase in cropping intensity | 0 | With improved access to water and improved agricultural systems, cropping intensity is expected to increase in the coming years. Precise information is not available at this time. Will be reported in MTR. | 150%
| % decrease in women drudgery | 0 | Issues related to gender equity has been the point of discussion in the village meetings. In 15 villages, women druggery relating to water has come down due to low cost water harvesting structure. Precise information is not available at this time. Will be reported in MTR. | 25% in atleast 1000 households
| % reduction in forest resource dependence of beneficiary households | 0 | Conservative estimates based on the biomass assesment of some sites, show regeneration of 0.7 tonnes/Ha of grasses due to restoration work. Total 240 hectares have been restored, thus an additional biomass of 175 tonnes is created. Additionally, efficient cooking stoves have been provided to 20 households and 7 commercial enterprises which are expected to reduce fuel wood consumption by 7-8 tonnes as on 31.03. 2018. Precise information to be provided during MTR. | (by 1,500 tons – fuel wood + 3,000 tons fodder)
Outcome 4: Improved understanding on threats and climate change impacts on the landscape and enhanced involvement of stakeholders | % of households having improved understanding on the importance of having robust and gender neutral CBOs as means to climate resilience. | 0 | Till date, around 2,500 households have been sensitized. Implementation of Knowledge Management Framework will be initiated in YII and is expected to deepen existing/ create understanding on aspects of CCA | 75%
| % of household having improved understanding on the importance of conserving and utilizing the forest resources in a sustainable manner in the context of climate change. | 0 | Till date, around 2,500 households have been sensitized. Implementation of Knowledge Management Framework will be initiated in YII and is expected to deepen existing/ create understanding on aspects of CCA | 75%
| % of households having improved knowledge/ decision making ability on climate resilient agricultural and other livelihood practices | 0 | Till date, around 2,500 households have been sensitized. Implementation of Knowledge Management Framework will be initiated in YII and is expected to deepen existing/ create understanding on aspects of CCA | 50%
| Adaptive strategies through project learning articulated, developed and communicated for replication and policy changes | 0 | Case studies are being prepared. 2 topics identified are - Eradication of Lantana and Indigenous seeds. Will be completed and cicrulated in Y II | Atleast 4
| Number of case studies/ research studies published in peer reviewed journals | 0 | Case studies are being prepared. 2 topics identified are - Eradication of Lantana and Indigenous seeds. Will be completed and cicrulated in Y II | Atleast 4
| Number of print/ audio/video media coverage generated | 0 | One Coffee Table Book and an audio-visual on the area profile of the Kanha Pench Corridor is work in progress. | Atleast 5

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Mobilizing the community took more time than expected. While there were delays in project implementation, the project team felt it was prudent to be patient and gradually intensify interventions.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | In some of the project villages inter and intra community conflict delayed the organisation of institutions. Regular interactions, trainings sessions and exposure visits of village leaders etc., are various measures taken to reduce these conflicts. There are delays in finalizing the Knowledge Management framework, as it was undertaken in a consultative manner - ensuring participation of key stakeholders was a challenge.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | While there are no changes made to the project design, the project team has responded proactively to some local challenges. For e.g., The community in two project villages have demanded that instead of water - centric entry point activities, they want community solar lighting to mitigate man-animal conflicts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations are inherent to the project design and will be there in all reporting periods. During the first year of implementation some inclusions were - Livelihood planning of women headed households, ensuring women participation in land developmental activities - lantana eradication, watershed development; Inclusion of women has ensured that the project benefits reach out to the most vulnerable section in the village community. It also ensures sustainability of enterprises promoted, as women are noticed to be less inclined to go on migration.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | National Bank of Agriculture and Rural Development
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 53512 | 21220 | 32292 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 25% | 25% | 25% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 |  | 1: Ineffective | Total | 56 |  | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 100% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Other | 1: No capacity | Total | 56 | Other | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Other
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 56 | 30% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability |  | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
| Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | 0 | Multi-community |  | Other | 56 | Multi-community |  | Other | 56 | Multi-community |  | Other
|  | 0 | Community |  | Other | 150 | Community |  | Other | 53 | Community |  | Other
|  | 0 | National |  | Other | 25 | National |  | Other | 0 | National |  | Other
| Indicator 4.1.2 Physical assets | 0 | Community |  | Agriculture | 5 | Community |  | Agriculture | 4 | Community |  | Agriculture
|  | 0 | Community |  | Other | 700 | Community |  | Other | 152 | Community |  | Other
|  | 0 | Community |  | Water management | 560 | Community |  | Water management | 0 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha protected | 1: Ineffective | Forests | 3000 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | ha protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 1800 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5000 | other |  | 500 | 5000 | other |  | 600
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on K78: senabh: village institutions, village development plans, wealth ranking
Note on K79: senabh: Self Help groups
Note on K80: senabh: Knowledge management material
Note on K81: senabh: Agro met stations
Note on K82: senabh: Energy efficient practices - Bio gas + Efficient devices + Solar lanterns
Note on K83: senabh: Micro - drip irrigation

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.