## Schedule
Proposed ICP 2011 Timetable
|  | 2009 |  |  |  | 2010 | [18 empty] | 2011 | [18 empty] | 2012 | [18 empty] | 2013
|  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Management, Fund Raising, and Advocacy
2 | Planning and monitoring progress (with RCs)
3 | Building partnerships (external and internal programs, international and regional organizations, etc.) | bar: 2009 Sep to 2010 Jan
4 | Mobilizing experts in various fields/ Maintaining a DB of experts | 2010 Aug: 1; 2010 Sep: 6; 2010 Nov: 0; 2010 Dec: 16; 2010 Jan: 3
5 | Fund raising activities
6 | Outreach and advocacy to policy-makers and users (website, helpdesk, newsletter, data access, etc.)
7 | Meetings
8 | Executive Board | 2010 Aug: 1; 2010 Sep: 8; 2010 Oct: 01; 2010 Nov: 1; 2010 Dec: 1801; 2010 Jan: 6
9 | Regional Coordinators | 2010 Aug: 1; 2010 Sep: 8; 2010 Oct: 02; 2010 Nov: 2; 2010 Dec: 1802; 2010 Jan: 6
10 | TAG | 2010 Aug: 1; 2010 Sep: 8; 2010 Oct: 03; 2010 Nov: 3; 2010 Dec: 1803; 2010 Jan: 6
11 | Users Conference | 2010 Aug: 1; 2010 Sep: 8; 2010 Oct: 04; 2010 Nov: 4; 2010 Dec: 1804; 2010 Jan: 6
12 | Methodology
13 | National Acounts | 2010 Aug: 2; 2010 Sep: 1; 2010 Nov: 0; 2010 Dec: 21; 2010 Jan: 3; 2011 Aug: 2; 2011 Sep: 1; 2011 Nov: 0; 2011 Dec: 21; 2011 Jan: 3; 2012 Aug: 2; 2012 Sep: 1; 2012 Nov: 0; 2012 Dec: 21; 2012 Jan: 3
14 | Prices | bar: 2009 Sep to 2010 Jun
15 | Price Survey Preparations
16 | Product Lists (Core, Regional, and Sub-Regional) | bar: 2009 Sep to 2010 Aug
17 | Survey design | bar: 2010 Jan to 2010 Aug
18 | Price survey data collection forms | bar: 2010 Jul to 2010 Aug
19 | Price Data Collection, Validation and Transmission
20 | Pilot Data Collection | 2010 Aug: 2; 2010 Sep: 4; 2010 Oct: 05; 2010 Nov: 5; 2010 Dec: 2405; 2010 Jan: 6; 2011 Aug: 2; 2011 Sep: 4; 2011 Oct: 05; 2011 Nov: 5; 2011 Dec: 2405; 2011 Jan: 6; 2012 Aug: 2; 2012 Sep: 4; 2012 Oct: 05; 2012 Nov: 5; 2012 Dec: 2405; 2012 Jan: 6
21 | Lesson learning from pilot collection / Modifying survey, if needed | 2010 Aug: 3; 2010 Sep: 3; 2010 Nov: 0; 2010 Dec: 33; 2010 Jan: 3; 2011 Aug: 3; 2011 Sep: 3; 2011 Nov: 0; 2011 Dec: 33; 2011 Jan: 3; 2012 Aug: 3; 2012 Sep: 3; 2012 Nov: 0; 2012 Dec: 33; 2012 Jan: 3
22 | First quarter data collection and validation | 2010 Aug: 3; 2010 Sep: 3; 2010 Oct: 01; 2010 Nov: 1; 2010 Dec: 3301; 2010 Jan: 6; 2011 Aug: 3; 2011 Sep: 3; 2011 Oct: 01; 2011 Nov: 1; 2011 Dec: 3301; 2011 Jan: 6; 2012 Aug: 3; 2012 Sep: 3; 2012 Oct: 01; 2012 Nov: 1; 2012 Dec: 3301; 2012 Jan: 6
23 | Second quarter data collection and validation | 2010 Aug: 3; 2010 Sep: 3; 2010 Oct: 02; 2010 Nov: 2; 2010 Dec: 3302; 2010 Jan: 6; 2011 Aug: 3; 2011 Sep: 3; 2011 Oct: 02; 2011 Nov: 2; 2011 Dec: 3302; 2011 Jan: 6; 2012 Aug: 3; 2012 Sep: 3; 2012 Oct: 02; 2012 Nov: 2; 2012 Dec: 3302; 2012 Jan: 6
24 | Third quarter data collection and validation | 2010 Aug: 3; 2010 Sep: 3; 2010 Oct: 03; 2010 Nov: 3; 2010 Dec: 3303; 2010 Jan: 6; 2011 Aug: 3; 2011 Sep: 3; 2011 Oct: 03; 2011 Nov: 3; 2011 Dec: 3303; 2011 Jan: 6; 2012 Aug: 3; 2012 Sep: 3; 2012 Oct: 03; 2012 Nov: 3; 2012 Dec: 3303; 2012 Jan: 6
25 | Fourth quarter data collection and validation | 2010 Aug: 3; 2010 Sep: 4; 2010 Nov: 0; 2010 Dec: 34; 2010 Jan: 3; 2011 Aug: 3; 2011 Sep: 4; 2011 Nov: 0; 2011 Dec: 34; 2011 Jan: 3; 2012 Aug: 3; 2012 Sep: 4; 2012 Nov: 0; 2012 Dec: 34; 2012 Jan: 3
26 | National annual averages computation and validation | 2010 Aug: 3; 2010 Sep: 4; 2010 Nov: 0; 2010 Dec: 34; 2010 Jan: 3; 2011 Aug: 3; 2011 Sep: 4; 2011 Nov: 0; 2011 Dec: 34; 2011 Jan: 3; 2012 Aug: 3; 2012 Sep: 4; 2012 Nov: 0; 2012 Dec: 34; 2012 Jan: 3
27 | National Accounts Implementation for ICP
28 | Training, assessment of capacity-building needs, and assistance to countries | bar: 2010 Feb to 2011 Jun
29 | N.A. compilation and review and preparation of metadata for 2005-2011 | bar: 2010 Feb to 2013 Mar
30 | Major aggregates (revised data for 2006, 2007, 2008, 2009), preliminary data for 2010 | bar: 2011 Jul
31 | Values for all basic headings for 2006, 2007, 2008, 2009, 2010 (preliminary) | bar: 2011 Jul
32 | Assessment of problems and assistance to countries | bar: 2011 Aug to 2012 Jun
33 | Major aggregates for 2011 (preliminary data for 2011 for initial results for 2011, to be used for editing) | bar: 2012 Jul
34 | All basic headings for 2011 (best possible estimates) | bar: 2012 Jul
35 | Assessment of problems and further assistance to countries | bar: 2012 Aug
36 | Major aggregates for 2011 (any revisions since July 2012) – data for compiling preliminary ICP results | bar: 2012 Oct
37 | All basic headings for 2011 (any revisions since July 2012) – data for compiling preliminary ICP results | bar: 2012 Oct
38 | Data review workshop in each region to consider the full set of ICP results based on the semi-final national accounts data | bar: 2012 Dec
39 | Major aggregates for 2011 (any revisions since October 2012) – final data to be used in the published ICP results | bar: 2013 May
40 | All basic headings for 2011 (any revisions since October 2012) – final data to be used in the published ICP results | bar: 2013 May
41 | Capacity Building, Quality and Software
42 | Capacity Building (Training, E-learning, etc.) | 2010 Aug: 4; 2010 Sep: 1; 2010 Nov: 0; 2010 Dec: 41; 2010 Jan: 3; 2011 Aug: 4; 2011 Sep: 1; 2011 Nov: 0; 2011 Dec: 41; 2011 Jan: 3; 2012 Aug: 4; 2012 Sep: 1; 2012 Nov: 0; 2012 Dec: 41; 2012 Jan: 3
43 | ICP Book | bar: 2009 Oct to 2010 Jun
44 | Data Quality Framework (DQAF-ICP) and Checklist | bar: 2009 Sep to 2010 Dec; 2011 Jun; 2012 Sep; 2013 Jun; 2013 Dec
45 | Software development, deployment, and support | 2010 Aug: 5; 2010 Sep: 2; 2010 Nov: 0; 2010 Dec: 52; 2010 Jan: 3; 2011 Aug: 5; 2011 Sep: 2; 2011 Nov: 0; 2011 Dec: 52; 2011 Jan: 3; 2012 Aug: 5; 2012 Sep: 2; 2012 Nov: 0; 2012 Dec: 52; 2012 Jan: 3
46 | Preparation of regional and global results
47 | Regional results computation and validation | bar: 2012 Nov to 2013 Dec
48 | Release of final regional results | bar: 2013 Jun to 2013 Dec
49 | Global results computation and validation | bar: 2013 Jun to 2013 Dec
50 | 2011 ICP results released | bar: 2013 Dec