## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 09/26/2019-09/26/2020
| Project Title: | Strengthening land based adaptation capacity in communities adjacent to protected areas in Armenia
| Project Summary: | The objective of the project is to reduce the climate risk vulnerability of local communities living adjacent to the “Khosrov Forest” and “Dilijan” National Park by strengthening the adaptive capacity of the agricultural sector and reinforcing their institutional and planning capacity for climate change adaptation. The specific objectives of the project are: 1.Community based, climate smart agricultural practices implemented in degraded areas to reduce climate risks vulnerability of production systems and sustain protected areas. 2.Value chains for climate smart agriculture strengthened and climate smart technologies made accessible for vulnerable rural communities, including equally for women and men. 3.Awareness, planning, monitoring and decision-making capacity on climate smart agriculture production methods and land degradation neutrality in target communities.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | EPIU | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Armenia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dilijan, Margahovit, Fioletovo, Urtsadzor | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-03-15
IE-AFB Agreement Signature Date: |  | 2019-09-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-09-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
Terminal Evaluation Date:
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project performance report. External Audit report | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Rubik Shahazizyan | Dominican Republic
| Email: | info@cep.am | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Vardan Meliqyan, deputy minister of environmnet, head of project management board | Equatoral Guinea
| Email: | deputy-minister@mnp.am | Eritrea
| Date: | 2019 July | Estonia
| Implementing Entity |  | Ethiopia
| Name: | EPIU | Fiji
| Email: | info@cep.am | Finland
| Date: | 2019 July | France
| Executing Agency |  | Gambia
| Name: | Ministry of Environment, RoA | Georgia
| Email: | minenv@env.am | Germany
| Date: | 2019 July | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information PPR 1: cumulative from project start to [26.09.2020] |  |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 26.09.2020 |  | 84885 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  | Overall disbursement of funds were low due to several factors: COVID 19 pandemic. The development of design and estimate documents for the construction of livestock watering point and repairments of field trucks has been completed with a delay of 3 months, due to COVID. Due to COVID-19 and martial law the development of the community management and business plans, including for climate smart agricultural value chains and increasing adaption of natural and agricultural ecosystems did not finish, due to which, the tenders for the selection of organizations for the design and implementation of works envisaged by the 1st and 2nd components have not started. Due to COVID-19 in the component 3 "Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices the task " based on population needs and capacity studies, awareness-raising development program was separated and a company is selected to carry out the task. The works will be completed in December, after which the other activities envisaged by the Program will start. There were price changes(around 30%) in activities related to increasing of adaptation of natural and agricultural ecosystems. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  | 7330.3588 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
Component 1
| Output 1.1 | Irrigation water supply systems are rehabilitated increasing water use efficiency
| Output 1.2 | Water efficient drip irrigation systems are installed in selected community orchards;
| Output 1.3 | Existing field tracks to remote pastures degraded lands are rehabilitated;
| Output 1.4 | Sowing areas of perennial plants are created reducing rangeland degradation;
| Output 1.5 | Community pastures and hay meadows are rehabilitated and improved their adaptive capacity;
| Output 1.6 | Livestock watering points are constructed;
| Output 1.7 | Degraded slopes are rehabilitated by belt planting of perennial, drought resistant plants;
|  | Preparation of design estimated documents | 27760.2524
Component 2
| Output 2.1 | Implementation of Climate smart agriculture technologies
| Output 2.2 | Nonheated, lightweight greenhouses are constructed in priority community areas
| Output 2.3 | Solar dryers are installed in priority community areas
| Output 2.4 | Community management and business plans are formulated for climate smart agricultural value chains. | 17636.5931
Component 3
| Output 3.1 | Farmer field schools and extension services have been provided to share best practices of climate smart agriculture and LDN for the targeted communities;
| Output 3.2 | Best practices examples and training material on climate smart agriculture are formulated, disseminated and made accessible
| Output 3.3 | Community based adaptation planning is conducted for target communities;
| Output 3.4 | Strategies for sustaining climate smart and gender responsive agriculture and LDN in target areas have been formulated.
| Output 3.5: | A monitoring system for land based adaptation measures and land degradation neutrality has been established for the target communities;
|  | IE oversight cost | 29686.307
|  | Project Execution cost | 9801.5563
|  | TOTAL | 84884.7087 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1
| Output 1.1 | Irrigation water supply systems are rehabilitated increasing water use efficiency | 285041 | Septemer 2021
| Output 1.2 | Water efficient drip irrigation systems are installed in selected community orchards; | 74833 | Septemer 2021
| Output 1.3 | Existing field tracks to remote pastures degraded lands are rehabilitated; | 309315 | Septemer 2021
| Output 1.4 | Sowing areas of perennial plants are created reducing rangeland degradation; | 117600 | Septemer 2021
| Output 1.5 | Community pastures and hay meadows are rehabilitated and improved their adaptive capacity; | 262000 | Septemer 2021
| Output 1.6 | Livestock watering points are constructed; | 51313 | Septemer 2021
| Output 1.7 | Degraded slopes are rehabilitated by belt planting of perennial, drought resistant plants; | 26000 | Septemer 2021
|  | Preparation of design estimated documents | 50000 | Septemer 2021
| Component 2 |  |  | Septemer 2021
| Output 2.1 | Implementation of Climate smart agriculture technologies | 5000 | Septemer 2021
| Output 2.2 | Nonheated, lightweight greenhouses are constructed in priority community areas | 23600 | Septemer 2021
| Output 2.3 | Solar dryers are installed in priority community areas | 68667 | Septemer 2021
| Output 2.4 | Community management and business plans are formulated for climate smart agricultural value chains. | 41152 | Septemer 2021
| Component 3 |  |  | Septemer 2021
| Output 3.1 | Farmer field schools and extension services have been provided to share best practices of climate smart agriculture and LDN for the targeted communities; | 10000 | Septemer 2021
| Output 3.2 | Best practices examples and training material on climate smart agriculture are formulated, disseminated and made accessible | 32142 | Septemer 2021
| Output 3.3 | Community based adaptation planning is conducted for target communities; | 7000 | Septemer 2021
| Output 3.4 | Strategies for sustaining climate smart and gender responsive agriculture and LDN in target areas have been formulated. | 17000 | Septemer 2021
| Output 3.5: | A monitoring system for land based adaptation measures and land degradation neutrality has been established for the target communities; | 15500 | Septemer 2021
|  | IE oversight cost | 80046 | Septemer 2021
|  | Project Execution cost | 12845 | Septemer 2021
|  | Total | 1489054 | Septemer 2021
|  | TOTAL |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risks related with procurement of services and equipment. | Ongoing with very low likelihood of happening. | Changes were adopted in the procurement plan and due to more market analysis new costs of the services and equipment were identifed. After the changes all the tenders took place and the contracts were signed.
Not all necessary stakeholders may take part in the process with the capacity and commitment required (from the inception phase to completion) or might feel left out in the process. Afterwards, there can be resistance from some stakeholders in adopting the proposed measures. | Ongoing with very low likelihood of happening. | The project will build upon an active stakeholder enagement strategy and frequent consultation. To ensure the equal participation of women, youth, elderly and other potentially vulnerable groups, dedicated consultations and working groups with these groups will be organized to provide ample space for the consideration of th specifc needs of these stakeholder groups. - A grievance redress mechanism would support community members and stakeholders to submit any complaint.
Project outcomes, including properties such as, greenhouses, dryers, etc. are not well protected | Ongoing with very low likelihood of happening. | Legally binding agreements will be signed with the beneficiaries who will be provided with assets (greenhouse, drier, etc) in the framework of the project. The agreements will stipulate the responsibility of the beneficiaries to maintain the provided assets in working condition and if necessary cover all costs of repairs for maintaining them in working conditions.
Beneficiaries may feel left out at the implementation process and or have insufficient collaboration between implementing body and stakeholders; | Ongoing with very low likelihood of happening. | The project will be implemented in close consultation with different stakeholders and in collaboration with the affected communities. The roles and responsibilities would be clarified during an inception workshop whereas ownership building will contribute to better collaboration between all stakeholders.
Delays in project implementation including those related to delayed procurement | Ongoing with very low likelihood of happening. | During the inception phase the working plan of the project implementation will be updated. The progress towards the timely implementation of the project will be monitored by weekly meetings of the PIU staff. PIU has to follow RA public procurement procedures, where the minimum days for certain phases of procurement process are established. In order to minimize the risk of delays because of delayed procurement, the maximum deadlines were included the project timeframe. project activities are well prepared to be completed In proposed timeframe. Monitoring activities will ensure implementation targets are kept.
Delays in obtaining construction permits | N/A at the moment | The project will contract only reliable and experienced construction companies that will ensure accurate filling out of request forms and timely obtaining of permits.
Delays in the disbursement of funds. | Medium | Disbursment of funds for the first year has been low. Many external factors affected the overall implementation of the project. The project team had a call with AF secretariat and possible change in implementation schedule will be requested. EPIU will ensure that in second year of the project all the funds for the fist year will be disbursed accordingly and all the relavant activities will be carried out
Mismanagement of resources | This risk is no longer applicable/relevant to the project | This risk is no longer applicable/relevant to the project
Project beneficiaries are not well chosen | This risk is no longer applicable/relevant to the project | This risk is no longer applicable/relevant to the project
Government is not supportive throughout the implementation phase and for the sustainability of the project | This risk is no longer applicable/relevant to the project | This risk is no longer applicable/relevant to the project
Implementation capacity constraints with limited human resources in national and regional authorities to ensure a timely implementation and the sustainability of the project | This risk is no longer applicable/relevant to the project | This risk is no longer applicable/relevant to the project
Project beneficiaries are resistant to change and/or the new technologies applied are difficult to manage | N/A at the moment | During the implementation phase consultations of different stakeholders will ensure the ownership building for the project. -Project will ensure active participation of stakeholders -Awareness and knowledge raising activities will increase the capacity for managing the new technologies applied and will ensure that beneficiaries are not resistant towards adaptation activities.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 Pandemic | Ongoing | All the activitites had to be implemented according to the Emergency Situation rules declared on March 16th 2020.Under strict restrictions, the EPIU and Contractors worked remotely using all possible means of communication. After the restrictions were eased, the EPIU and Contractors worked in the Project communities to comply with the emergency rules. The contractor organizations have applied to EPIU with a request to extend the termination of the works contracts. Pursuant to the RA Law on Procurement, the EPIU has extended the term of contracts by 1 month
Martial Law- Military operations, War in the country | Ongoing | On the instructions of the EPIU, the affiliated organizations primarily carry out the activities related to the community heads and beneficiaries. The EPIU has recommended that Contractors work with family members of missing beneficiaries to obtain their prior consent to be involved in the Project. Contractor organizations cooperate intensively with the officials of the regional administrations in order to quickly solve the problems that have arisen. Due to the coronavirus and ongoing martial law/military operations, there are changes in the prices of goods, services and works in the country. After this EPIU market research is carried out by the project manager, coordinator and the monitoring specialist. In parallel a market study is also carried out by the organization that develops the management plans of the works implemented in the communities. After the market research, the EPIU will present the results, its proposals to the Foundation, and will organize discussions. After the end of the war and martial law, EPIU plans to announce tenders in a short period of time and to start activities both planned in first and second year. Furthermore, after consultations with the Adaptation Fund EPIU is willing to reuqest for project extension. More specific details on timeframe and schedule of activities will be shared with the fund when the decision is made about the request.
Price changes in activities related to increasing of adaptation of natural and agricultural ecosystems.: | Ongoing | A market research is carried out by the project manager, coordinator and the monitoring specialist. After the results of the research EPIU will organize a discussion with the fund related to the issue.
Delays in implementation time table and schedule of activities | Ongoing | After consultations with the Adaptation Fund EPIU is willing to reuqest for project extension. More specific details on timeframe and schedule of activities will be shared with the fund when the decision is made about the request.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
COVID-19 Pandemic: 1. The transport communication between the regions was stopped for 1.5 months in the republic. 2. Gatherings, seminars, meetings, work of schools, higher education institutions and other mass events were prohibited. 3. All public-private organizations mainly worked remotely. 4. Restrictions have been eased since May 4, 2020. Steps to reduce risks: 1. Under strict restrictions, the EPIU and Contractors worked remotely using all possible means of communication. 2. After the restrictions were eased, the EPIU and Contractors worked in the Project communities to comply with the emergency rules. 3. The contractor organizations have applied to EPIU with a request to extend the termination of the works contracts. 4. Pursuant to the RA Law on Procurement, the EPIU has extended the term of contracts by 1 month Martial law 1. Military operations. 2. General mobilization. 3. Mobilization of equipment and human resources. 4. Organizing volunteer detachments from the communities under the leadership of the community leaders. 5. Absence of some community leaders, council members and decision makers from the communities. 6. Absence of some beneficiaries from the communities. 7. Ban on imports of all kinds of goods from countries in the conflict with Armenia Steps to reduce risks: 1. On the instructions of the EPIU, the affiliated organizations primarily carry out the activities related to the community heads and beneficiaries. 2. The EPIU has recommended that Contractors work with family members of missing beneficiaries to obtain their prior consent to be involved in the Project. 3. Contractor organizations cooperate intensively with the officials of the regional administrations in order to quickly solve the problems that have arisen Price changes in activities related to increasing of adaptation of natural and agricultural ecosystems. 1. The tender for the implementation of natural-agricultural ecosystems improvement works in Urtsadzor community was not held due to high bid by the participants. A new competition has been announced, which did not take place due to the absence of participants. 2. Due to the coronavirus and ongoing martial law, there are changes in the prices of goods, services and works in the country. Steps to reduce risks: 1. A market research is carried out by the project manager, coordinator and the monitoring specialist. 2. In parallel a market study is also carried out by the organization that develops the management plans of the works implemented in the communities. 3. After the market research, the EPIU will present the results, its proposals to the Foundation, and will organize discussions. Overall risks and further steps for the nex reporting period 1.The development of design and estimate documents for the construction of livestock watering point and repairments of field trucks has been completed with a delay of 3 months, due to which the construction company will be selected in November. Construction will begin in March-April 2021 due to disability of working in winter conditions 2 Due to COVID-19 and martial law the development of the community management and business plans, including for climate smart agricultural value chains and increasing adaption of natural and agricultural ecosystems did not finish, Due to which, the tenders for the selection of organizations for the design and implementation of works envisaged by the 1st and 2nd components have not started. 3. Activities for rehabilitation of arable lands and Rehabilitation of community pastures and hay meadows did not start because the bids of the tender participants exceeded the budgeted amount by 35%. 4. Due to COVID-19 in the component 3 "Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices the task "Based on population needs and capacity studies, awareness-raising development program was separated and a company is selected to carry out the task. The works will be completed in December, after which the other activities envisaged by the Program will start. 5.After the end of the war and martial law, EPIU plans to announce tenders in a short period of time and to start activities both planned in first and second year. 6. Furthermore, after consultations with the Adaptation Fund EPIU is willing to reuqest for project extension. More specific details on timeframe and schedule of activities will be shared with the fund when the decision is made about the request.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 - Access and equity |  |  | Lack of equity in access to project resources and activities. | Management: The ESS and Gender specialist will monitor and implement measures and indicators identified in the ESMP. Avoidance: Measures provided in the ESMP is taken into consideration to ensure ES and Gender safeguarding is followed and risks and impacts remains low. | Monitoring reports. | Sharing the benefits of the project with stakeholders. The programme will make sure equal ditsribution of programme benefits. | From the inception of the project all the beneficiaires have been identified in order to provide access and equity for all project stakeholders. | N/A at this moment | N/A at this moment
3 – Marginalized and vulnerable Groups |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 – Human rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 – Core labour rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | Damage and/or degradation to natural habitats as a result of project activities. | Management: Environment Imapct Assessment; Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment | The likelihood that natural habitats may be affected is very low. | Natural habitats are under control of the Ministry of Environment and there will be no intervention or activities in those areas. | N/A at this moment | N/A at this moment
10 – Conservation of biological diversity |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 – Climate change |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 – Public health |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 – Physical and cultural heritage |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | There are no cases of unanticipated ESP risks.
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Regular monitoring and evaluation of implmentation of activities are carried out to ensure that all activities for implementation are compliant with the ESMP.
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements have been effective
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Implementing entity is also the executing entity for the project and all the arrangements are in place.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation arrangements have been effective
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
To date no grievances have been received.
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Reduce the climate risk vulnerability of local communities living adjacent to the “Khosrov Forest” and “Dilijan” National Parks by strengthening the adaptive capacity of the agricultural sector and reinforcing their institutional and planning capacity for climate change adaptation by implementing adaptation measures in selected communities | Objective | Percentage of women beneficiaries | 0 | 40% | Good
Value chains for climate smart agriculture are strengthened and climate smart technologies are accessible for vulnerable rural communities; | Outcome | Percentage of women beneficiaries benefitting from climate smart technologies | 0 | 50% | Good
Non-heated, lightweight greenhouses are constructed in priority community areas | Output | Percentage of beneficiaies with access to green houses, which are women | 0 | 70% | Good
Solar dryers are installed in priority community areas | Output | Percentage of beneficiaies with access to solar dryers, which are women | 0 | 80% | Good
Awareness, planning, monitoring and decision making capacity on climate smart agriculture production methods and LDN has increased in target communities; | Outcome | Percentage of beneficiaires benefitting from awareness raising and capacity building for climate smart agriculture and LDN, which are women | 0 | 40% | Good
Farmer field schools and extension services have been provided to share best practices of climate smart agriculture and LDN for the targeted communities; | Output | Percentage of beneficiaires aware of climate change impacts and appropriate responses to threats, which are women | 0 | 40% | Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity has made all necessary efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the household baseline incorporated sex disaggregated data and gender specific questions. 2 - Encouraging project partners/ executing entities to hold gender sensitive consultations and assessments, for example holding separate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men. 3 - Ensuring that the Inception Workshop and Implmentation related Workshops had participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during workplanning
Have the implementation arrangements at the IE been effective during the reporting period? |  | All the arrangments made from IE/EE have been effective. IE made sure to have all the arrangments in place during the start of the project, even at the design of the project. All the specialists involved in the implementation carry out all necessary arrangements such as: 1) track gender indicators in all activities; 2) aim for equal participation of women in project activities and activity leadership structures
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | -
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | -
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Not at this moment
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances relating to gender matters have been received in the reporting period. |  | No grievances relating to gender matters have been received in the reporting period.

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 |  | Component 1: Community based, climate smart agricultural practices in degraded areas and buffer zones |  | Preparation of design estimates for reconstruction of existing field trucks and construction for livestock watering points is completed. The tender for construction company is announced. The tender for rehabilitation for arable land, community pastures and hay medows was anounced, however the tender did not take place as there were no participants due to low budget. After the tender project manager, coordinator and monitoring specialist are conducting a research for the price evaluation. | MS
| Component 2 |  | Component 2 Strengthening value chains and climate smart technology transfer for vulnerable communities |  | The activity for community management and business plans, including for climate smart agricultarual value chains and increasing adaptation of natural and agricultural ecosystems is started. The draft management and business plans are ready, it will be finalised next month. After the finalisation of the plans all the activities related to component 1 and 2 will be carried out including both for first and second year. | MS
| Component 3 |  | Component 3 Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices |  | Outputs 3.1 and 3.2 are undergoing. It will be completed in coming two months and all the activities envisaged for the first and second year will be completed in the next reporting period. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Mr. Rubik Shahazizyan, Project Manager
| Name: | Mr. Vahagn Babayan, Project Coordinator
| Email: | info@cep.am
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall project progress is marginally satisfactory. Due to COVID-19 and martial law the development of the community management and business plans, including for climate smart agricultural value chains and increasing adaption of natural and agricultural ecosystems did not finish, Due to which, the tenders for the selection of organizations for the design and implementation of works envisaged by the 1st and 2nd components have not started. Activities for rehabilitation of arable lands and rehabilitation of community pastures and hay meadows did not start because the bids of the tender participants exceeded the budgeted amount by 35%. Due to COVID-19 in the component 3 "Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices the task "based on population needs and capacity studies, awareness-raising development program was separated and a company is selected to carry out the task. The works will be completed in December, after which the other activities envisaged by the Program will start. After the end of the war and martial law, EPIU plans to announce tenders in a short period of time and to start activities both planned in first and second year. Environmental , monitoring, gender and social specialist developed risk management plan for all activities which will be carried out in the project. All the risk management plans will be included in the ToR's for all tenders which will be anounced.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 |  | Component 1: Community based, climate smart agricultural practices in degraded areas and buffer zones |  | Preparation of design estimates for reconstruction of existing field trucks and construction for livestock watering points is completed. The tender for construction company is announced. The tender for rehabilitation for arable land, community pastures and hay medows was anounced, however the tender did not take place as there were no participants due to low budget. After the tender project manager, coordinator and monitoring specialist are conducting a research for the price evaluation. | MS
| Component 2 |  | Component 2 Strengthening value chains and climate smart technology transfer for vulnerable communities |  | The activity for community management and business plans, including for climate smart agricultarual value chains and increasing adaptation of natural and agricultural ecosystems is started. The draft management and business plans are ready, it will be finalised next month. After the finalisation of the plans all the activities related to component 1 and 2 will be carried out including both for first and second year. | MS
| Component 3 |  | Component 3 Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices |  | Outputs 3.1 and 3.2 are undergoing. It will be completed in coming two months and all the activities envisaged for the first and second year will be completed in the next reporting period. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Vardan Meliqyan, deputy minister of environmnet, head of project management board
| Email: | deputy-minister@mnp.am
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Community based, climate smart agricultural practices are implemented in degraded areas to reduce climate risks vulnerability of production systems and sustain protected areas; | •Total area of land rehabilitated and with increased adaptation capacity •Water loss in irrigation systems reduced •% of livestock benefitting adapted pasture management | x ha of land degraded in target communities Water losses in irrigation system (70%) 10% of livestock benefitting adapted pasture management |  | xx ha of land (xx%) rehabilitated Water losses in irrigation system (30%) 50% of livestock
Output 1.1: Irrigation water supply systems are rehabilitated increasing water use efficiency; | # m of irrigation system rehabilitated # solar water pumps installed | TBD |  | 120m rehabilitated 3 pumps installed
Output 1.2: Water efficient drip irrigation systems are installed in selected community orchards; | # ha orchards equipped with drip irrigation | TBD |  | 5.2ha drip irrigation installed
Output 1.3: Existing field tracks to remote pastures degraded lands are rehabilitated; | % Percentage of field tracks degraded / rehabilitated # km field tracks rehabilitated # culverts installed | 0% of field trucks are rehabilitated. 0 culverts installed |  | 30% of field tracks rehabilitated 39.5km rehabilitated 50 culverts installedn
1.4: Sowing areas of perennial plants are created reducing rangeland degradation; | # ha of perennial sowing areas of perennial plants are created | 0 ha is established |  | 10ha of perennial sowing area established
Output 1.5: Community pastures and hay meadows are rehabilitated and improved their adaptive capacity; | # ha hay meadows and arable lands rehabilitated # ha pastures rehabilitated | 0 ha hay pastures, meadows and arable lands rehabilitated |  | 1382 ha hay pastures, meadows and arable lands rehabilitated
Output 1.6 Livestock watering points are constructed; | # No of watering points constructed | No of watering points constructed |  | 15 watering points constructed
Output 1.7: Degraded slopes are rehabilitated by belt planting of perennial, drought resistant plants | # ha degraded slopes rehabilitated by the creation of agroforest | 0 ha |  | 3 ha of agroforestry planted
Outcome 2: Value chains for climate smart agriculture are strengthened and climate smart technologies are accessible for vulnerable rural communities; | • Total number of beneficiaries benefitting from climate smart technologies • Increased income, or avoided decrease in income • Percentage of women beneficiaries benefitting from climate smart technologies | TBD |  | 350 beneficiaries 50% of beneficiaries of climate smart technology are women
Output 2.1 Smart agricultural practices | X ha sowing of herbs, X ha anti-hail nets Constructed X ha Planting shrubs and mulching | 0 ha sowing of herbs 0ha of anti hail nets 0 ha planting shrubs |  | 0.5 ha sowing of herbs, 2.5 ha anti- hail nets Constructed 3.6 ha planting shrubs and mulching
Output 2.2: Non-heated, lightweight greenhouses are constructed in priority community areas | m2 of green houses constructed # no of beneficiaries with access to green houses % of beneficiaies with access to green houses, which are women | No greenhouses are constructed |  | 3000m2 of green houses constructed 100 beneficiaries 70 % of beneficiaies are women
Output 2.3: Solar dryers are installed in priority community areas | m2 of solar dryers constructed # no of beneficiaries with access to solar dryers % of beneficiaies with access to solar dryers, which are women | No soler dryers constructed |  | 150 m2 of solar dryers constructed 100 beneficiaies 80 % of are women
Output 2.4: Community management and business plans are formulated for climate smart agricultural value chains | # Community management and business plans are formulated for climate smart agricultural value chains | No business plans formulated | Community business plans are formulated | 2 business plans formulated
Outcome 3: Awareness, planning, monitoring and decision making capacity on climate smart agriculture production methods and LDN has increased in target communities; | No of beneficiaries benefitting from awareness raising and capacity building for climate smart agriculture and LDN % of beneficiaires benefitting from awareness raising and capacity building for climate smart agriculture and LDN, which are women | 0 beneficiares |  | 300 beneficiaries 40% beneficiaries are women
Output 3.1: Farmer field schools and extension services have been provided to share best practices of climate smart agriculture and LDN for the targeted communities; | # number of beneficiaries aware of climate change impacts and appropriate responses to threats % of beneficiaires aware of climate change impacts and appropriate responses to threats, which are women | 0 beneficiares |  | 200 beneficiaries 40% women beneficiaries
Output 3.2 Best practices examples and training material on climate smart agriculture are formulated, disseminated and made accessible; | # training programs and thematic topics Awareness raised at community level of climate change threats | 0 trainings |  | 4 training programs and thematic topics
Output 3.3 Community based adaptation planning is conducted for target communities; | No of community based adaptation plans formulated | Not forumulated |  | 4 community based adaptation plans formulated
Output 3.4 Strategies for sustaining climate smart agriculture and LDN in target areas have been formulated. | Strategy for sustaining climate smart agriculture and LDN in target areas have been formulated. | Not available |  | 3 community based adaptation plans formulated

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | There were some implemetnation issues regarding the Management Board establishment due to legilation issues. Active consultations between state institutions enabled to solve the problem and move on to project implementation. This issue enabled active communication between different stakeholders and will help in solving of any future problems regarding the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The huge delay in implementaion is COVID-19 pandemic. Armenia currently is 10th by total cases for 1 million popoulation and the country is still in emergency situation starting March 16. All the implementation activities are carried out according to the rules of emergency situation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There have not been major changes in project outputs which will differ from the initial outputs.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | All the activities which had environmental and social safeguard measures have been effective, such as identification of beneficiaries with gender equity.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender consideration have been an integral part of our project from the development process. Starting from the project development phase EPIU has ensured equal participation for both men and women in the consulatations. During the project implementation this approach was always in place. During the identification of stakeholders the project team ensured that women participation is ensured. Furthermoe during the process women showed active participation in community based decision making and during the consultations periods. Also we belive that women involved in the project will be an important part for project sustainablity and knowledge sharing.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | EPIU
Type of implementing entity | NIE
Country | Armenia
Region | Eastern Europe
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 16000 | 16000 | 0 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 40% | 40% | 0% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 300 | 40% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.2: No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | km rehabilitated | 1: Ineffective | Other | 40 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 10 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1382 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 1: Ineffective | Forests | 3 | ha rehabilitated | 5: Very effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Personal capital | Agriculture | Supporting livelihoods | 100 | Personal capital | Agriculture | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 350 | Agriculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.