## SPD
Code | [6 empty] | BHs | SPD | Coordinator | 2003-12-01 |  |  |  | 2004-01-01 |  |  |  | 2004-02-01 |  |  |  | 2004-03-01 |  |  |  | 2004-04-01 |  |  |  | 2004-05-01 |  |  |  | 2004-06-01 |  |  |  | 2004-07-01 |  |  |  | 2004-08-01 |  |  |  | 2004-09-01 |  |  |  | 2004-10-01
900 | [9 empty] | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4 | W1 | w2 | w3 | w4
100000 | a | GDP |  |  |  |  | 155
110000 | a |  | Final Consumption expend by households |  |  |  | 110
110100 | a |  |  |  | Food and non-alchoholic beverage |  | 29 | 184
| a |  |  |  |  | Food | 27
| a |  |  |  |  | Non Alchoholic beverage | 2
110200 | a |  |  |  | Alchoholic beverage, tobacco and narcotics |  | 5 | 19
| a |  |  |  |  | Alchoholic beverages | 3
| a |  |  |  |  | Tobacco | 1
| a |  |  |  |  | Narcotics | 1
110300 | a |  |  |  | Clothing and Footwear |  | 5 | 120
| a |  |  |  |  | Clothing | 3
| a |  |  |  |  | Footwear | 2
| a |  |  |  | Food, Beverage, Tobacco, Clothing and Footwear |  | 39 | 323
| a |  |  |  |  | Master SPDs Templates Prepared and Sent to Regions
| a |  |  |  |  | Regions Send Comments to Global Office
| a |  |  |  |  | Master SPDs Prepared and Sent to regions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys
| a |  |  |  |  | Reg/Country Select PS
| a |  |  |  |  | Final Review PS
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
Global Office inputs Asia's PSs into SPD system
110400 | a |  |  |  | Housing, water, electricity, Gas |  | 7 | 2
| a |  |  |  |  | Actual and imputed rentals | 1
| a |  |  |  |  | Maintenance and repair | 1
| a |  |  |  | Housing |  | 2 | 2
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office | bar: 2004-05-01 w3 to 2004-06-01 w3
Region amends/adds SPDs | bar: 2004-06-01 w4 to 2004-07-01 W1
Global Office reviews amendments/additions | bar: 2004-07-01 W1 to 2004-07-01 w2
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys* | bar: 2004-07-01 W1 to 2004-07-01 w3
| a |  |  |  |  | Reg/Country Select PS* | bar: 2004-07-01 w3 to 2004-08-01 W1
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office | bar: 2004-07-01 w4 to 2004-08-01 W1
| a |  |  |  |  | Taking and Compiling pictures | bar: 2004-07-01 w2 to 2004-08-01 W1
| a |  |  |  |  | Regional meeting to discuss and adopt PSs | bar: 2004-08-01 w3 to 2004-08-01 w4
Translate regional PSs into local languages | bar: 2004-09-01 W1 to 2004-09-01 w4
110400 | a |  |  |  | Housing, water, electricity, Gas |  | 7 | 27
| a |  |  |  |  | Water | 2
| a |  |  |  |  | electricity | 3
110500 | a |  |  |  | Furnishings and household equipment |  | 13 | 150
| a |  |  |  |  | Furniture | 3
| a |  |  |  |  | Textiles | 1
| a |  |  |  |  | Appliances | 3
| a |  |  |  |  | Glassware, tableware | 1
| a |  |  |  |  | Tools and equipment | 2
| a |  |  |  |  | Household maintenance | 3
| a |  |  |  | Utilities, Furniture and equipment |  | 20 | 175
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office | bar: 2003-12-01 w3 to 2004-02-01 W1
Region amends/adds SPDs | bar: 2004-02-01 w2 to 2004-02-01 w3
Global Office reviews amendments/additions | bar: 2004-02-01 w3 to 2004-02-01 w4
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys* | bar: 2004-02-01 w3 to 2004-03-01 W1
| a |  |  |  |  | Reg/Country Select PS* | bar: 2004-03-01 W1 to 2004-03-01 w3
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office | bar: 2004-03-01 w2 to 2004-03-01 w3
| a |  |  |  |  | Taking and Compiling pictures | bar: 2004-02-01 w4 to 2004-03-01 w3
| a |  |  |  |  | Regional meeting to discuss and adopt PSs | bar: 2004-04-01 W1 to 2004-04-01 w2
Translate regional PSs into local languages | bar: 2004-04-01 w3 to 2004-05-01 w2
110600 | a |  |  |  | Health |  | 7 | 33
| a |  |  |  |  | Medical products, appliances and equipment | 3
| a |  |  |  |  | Outpatient services | 3
| a |  |  |  |  | Hospital Services | 1
| a |  |  |  | Health |  | 7 | 33
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office
Region amends/adds SPDs
Global Office reviews amendments/additions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys*
| a |  |  |  |  | Reg/Country Select PS*
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
110700 | a |  |  |  | Transport |  | 13 | 74
| a |  |  |  |  | Purchase of Vehicles | 4
| a |  |  |  |  | Operation of personal transport equipment | 3
| a |  |  |  |  | Transport services | 6
110800 | a |  |  |  | Communication |  | 3 | 11
| a |  |  |  |  | Postal services | 1
| a |  |  |  |  | Telephone and telex equipment | 1
| a |  |  |  |  | Telephone and telefax services | 1
[5 empty] | Transport and Communication |  | 16 | 85
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office
Region amends/adds SPDs
Global Office reviews amendments/additions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys*
| a |  |  |  |  | Reg/Country Select PS*
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
110900 | a |  |  |  | Recreation and Culture |  | 13 | 102
| a |  |  |  |  | Audio-visual, photographic and equipment | 3
| a |  |  |  |  | Other major durables for recreation and culture | 2
| a |  |  |  |  | Other recreational items | 3
| a |  |  |  |  | Recreational and culture services | 3
| a |  |  |  |  | Newspaper, books and stationary | 1
| a |  |  |  |  | Package holidays | 1
| a |  |  |  | Recreation & Culture |  | 13 | 102
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office
Region amends/adds SPDs
Global Office reviews amendments/additions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys*
| a |  |  |  |  | Reg/Country Select PS*
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
111000 | a |  |  |  | Education |  | 1 | 6
| a |  |  |  | Education |  | 1 | 6
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office
Region amends/adds SPDs
Global Office reviews amendments/additions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys*
| a |  |  |  |  | Reg/Country Select PS*
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
111100 | a |  |  |  | Restaurants and Hotels |  | 2 | 16
| a |  |  |  |  | Catering services | 1
| a |  |  |  |  | Accommodation Services | 1
111200 | a |  |  |  | Miscellaneous Goods and Services |  | 10 | 65
| a |  |  |  |  | Personal care | 2
| a |  |  |  |  | Prostitution | 1
| a |  |  |  |  | Personal effects (jewelry, watches) | 2
| a |  |  |  |  | Social protection | 1
| a |  |  |  |  | Insurance | 1
| a |  |  |  |  | Financial Services | 2
| a |  |  |  |  | Other services | 1
111300 | a |  |  |  | Balance of exp of residents abroad |  | 2
| a |  |  |  | Restaurant, Misc Goods & expend of residents abroad |  | 14 | 81
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office
Region amends/adds SPDs
Global Office reviews amendments/additions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys*
| a |  |  |  |  | Reg/Country Select PS*
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
120000 | a |  |  | Individual Consumption expenditure by NPISHS |  |  | 1
130000 | a |  |  | Individual Consumption expenditure by Government |  |  | 21
130100 | a |  |  |  | Housing |  | 1
130200 | a |  |  |  | Health |  | 12
| a |  |  |  |  | Health benefits and reimbursements | 7
| a |  |  |  |  | Production of health services | 5
130300 | a |  |  |  | Recreation and Culture |  | 1
130400 | a |  |  |  | Education |  | 6
| a |  |  |  |  | Education benefits and reimbursements | 1
| a |  |  |  |  | Production of education services | 5
130500 | a |  |  |  | Social protection |  | 1
| a |  |  |  | Expenditure by NPISHS and Government |  | 22
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office
Region amends/adds SPDs
Global Office reviews amendments/additions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys*
| a |  |  |  |  | Reg/Country Select PS*
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
140000 | a |  | Collective Consumption Exp by Government |  |  |  | 5
| a |  |  |  | Collective Consumption Exp by Government |  | 5
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office
Region amends/adds SPDs
Global Office reviews amendments/additions
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys*
| a |  |  |  |  | Reg/Country Select PS*
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office
| a |  |  |  |  | Taking and Compiling pictures
| a |  |  |  |  | Regional meeting to discuss and adopt PSs
Translate regional PSs into local languages
150000 | a |  | Expenditure on Gross Fixed Capital Formation |  |  |  | 12
150100 | a |  |  |  | Machinery and equipment |  | 8
150200 | a |  |  |  | Construction |  | 3
150300 | a |  |  |  | Other products |  | 1
160000 | a |  |  | Changes in inventories |  |  | 4
| a |  |  |  | Changes in inventories |  | 2
| a |  |  |  | Acquisition less disposal of valuables |  | 2
| a |  |  |  | Expenditure on Gross Fixed Capital Formation |  | 16
| a |  |  |  |  | SPD formatted for SPD software sent to Regional Office | bar: 2004-05-01 w3 to 2004-06-01 w3
Region amends/adds SPDs | bar: 2004-06-01 w4 to 2004-07-01 W1
Global Office reviews amendments/additions | bar: 2004-07-01 W1 to 2004-07-01 w2
| a |  |  |  |  | Regions/Countries Conduct Pre-Surveys* | bar: 2004-07-01 W1 to 2004-07-01 w3
| a |  |  |  |  | Reg/Country Select PS* | bar: 2004-07-01 w3 to 2004-08-01 W1
| a |  |  |  |  | Final Review PS/ Send regional SPDs & PSs to Global Office | bar: 2004-07-01 w4 to 2004-08-01 W1
| a |  |  |  |  | Taking and Compiling pictures | bar: 2004-07-01 w2 to 2004-08-01 W1
| a |  |  |  |  | Regional meeting to discuss and adopt PSs | bar: 2004-08-01 w3 to 2004-08-01 w4
Translate regional PSs into local languages | bar: 2004-09-01 W1 to 2004-09-01 w4
a
170000 | a |  | Balance of exports and imports |  |  |  | 2
*Regions may reverse these two steps depending on their chosen approach. See ICP Handbook, chapter 5: Product lists, specifications and the Pre-Survey.

## Work Plan - Timetable
TIMETABLE
| 2003 | [11 empty] | 2004 | [11 empty] | 2005 | [11 empty] | 2006
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Structured Product Descriptions (SPDs)
SPD Software
First version to regions
Incorporate comments from regions*
Revised version sent to regions
Developing SPDs and List of Specifications (PSs)
Consumption
Food Clothing and Footwear
Housing Utilities, Furniture and equipment
Transport, Communication and Rec. & Culture
Restaurant, Misc Goods & expend of residents abroad
Housing, Education and Health
Government Expenditure and Capital Formation
Ring Comparison
Determine ring countries and ensure participation
Determining ring countries
Recruiting ring countries
Develop SPDs and List of Specifications (PSs)
Food Clothing and Foot wear
Rest of Consumption
Government Expenditure and Capital Formation
ICP Handbook
Drafting handbook and translation
Chapter 1 - 5
Chapter 6 and 7
Translation (Chapter 3-7)
Identify Translators
Translation Commissioned
Draft submitted to Global Office
Draft edited and proofread
Chapters distributed in 6 languages
Chapter 8-10
Chapter 8 (Government) draft finalized
Chapter 9 (Capital formation) draft finalized
Chapter 10 (modified ring) draft finalized
Translation (Chapter 8-10)
Identify Translators
Translation Commissioned
Draft submitted to Global Office
Draft edited and proofread
Chapters distributed in 6 languages
Chapter 11-14
Chapter 11 Housing
Chapter 12 (aggregation) draft finalized
Chapter 13 (regression and extrapolation) draft finalized
Chapter 14 (uses of PPP data) draft finalized
Translation (Chapter 11-14)
Identify Translators
Translation Commissioned
Draft submitted to Global Office
Draft edited and proofread
Chapters distributed in 6 languages
ICP Tool Pack
Data Collection and Editing Module**
Software Development
Presentation to regions
Incorporating comments
Final version
Testing and finalizing English Version
Translation
Identify Translators
Commission translation
Test translated version
Data Collection Module distributed
Training
Training regional trainers (using English Version)
Training National Data Collectors (in various languages)
Data Administration and Analysis Module**
Software Development
Testing and finalizing English Version
Translation
Identify Translators
Commission translation
Test translated version
Data Administration Module distributed
Training
Training regional trainers (using English Version)
Training National Coordinators (in various languages)
Price Surveys
Resource Transfer and Disbursement Schedule
MOUs Between Regions and Countries
Determine venue to transfer resources to countries
Transfer resources
Develop National Surveys Plan of Action and Schedule
Develop National Survey Framework & Schedule
Determine outlets and frequency of data collection
Determine procedure to estimate national and annual avg.
Recruiting/Identifying data collectors and supervisors Schedule
Identifying data collectors and supervisors
Identify Consultants for Technical Assistance where needed
Training for data collectors and supervisors
Training data collection, verification and processing
Tool Pack training
Data Collection
Consumption (food, clothing and footwear)
Consumption (non-food, clothing and footwear)
Housing, Health and Education
Government Expenditure
Capital Formation
Expenditure Weights
Compiling Detailed Expenditure Weights
Statistical capacity assessment
Determine level of detailed that can be prepared
Develop work plan and time table
Determine Technical Assistance Needs
Identify Consultants
Prepare preliminary estimates
Compile Final estimates
Data Editing
Data Editing (food clothing and footwear)
Data Editing (rest of consumption goods and services)
Data Editing (Government Expenditure, Capital Formation)
Calculation and Dissemination
Note on M93: wb226922: Potentially Nov 14 Tunis
Note on M64: wb226922: Potentially Nov 14 Tunis
Note on M121: wb226922: Potentially Nov 14 Tunis
Note on M20: wb226922: Potentially Nov 14 Tunis
Note on M31: wb226922: Potentially Nov 14 Tunis
Note on M136: wb226922: Potentially Nov 14 Tunis
Note on M138: wb226922: Potentially Nov 14 Tunis