## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 21 May 2014 to 20 May 2015
| Project Title: | Enhancing Climate Change Resilience of Rural Community Living in Protected Area in Cambodia
| Project Summary: | The climate change-induced hazard of erratic rainfall, which leads to droughts and floods, is decreasing agricultural productivity in Cambodia thereby constraining efforts to reduce poverty levels. These erratic rainfall events are predicted to increase under future climate change scenarios. Some of the most vulnerable groups in Cambodia are rural communities living in Protected Areas (PAs). This is because of the dependence of these communities on ecosystem services and a lack of alternative, climate-resilient livelihoods. As a result of erratic rainfall and consequent decreasing agricultural productivity, these communities are increasingly reliant on forest ecosystems to provide supplementary food sources and income from collecting and selling non-timber forest products (NTFPs) and fuelwood. Widespread degradation of forest ecosystems, however, is reducing the efficacy of this adaptation response. The consequences of the climate change-induced hazard of erratic rainfall include: i) increased erosion as a result of floods which damages crop production; ii) crop failure or reduction of yield as a result of drought; and iii) damaged infrastructure as a result of extreme rainfall events which limits access to urban markets. An Adaptation Fund (AF) project has been developed by UNEP and the Ministry of Environment (MoE) in Cambodia to address the vulnerability of rural communities to climate change using ecoagriculture. The project “Enhancing Climate Change Resilience of Rural Communities living in Protected Areas in Cambodia” aims to enhance the climate change resilience of communities living around five community protected area (CPA) intervention sites, as well as downstream communities, to the climate change-induced hazard of erratic rainfall. The project has three main components: 1. Protocols for ecoagriculture interventions Component 1 will use bio-physical, ecological and socio-economic research to develop restoration and conservation agriculture protocols to be implemented in Component 2. 2. Concrete ecoagriculture adaptation interventions Component 2 will ensure that the restored forests and productive agricultural areas are maintained and the benefits maximised. Alternative livelihoods established through the AF project will increase the resilience of local communities to the effects of climate change. 3. Institutional capacity, awareness raising and upscaling of ecoagriculture interventions Component 3 will create an enabling environment for the ecoagriculture concept to be implemented in other PAs in Cambodia, through awareness raised at a local and national level, and an upscaling strategy supported by policy revision where required. The AF project activities will be based on the best available knowledge, technology and proven approaches regarding restoring natural capital and intensifying agriculture in PAs. These activities, within five years, will enhance food supply and conserve topsoil at the CPA intervention sites. The AF project will also implement measures to build the capacity of local communities to restore and intensify agriculture. This improved capacity will increase the climate change resilience of local communities. It will also enable replication and upscaling of the AF project approach to other CPAs, thereby sustaining benefits beyond the lifetime of the AF project.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2H81 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Kingdom of Cambodia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Project offices: #48 Preah Sihanouk Blvd., 2nd Floor, Phnom Penh, Cambodia Protected Areas: Boeungper Wildlife Sanctuary (Chiork Boeungprey Community Protected Area (CPA), Chorm Thlok CPA and Skor Krouch CPA), Phnom Kulen National Park (Chop Tasok CPA) and Phnom Prech Wildlife Sanctuary (Ronouk Khgneng). | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-28
IE-AFB Agreement Signature Date: |  | 2013-03-08 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2013-05-21 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2016-12-01
| Terminal Evaluation Date: | 2018-05-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project reports: Inception Workshop Report 2013; Follow-up Inception Workshop Report 2013; Quarterly Expenditure Reports (Q2, Q3, Q4 2013, Q1, Q2, Q3, Q4 2014, and Q1 2015), Second PSC meeting minutes. TORs: Project Steering Committee; National Project Coordinator; Chief Technical Adviser (CTA); Financial and Administrative Assistant; Team Leaders (3); Assistant Team Leaders (3); Field leaders (4); Baseline Study. TORs for National Experts (17): Adaptation Training Expert; Agricultural Adaptation Expert; Agricultural and Market Assessment Expert; Agriculture Climate Forecasting Expert; Botanist; Awareness Campaign Expert; Capacity Building Expert; Finance and Insurance Expert; Hydrologist; Institutional Mapping Expert; Land Tenure Policy Expert; Socio-economic Expert; Web-based Data Expert; Redd+ Expert; Livelihood expert group; National Research and Monitoring coordinator; and International Research and Monitoring coordinator. Consultant reports: Baseline Study Report; and 14 National Expert Reports. Training Needs Assessment. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | afcpa@online.com.kh (website under construction) | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Ouk Navann | Dominican Republic
| Email: | AFCPA@online.com.kh | Ecuador
| Date: | 2014-05-31 | Egypt
| Government DA |  | El Salvador
| Name: | Dr. Tin Ponlok | Equatoral Guinea
| Email: | Etap@online.com.kh | Eritrea
| Date: | 2014-05-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Atifa Kassam | Fiji
| Email: | atifa.kassam@unep.org | Finland
| Date: | 2014-05-31 | France
| Executing Agency |  | Gambia
| Name: | Dr. Yin Kimsean | Georgia
| Email: |  | Germany
| Date: | 2014-05-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information: cumulative from project start to 31 May 2015
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 May 2015 | 929312
Add any comments on AF Grant Funds. (word limit=200) | The amount reported above is the cumulative expenditure/disbursement from inception up until 31 May 2015.
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach | 66409
| 1.2 Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products | 19400
| 1.3 Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 | 22500
| 2.1 Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2 | 59634.75
| 2.2 Forest restoration and conservation agriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites | 299149.69
| 2.3 Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies | 31700.57
| 2.4 Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 4600
| 3.1 Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities | 36895.38
| 3.2 Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation | 11200
| 3.3 National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia | 0
| 4. Project/Programme Execution cost | 54803.89
| Monitoring and Evaluation | 4021.13
| TOTAL | 610314.41
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach | 78750 | 2016-05-16
| 1.2 Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products | 4000 | 2016-05-16
| 1.3 Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 | 30000 | 2016-05-16
| 2.1 Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2 | 77000 | 2016-05-16
| 2.2 Forest restoration and conservation agriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites | 714643 | 2016-05-16
| 2.3 Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies | 60000 | 2016-05-16
| 2.4 Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 42000 | 2016-05-16
| 3.1 Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities | 86600 | 2016-05-16
| 3.2 Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation | 5400 | 2016-05-16
| 3.3 National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia | 0 | n/a
| 4. Project/Programme Execution cost | 68400 | 2016-05-16
| Monitoring and Evaluation | 36300 | 2016-05-16
| TOTAL | 1203093
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Current climate and seasonal variability and/or hazard events result in poor restoration results or agricultural yields. | Low | The Botanist, Agricultural Climate Forecasting Expert and Agricultural Adaptation Expert have identified appropriate flood- and drought-resistant species to utilise during restoration activities. Restoration actvities have been timed to coincide with the onset of the wet season.
Intervention sites may be sold for Economic Land Concessions. | Low | The intervention sites are situated within CPAs, which by law cannot be sold as Economic Land Concessions. A Land Tenure Expert has undertaken a study to confirm the legal status of CPAs and educate local community members about their land tenure rights.
Disagreement amongst stakeholders with regards to demonstration site selection. | Low | The interventions sites were selected using an agreed upon list of criteria to ensure that the selection process was transparent and equitable. The selection process was conducted through a thorough participatory approach, with multiple meetings/workshops with local communities. At each project site, the relevant CPA Community Management Committees have identified the specific sites for project activities.
Communities may not adopt activities during or after the AF project. | Low | Extensive community consultations have been held since the initiation of the project. These consultations have been conducted during the baseline study and as part of the duties of the 14 National experts. Therefore local knowledge is included in the design of project interventions and activities, reducing the risk that local communities may not adopt the project interventions. In addition to the work conducted by consultants to the project, the national government counterparts (team leaders, assistant team leaders and field leaders) visit each of the target communities regularly to inform community members of project activities and ensure their continued support. During one such visit, each household within all five CPA intervention sites was visited to assess their willingness to participate in the project activities and obtain a "family profile". Based on this information, 198 households in Beungper Wildlife Sanctuary, 20 households in Phnom Kulen National Park and 10 households in Phnom Prich National Park were selected to participate in project activities during the second year. Because these households were selected based on their willingness and capacity to participate, the risk of them not adopting project activities is low. Water infrastructure, including ponds, dams, wells and distribution systems, have also been constructed at each of the project sites. This tangible benefit to local communities has generated additional support for the project. Finally, the project is, and will continue to, undertake training in local communities to promote ecoagriculture and highlight the benefits provided by the AF project interventions. To date, training has been provided on nursery management, seed propagation, climate change awareness, ecoagriculture, land tenure and family financial management.
Loss of government support may result in lack of prioritisation of AF project activities. | Low | 10 government counterparts (team leaders, assistant team leaders and field leaders) have been hired by the project to facilitate the implementation of project activities. The government therefore has a vested interest to maintain its support of project activities. In addition, regular government stakeholder consultations have taken place to keep them informed of project progress and the benefits that the project offers to their ongoing agriculture and forestry programmes. High-level government officials, including the Minister of Environment, have also been involved in the inauguration of project intervention sites. The physical demonstration of project activities to government officials has ensured their continued support of the project.
Institutional capacities and relationships are not sufficient to provide effective solutions to climate problems that are complex and multi-sectoral. | Medium | Institutional capacity development is included in the design of the project. To date, an Institutional capacity expert has undertaken an institutional mapping exercise and gap analysis in relevant government departments and research institutions to determine potential shortfalls for the planning and implementation of ecoagriculture interventions in CPAs. The results of this assessment have been used to ensure that the necessary and appropriate government departments have been included in the implementation of project activities (e.g. staff from the Ministry of Agriculture have been involved in the training on ecoagriculture and the selection of drought-resilient rice varieties). In addition, national experts have been hired where appropriate to contribute specialised technical expertise. These experts have transferred knowledge and skills to government officials. High-level government officials, including the Minister of Environment, have also been involved in the inauguration of project intervention sites. This has ensured awareness of, and support for, the project across multiple government departments.
Capacity constraints of local institutions may limit the ability to undertake the research and interventions. | Medium | The Royal University of Phnom Penh and the Royal Agriculture University have been approached to contribute to the long-term research objectives of the project. These are the premier research institutions within Phnom Penh. Five MSc students with appropriate supervisors have been identified to undertake research related to the AF project over the next two years. Additional MSc students will be recruited in 2016. Furthermore, an International Research and Monitoring Coordinator (in addition to a National Research and Monitoring Coordinator) has been recruited to guide the research and monitoring activities of the students, national experts and project monitoring team. Finally, the CTA for the project is actively engaged to provide technical advice on project interventions, monitoring and research.
Priority interventions implemented are not found to be cost-effective. | Low | Cost-effectiveness was an important consideration in the design of the project, and thus the risk that interventions are found not to be cost-effective is low. In addition, an Agricultural Market Assessment expert was hired with the specific objective to analyse the cost-benefit of selected interventions. The findings of this expert were used to guide further project interventions.
Lack of commitment/buy-in from local communities may result in failure of intervention sites. | Low | Extensive community consultations have been held since the initiation of the project. These consultations have been conducted during the baseline study and as part of the duties of the 14 National experts. Therefore local knowledge is included in the design of project interventions and activities, reducing the risk that local communities may not adopt the project interventions. In addition to the work conducted by consultants to the project, the national government counterparts (team leaders, assistant team leaders and field leaders) visit each of the target communities regularly to inform community members of project activities and ensure their continued support. During one such visit, each household within all five CPA intervention sites was visited to assess their willingness to participate in the project activities and obtain a "family profile". Based on this information, 198 households in Beungper Wildlife Sanctuary, 20 households in Phnom Kulen National Park and 10 households in Phnom Prich National Park were selected to participate in project activities during the second year. Because these households were selected based on their willingness and capacity to participate, the risk of them not adopting project activities is low. Water infrastructure, including ponds, dams, wells and distribution systems, have also been constructed at each of the project sites. This tangible benefit to local communities has generated additional support for the project. Finally, the project is, and will continue to, undertake training in local communities to promote ecoagriculture and highlight the benefits provided by the AF project interventions. To date, training has been provided on nursery management, seed propagation, climate change awareness, ecoagriculture, land tenure and family financial management.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The percieved threat of CPA land being sold as an Economic Land Concession has led to communities clearing land within the CPA for farming activities, which threatens the project's restoration objectivies. | Medium | Based on the recommendations of the baseline study, the project restoration interventions have been adjusted to focus on agricultural land within CPAs in addition to the degraded forest areas which were initiatlly targeted by the project. This is due to the recently identified increased risk of land clearance within CPA's following the Economic Land Concessions which has resulted in less communally owned areas of degraded forests available for restoration. An agroforestry approach will be adopted in the agricultural lands within CPAs which will increase the ecological diversity and functioning of these areas while maintaining the livelihoods of the local farmers. Because local communities continue to derive income and livelihoods from these lands, this will reduce the threat of land clearance once project activities have ended. In addition, local community members in the Chom Thlork CPA (where this risk is high) have signed contracts with the government pledging not to clear additional areas of forest within the CPA. Training on land tenure and community land tenure rights has also been provided to local communities. This training has emphasised the fact that CPA's cannot legally be sold as an Economic Land Concession, and therefore community members do not need to clear land in order to "claim" it.
Government counterparts, assigned to work part-time with the project do not have sufficient time to dedicate to the project, which negatively the implementation of project activities. | Low | Thorough workplans have been developed for the project to enable the government counterparts the opportunity to manage their time and set aside time to work on the project in advance. Through the involvement of high-level government officials in project activities, the project has garnered significant support within the MoE. Government staff are therefore encouraged to work on the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1: Protocols for ecoagriculture interventions.
| Information on preferred ecoagriculture interventions gathered through a particpatory approach. |  | Consulants gather information from participating communities. Reports on preferred ecoagriculture interventions. Establish MSc research in local institutions. |  | Consultants have visited project intervention sites and collected the relevant information. The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. 5 students from two separate universities have received bursaries through the project and began their research dissertations at the beginning of 2015. | S
| Economic assesments undertaken to identify appropriate ecoagriculture interventions |  | Consulants gather information from participating communities. Reports on economic assessments of preferred ecoagriculture interventions. |  | Consultants have visited project intervention sites and collected the relevant information. The three relevant reports (Microfinance/Insurance assessment; Market assessment; socio-economic assessment) have been submitted and finalised. | S
Component 2: Concrete ecoagriculture interventions.
| Training on ecoagriculture interventions has started. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 43 training events have been conducted. This includes: i) 1 training needs assessment; ii) 7 Training of Trainer events (involving CPA management commitees and local extension officers) on seven separate topics; ii) 35 (7 topics at each of the 5 CPAs) community training workshops. | S
| Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration has started. Chamkar-based agroforestry plots established. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed and inaugurated. Forest restoration has begun iat CPAs in Beung Per Wildlife Sanctuary and Phnom Kulen National Park. A demonstration agroforestry plot has been established. Community members to pilot the agroforestry plots have been identified, but planting has yet to begin. 224 homegardens have been established. 64 households in total have recieved and planted drought-resilient rice varieties. | S
| Local communities' s livelihoods are enhanced. |  | Prepare ToR and recruit National consultant. A livelihood development plan for each CPA is developed. |  | ToR prepared a national consultantcy has been recruited. A draft livelihood development plan for each CPA is currently being prepared. | S
| Socio-economic and ecosystem monitoring of project impacts. |  | Prepare ToR and recruit consultants. A research and monitoring framework is developed. Monitoring tools are developed. |  | ToRs have been prepared and both an International and a National Research and Monitoring Coordinator have been recruited. A draft research and monitoring framework has been prepared and submitted to the PMU. Draft monitoring tools have been prepared and submitted to the PMU. | S
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
| Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. | MS
| CPA Management plans updated/developed. |  | Prepare ToRs and recruit National Consultant. Conduct consultations with local communities to draft CPA management plans. |  | ToR prepared a national consultant has been recruited. Consultations with local communities have been undertaken, and the CPA management plans are expected to be completed by the end of 2015. | S
Project operation and management
| Project management unit. |  | Manage project activities. Recruit necessary consultants. Undertake annual audit. |  | Project activities have been well coordinated and are largely progressing according to the workplan prepared. The necessary recruitment processes have been followed to recruit consultants. The annual audit was undertaken. | S
| Procurement |  | Prepare procurement plan. Procure consultancies for second year. Procure goods and services for ecoagriculture interventions. |  | A procurement plan was prepared. The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example nursery construction firms) necessary for the ecoagriculture interventions. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ouk Navann, National Project Coordinator
| Email: | navanouk@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
In general, the project implementation progress is going very well towards the achievement of second year of implementation. The project has established Project Steering Committee, employed the Project Management Unit, employed Government Counterparts and recruited many consultants. The project has established three nurseries, established nursery team and trained them on nursery management and seedling propagation. In addition, project teams have organized a total of 43 training events with local communities. Furthermore, the project team with local villagers planted a huge amount of indigenous trees and distributed similar amount of fruit tree to households. Local communities at the project targeted areas have shown their strong commitment to participate with the project activities. The project teams worked closely with local communities to develop working relationships and build trust. This collaboration has resulted in nursery construction and management, construction of water supply infrastructures, establishment of homegardens and implementation of climate-resilient rice trials. The success of these interventions has encouraged additional households to participate in the project interventions. Moreover, the project has made significant progress towards developing ecoagriculture protocols, training of local communities, developing a research and monitoring plan and developing alternative livelihoods. Limited time availability of the government counterpart with the long distance of seasonal bad road condition between the five project intervention sites has also posed some challenges to the project implementation. The project is still however able to deal with these challenges mainly through government counterparts who have improved communication with the target communities, and increased their willingness to participate in project activities. The only significant aspect where the project is behind is regarding the implementation of agroforestry activity with household; however, the project team has established one pilot agroforestry site as project feasibility to public. In conclusion, I would rate the performance of the project as satisfactory because of the project teams have trained a large amount of local communities, the completion of various expert technical assessments, the successful implementation of on-the-ground interventions with pilot families such as homegardens, trial resilience rice seeds, provision of water supply infrastructures.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1: Protocols for ecoagriculture interventions.
| Information on preferred ecoagriculture interventions gathered through a particpatory approach. |  | Consulants gather information from participating communities. Reports on preferred ecoagriculture interventions. Establish MSc research in local institutions. |  | Consultants have visited project intervention sites and collected the relevant information. The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. 5 students from two separate universities have received bursaries through the project and began their research dissertations at the beginning of 2015. | S
| Economic assesments undertaken to identify appropriate ecoagriculture interventions |  | Consulants gather information from participating communities. Reports on economic assessments of preferred ecoagriculture interventions. |  | Consultants have visited project intervention sites and collected the relevant information. The three relevant reports (Microfinance/Insurance assessment; Market assessment; socio-economic assessment) have been submitted and finalised. | S
Component 2: Concrete ecoagriculture interventions.
| Training on ecoagriculture interventions has started. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 43 training events have been conducted. This includes: i) 1 training needs assessment; ii) 7 Training of Trainer events (involving CPA management commitees and local extension officers) on seven separate topics; ii) 35 (7 topics at each of the 5 CPAs) community training workshops. | S
| Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration has started. Chamkar-based agroforestry plots established. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed and inaugurated. Forest restoration has begun at CPAs in Beung Per Wildlife Sanctuary and Phnom Kulen National Park. A demonstration agroforestry plot has been established. Community members to pilot the agroforestry plots have been identified, but planting has yet to begin. 224 homegardens have been established. 64 households in total have recieved and planted drought-resilient rice varieties. | S
| Local communities' s livelihoods are enhanced. |  | Prepare ToR and recruit National consultant. A livelihood development plan for each CPA is developed. |  | ToR prepared a national consultantcy has been recruited. A draft livelihood developemnt plan for each CPA is currently being prepared. | S
| Socio-economic and ecosystem monitoring of project impacts. |  | Prepare ToR and recruit consultants. A research and monitoring framework is developed. Monitoring tools are developed. |  | ToRs have been prepared and both an International and a National Research and Monitoring Coordinator have been recruited. A draft research and monitoring framework has been prepared and submitted to the PMU. Draft monitoring tools have been prepared and submitted to the PMU. | S
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
| Awareness raising campaign is implemented. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. | S
| CPA Management plans updated/developed. |  | Prepare ToRs and recruit National Consultant. Conduct consultations with local communities to draft CPA management plans. |  | ToR prepared a national consultant has been recruited. Consultations with local communities have been undertaken, and the CPA management plans are expected to be completed by the end of 2015. | S
Project operation and management
| Project management unit. |  | Manage project activities. Recruit necessary consultants. Undertake annual audit. |  | Project activities have been well coordinated and are largely progressing according to the workplan prepared. The necessary recruitment processes have been followed to recruit consultants. The annual audit was undertaken. | HS
| Procurement |  | Prepare procurement plan. Procure consultancies for second year. Procure goods and services for ecoagriculture interventions. |  | A procurement plan was prepared. The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example nursery construction firms) necessary for the ecoagriculture interventions. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Atifa Kassam
| Email: | atifa.kassam@unep.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has progressed extremely well since the last PPR, with all relevant studies conducted, the three nurseries established including water infrastructure to support the nurseries and various trainings delivered to local communities. While there has been progress in developing a draft monitoring framework , efforts need to be made going forward to ensure that the results and lessons learned coming out of the pilot demonstrations are collected and fed back into the project. I would rate the project as Satisfactory given that all expected milestones and targets have been acheived thus far.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Chief Technical Advisor | Component 1: Protocols for ecoagriculture interventions.
| Information on preferred ecoagriculture interventions gathered through a particpatory approach. |  | Consulants gather information from participating communities. Reports on preferred ecoagriculture interventions. Establish MSc research in local institutions. |  | Consultants have visited project intervention sites and collected the relevant information. The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. 5 students from two separate universities have received bursaries through the project and began their research dissertations at the beginning of 2015. | S
| Economic assesments undertaken to identify appropriate ecoagriculture interventions |  | Consulants gather information from participating communities. Reports on economic assessments of preferred ecoagriculture interventions. |  | Consultants have visited project intervention sites and collected the relevant information. The three relevant reports (Microfinance/Insurance assessment; Market assessment; socio-economic assessment) have been submitted and finalised. | S
Component 2: Concrete ecoagriculture interventions.
| Training on ecoagriculture interventions has started. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Traiing material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 43 training events have been conducted. This includes: i) 1 training needs assessment; ii) 7 Training of Trainer events (involving CPA management commitees and local extension officers) on seven separate topics; ii) 35 (7 topics at each of the 5 CPAs) community training workshops. | S
| Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration has started. Chamkar-based agroforestry plots established. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed and inaugurated. Forest restoration has begun iat CPAs in Beung Per Wildlife Sanctuary and Phnom Kulen National Park. A demonstration agroforestry plot has been established. Community members to pilot the agroforestry plots have been identified, but planting has yet to begin. 224 homegardens have been established. 64 households in total have recieved and planted drought-resilient rice varieties. | S
| Local communities' s livelihoods are enhanced. |  | Prepare ToR and recruit National consultant. A livelihood development plan for each CPA is developed. |  | ToR prepared a national consultantcy has been recruited. A draft livelihood developemnt plan for each CPA is currently being prepared. | MS
| Socio-economic and ecosystem monitoring of project impacts. |  | Prepare ToR and recruit consultants. A research and monitoring framework is developed. Monitoring tools are developed. |  | ToRs have been prepared and both an International and a National Research and Monitoring Coordinator have been recruited. A draft research and monitoring framework has been prepared and submitted to the PMU. Draft monitoring tools have been prepared and submitted to the PMU. | S
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
| Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. | MS
| CPA Management plans updated/developed. |  | Prepare ToRs and recruit National Consultant. Conduct consultations with local communities to draft CPA management plans. |  | ToR prepared a national consultant has been recruited. Consultations with local communities have been undertaken, and the CPA management plans are expected to be completed by the end of 2015. | S
Project operation and management
| Project management unit. |  | Manage project activities according to workplan. Recruit necessary consultants. Undertake annual audit. |  | Project activities have been well coordinated and are largely progressing according to the workplan prepared. The necessary recruitment processes have been followed to recruit consultants. The annual audit was undertaken. | S
| Procurement |  | Prepare procurement plan. Procure consultancies for second year. Procure goods and services for ecoagriculture interventions. |  | A procurement plan was prepared. The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example nursery construction firms) necessary for the ecoagriculture interventions. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Anthony Mills
| Email: | anthony.mills@c4es.co.za
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Building on the preparatory work conducted during the first year, the project has made good progress towards the achievement of expected outcomes during the second year of implementation. The project team has worked hard with local communities to develop working relationships and build trust. The construction of infrastructure (particularly water supply infrastructure) that provided tangible benefits to communities was an important part of this process. The establishment of these relationships enabled the implementation of on-the-ground interventions with pilot families. These interventions included nursery construction and management, establishment of homegardens and implementation of climate-resilient rice trials. The success of these interventions during the second year of the project has encouraged additional households to participate in the project interventions, and indeed the total number of people implementing homegardens and rice trials is expected to double during the third year of implementation. In addition to on-the-ground interventions (Outcome 2), the project has made significant progress towards developing ecoagriculture protocols (Outcome 1), training of local communities (Outcome 2), developing a research and monitoring plan (Outcome 2) and developing alternative livelihoods (Outcome 2). National consultants have been hired, undertaken the required assessments and submitted their final reports for all of the activities expected to be completed by this time. In addition, a total of 43 training events have been conducted with local communities. Work towards Outcome 3 of the project is mostly scheduled for years 4 and 5 and thus satisfactory progress has been made towards the achievement of this target. The only significant aspect where the project is behind is regarding the implementation of agroforestry in chamkar (agricultural land) plots. To date this intervention is being demonstrated in pilot plots, but is yet to be implemented by community members. It is expected that this intervention will start in July/August 2015 (coinciding with the start of the rainy season). The project is also behind on spending (as it was predicted in the project document), however this is because it has taken time to build the trust of local communities and get them to participate in the ecoagriculture interventions. However, good progress has been made in this regard and interventions will be rolled out to an ever-increasing number of households as the project progresses. Overall, because of the various trainings provided to local communities, the completion of various technical assessments by national consultants and the successful implementation of on-the-ground interventions with pilot families, I would rate the performance of the project as Satisfactory.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicators | Baseline |  | Progress since inception | Target for project end
Objective: Enhance the climate change resilience of communities living around at least three CPA intervention sites, as well as downstream communities, to the climate change-induced hazard of erratic rainfall. | Obj 1 Percentage change in the climate change vulnerability index at each target CPA. | The following table shows the current climate change vulnerability index score at each CPA. The maximun vulnerability index score is 120, but normally ranges between 0 and 50. |  | It is too early to detect a change in the climate change vulnerability index. However, the activities undertaken thus far lay the foundation for a reduction in vulnerability in the target CPAs during the project lifespan. Furthermore, a context-specific methodology to measure the climate change vulnerability index of target communities was developed during the baseline study. The methodology measures vulnerability as a product of exposure and sensitivity to climate risks minus adaptive capacity. The maximun vulnerability index score is 120, but normally ranges between 0 and 50. The baseline climate change vulnerability index scores were collected. The index will be measured again (using the same methodology) at the mid-term and end of the project to assess progress towards to the target reduction in vulnerability. | A 20% decrease in the climate change vulnerability index at each target CPA by the end of the project.
Vulnerability index
|  | Chiork Boeungprey | 10.4
|  | Chorm Thlok | 15.2
|  | Skor Krouch | 25.8
|  | Chop Tasok | 12.1
|  | Ronouk Khgneng | 27.6
| Obj 2 Number of project beneficiaries, gender dissagragated, benfitting from the project's ecoagriculture interventions. | No beneficiaries before the start of the project |  | 3 nurseries have been constructed and community nursery management teams have been established. 126 community members (52 at Beung Per, 35 at Phnom Kulen and 39 at Phnom Prich) are actively involved in the community nursery management teams. 1891 households in total (~ 5 people per household) have recieved fruit trees for planting around their homestead. 54 households in Chop Tasok, 57 in Ronouk Khgeng, 198 in Chiork Beungprey, in 600 Chom Thlork and in 982 Skor Crouch. 64 households in total have recieved and planted drought-resilient rice varieties. (33 Chom Thlork, 4 Chirok Beungprey and 27 in Skor Krouch) 244 households in total are befitting from homegarden activities. (16 households in Chop Tasok, 30 in Ronouk Khgeng, 21 in Chiork Beungprey, in 97 Chom Thlork and in 80 Skor Crouch). 43 training events have taken place (with ~100 participants per event). Water supply infrastructure, reforestation activities and the strenthening of community management committees is benefitting all households within the five project intervention sites. | At least 1000 people, 50% of which are women, are benefitting from the project's interventions by the end of the project.
Outcome 1: Technical expertise and a local enabling framework for forest restoration and ecoagriculture interventions that build climate resilience developed at CPA intervention sites through a consultative and participatory process. | Outcome 1. Change in the capacity of national and local government officials to implement forest restoration and conservation agriculture interventions that build climate resilience. | National and local government officials have limited capacity to implement forest restoration and conservation agriculture interventions that build climate resilience. |  | Significant progress has been made towards developing the technical knowledge required to implement forest restoration and conservation agriculture interventions through the production of 11 technical assessments and reports. The technical knowledge developed through these assessments, including climate-resilient species selections, market assessments and hydrological studies, will build the capacity of the government to implement forest restoration and conservation agriculture interventions. Government staff at the commune and nature reserve level have also been trained on climate change, ecoagriculture and nursery management. Thus far, at least 10 national and local government officials in the Research and Community Protected Area Development Department have benefitted from the training and technical expertise generated through the project. | 15 national and local government officials in the Research and Community Protected Area Development Department have fully developed capacity to implement forest restoration and conservation agriculture interventions that build climate resilience.
Output 1.1: Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach. | 1.1.1 Number and type of specialist reports developed for the project – through a participatory approach with local communities where relevant – in the first year. | No specialist reports on climate changes impacts and the preferred ecoagriculture interventions. |  | National consultants were recruited to undertake the necessary assessments. The 6 reports required have been submitted. | At least 6 specialist reports submitted to the PMU by the end of the first year of the project. These reports must include: • 1 x gap analysis (including the results of an institutional mapping exercise); • 1 x multi-use plant species assessment (including identification of climate-resilient indigenous plant species), with results disaggregated by CPA; • 1 x crop variety assessment (including identification of climate-resilient crop varieties), with results disaggregated by CPA; • 1 x planting schedule (based on useful plant species assessment); • 1 x improved rice variety assessment report; and • 1 x hydrological assessment report (including water challenges, potential water sources and proposed interventions), with results disaggregated by CPA.
| 1.1.2 Number of MSc research projects on ecoagriculture initiated at a local university. | No MSc research projects on ecoagriculture in Cambodia. |  | Five MSc students have started their course in Natural Recourse Management and REDD+ for the Academic year 2015. These students will undertake research dissertation on the project's ecoagriculture interventions. 3 scholars are from the Royal University of Agriculture and 2 scholars are from the Royal University of Phnom Penh. | At least 5 MSc projects on ecoagriculture initiated at local universities over the duration of the AF project.
Output 1.2: Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products. | 1.2.1 Number and type of economic assessment reports developed for the project – through a participatory approach with local communities where relevant – in the first year. | No economic assessment reports on the preferred ecoagriculture interventions and associated micro-finance/insurance products. |  | Consultants have been recruited to undertake the necessary assesments. The five reports required have been developed. | At least 5 economic assessment reports submitted to the PMU by the end of the first year of the project. These reports must include: • 1 x report identifying locally available weather index-based insurance and micro-finance products; • 1 x market assessment of micro-finance opportunities for farmers at CPA intervention sites (including potential business plans for such products); • 1 x local agricultural market assessment; • 1 x cost-benefit analysis of potential crop/tree species to be planted; and • 1 x socio-economic assessment of proposed ecoagriculture approaches.
Output 1.3: Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2. | 1.3.1 Number and type of technical protocols – informed by output 1.1 – for ecoagriculture interventions developed in the second year of project. | There are no formal, technical protocols specific to the ecoagriculture approaches and project sites proposed by the AF project. |  | The formal technical protocols are being developed based on the combined findings of the various experts. A consultant has been recruited to undertake this colsolidation and first drafts of of the technical protocols have been submitted to the PSC. | At least 5 technical protocols (1 per CPA) for the preferred ecoagriculture interventions submitted to the PMU in the second year of the project. These reports must include protocols for: • restoration; • chamkar-based agroforestry; • homegarden establishment; • planting useful species around chamkar; • growing climate-resilient rice; and • implementing additional activities.
Outcome 2: Multi-use forests established and maintained and agricultural practices diversified/intensified to supply a diverse range of food and stabilize topsoil, despite an increase in climate change-induced droughts and floods. | Outcome 2 Number of households that have benefited from chamkar-based agroforestry plots and intensified/diversified homegardens at the target CPAs. | No chamkar-based agroforestry plots have been established at the five target CPAs. |  | 244 households in total are befitting from homegarden activities. (16 households in Chop Tasok, 30 in Ronouk Khgeng, 21 in Chiork Beungprey, in 97 Chom Thlork and in 80 Skor Crouch). Preparation has begun for additional households to establish homegardens in 2015, and the number of households is expected to double. A demonstration agroforestry plot has been established at Chom Thlork. Chamkar-based agroforestry plots will be piloted in August 2015. | 1000 households have benefited from chamkar-based agroforestry plots and 800 households have benefited from intensified/diversified homegardens at the target CPAs by the end of the project.
There is 1 intensified/diversified homegarden at Chop Tasok.
There are no intensified/diversified homegardens at the other four target CPAs. Therefore only 1 household has benefited an intensified/diversified homegarden.
Output 2.1: Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2. | 2.1.1 Number of CPA Management Committees, local authority members and agricultural extensions officers located throughout Cambodia trained on climate change and ecoagriculture interventions. | There has been no formal training encompassing the full ecoagriculture approach preferred by the AF project. |  | A consultant has been recruited and is in the process of designing the relevant training course. In addition, 7 training events have been organized by May 2015 with each of the five target CPA management committees on climate change awareness, with total ~50 (10 per CPA) participants of which more than 50% are women. | Mid-term: At least 30 CPA Management Committees; 10 local authorities members; and 5 agricultural extension officers throughout Cambodia trained on climate change and ecoagriculture interventions over the duration of the AF project. End of project: At least 60 (i.e. 50%) CPA Management Committees; 20 local authority members; and 10 agricultural extension officers throughout Cambodia trained on climate change and ecoagriculture interventions over the duration of the AF project.
| 2.1.2 Number of CPA community members, gender disaggregated, at project intervention sites trained on climate change and ecoagriculture interventions. | There has been no formal training encompassing the full ecoagriculture approach preferred by the AF project. |  | 35 training events (7 topics in each of the 5 CPAs) have been undertaken on nursery management and seed propagation, climate change, ecoagriculture, sustainable liveilhoods, livestock farming, land tenure and financial management. On average, 100 people have been involved in each training event (3500 people trained on average). | Mid-term: A total of at least 1250 CPA community members (30% of which should be women) trained on climate change and ecoagriculture interventions. End of project: A total of at least 2500 CPA community members (30% of which should be women) trained on climate change and ecoagriculture interventions.
| 2.1.3 Number of patrolling committees established/strengthened. | 1 formal patrolling committee at Ronouk Khgneng. |  | A patrolling committee has been established at all 5 CPAs. A reporting mechanism has been established and each team submits a monthly report to government counterparts. These patrrolling teams are supported with $150 for food and petrol costs. | 4 patrolling committees established (Chiork Boeungprey, Chorm Thlok, Skor Krouch and Chop Tasok) and 1 patrolling committee strengthened (Ronouk Khgneng).
| 2.1.4 Annual number of transgressions in each CPA between July 2014 and the end of the AF project. | 1 incident in 2012–2013 at Ronouk Khgneng. |  | Patrolling committees began to sumbit monthly patrolling reports in August 2014. The decrease in the number of transgressions will be measured once baseline values for the first year of reporting have been established this year. In Beung Per, 27.5 ha of illegally cleared forest has been reforested. | At least a 40% reduction in the annual number of transgressions in each CPA between July 2014 and the end of the AF project.
No reliable data on the current incidence of transgression was available for the remaining four CPAs. The baseline number of transgressions per year in each CPA will be measurable once patrolling committees have been established in each CPA.
Output 2.2: Forest restoration and ecoagriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites. | 2.2.1 Number of community-managed nurseries established at project intervention sites. | No functioning nurseries at any of the five CPAs. |  | The first AF nursery has been established to service the three CPAs within Beungprey Wildlife Sanctuary. The nursery was officially inaugurated by the Minister of the Environment on July 14, 2014. The Second AF nursery in Chup Tasok CPA of Kulen National Park was inaugurated on 06 March 2015 and the third AF nursery in Rounouk Khgneng CPA of Phnom Prech Wildlife Sanctury was inaugurated on 18 May 2015. All three nurseries have their own nursery management teams who have been well trained on nursery management and seedling propagation. | At least 3 nurseries established during the first year of the AF project, including: • 1 in Boeungper, • 1 in Phnom Kulen; and • 1 in Phnom Prech.
| 2.2.2 Number of qualified community-liaison planting officers contracted to assist with implementation of project activities at intervention sites. | 0 community liaison planting officers have been contracted. |  | 10 Government counterparts (fulfilling the role of community liaison planting officers) have been contracted. | 10 community liaison planting officers contracted in the first year, including: • 4 in Boeungper, • 3 in Phnom Kulen; and • 3 in Phnom Prech.
| 2.2.3 Hectares of degraded forest within target CPAs restored. | No forest restoration has taken place at the five target CPAs. |  | In August 2014, 21,270 fruit trees to be planted around homesteads were distributed, and 47,914 indigenous trees planted were planted in degraded areas of CPAs in Beung Per. By June 2015, and additional 45,000 fruit trees and 90,000 indigenous trees were planted. 40,000 of these indigenous trees were used to restore 27.5ha area of reclaimed, degraded land within Chorm Thlork. | At least 30 ha of degraded forest restored in Chorm Thlok CPA before the end of the project.
| 2.2.4 Number of intensified/diversified homegardens established at the target CPAs. | There is 1 intensified/diversified homegarden at Chop Tasok. |  | 244 households in total are befitting from homegarden activities. (16 households in Chop Tasok, 30 in Ronouk Khgeng, 21 in Chiork Beungprey, in 97 Chom Thlork and in 80 Skor Crouch). The homegardens establshed include: i) vegetables; ii) fruit trees; and iii) indigenous tree species. The species planted in each homegarden represent at least 4 canopy layers: herb, shrub, understory and canopy. In addition, target households who will participate in this intervention during year 3 have been identified, and the total number fo beneficiaries is expected to double. | Mid-term: 300 intensified/diversified homegardens established at the five target CPAs. A diversified/intensified homegarden should include at least 20 species, of which: i) at least 5 are indigenous fruit/soil-binding tree species; and ii) at least 8 are different vegetable species. Furthermore, the species planted within the homegarden should be representative of at least 4 different canopy layers (emergent, canopy, understory, shrub and herb). End of project: 800 intensified/diversified homegardens established at the five target CPAs. A diversified/intensified homegarden should include at least 20 species, of which: i) at least 5 are indigenous fruit/soil-binding tree species; and ii) at least 8 are different vegetable species. Furthermore, the species planted within the homegarden should be representative of at least 4 different canopy layers (emergent, canopy, understory, shrub and herb).
There are no intensified/diversified homegardens at the other four target CPAs.
| 2.2.5 Percentage of households at each CPA growing climate-resilient rice. | No households in any of the CPAs are growing climate-resilient rice varieties. |  | Consultants have been recruited to design the appropriate, scientific protocols for this intervention. In addition, project teams have distributed climate-resilient rice varieties for trialing for 64 households by August 2014 of which each family received 25kgs of rice resilience seeds species and 329 households by June 2015 of which each household received 20kgs of climate-resilient rice varieties. By June 2015, 17% (329 of 1895) households will have trialled climate-resilient rice. | Mid-term: 5% of households at each CPA growing climate-resilient rice varieties introduced by the AF project. End of project 15% of households at each CPA growing climate-resilient rice varieties introduced by the AF project.
| 2.2.6 Proportion of households in the five target CPAs that report an improvement in i) access to water; ii) access to new seed varieties; and iii) access to improved rice storage techniques, as a result of additional interventions. | The percentage of farmers who irrigate their crops is: 0% at Chiork Boeungprey; 12% at Chorm Thlok; 6% at Skor Krouch; 6% at Chop Tasok; and 19% at Ronouk Khgneng. No climate-resilient rice seeds have been introduced at the five target CPAs. No households at Chorm Thlok or Chop Tasok have access to improved rice storage techniques. |  | A hydrologist has been recruited to select appropriate sites for dam and well construction. A report detailing his findings has been submitted. In addition, project teams have dug 2 ponds for Chiork Boeungprey nusery together with its automatic solar water pumping system and storage tankers. Tube wells fitted with hand pumps have also been supplied to 16 households in Chiork Beungprey. In Ronouk Khgeng, 7 pumping wells have been constructed, and rain water harvesting storage tank have been distributed to 77 households. In Chop Tasok a complete water supply system, which links a natural spring to all households and the project nursery has been constructed. The percentage of households that report an improvement in access to water and improved rice storage techniques will be assessed through a survey at the mid-term of the project. | Mid-term: 50 % of households in the five target CPAs report an improvement in i) access to water; and ii) access to new seed varieties as a result of additional interventions. 50% of households in Chorm Thlok and Chop Tasok report an improvement in access to improved crop storage techniques as a result of additional interventions. End of project: 80% of households in the five target CPAs report an improvement in i) access to water; and ii) access to new seed varieties as a result of additional interventions. 80% of households in Chorm Thlok and Chop Tasok report an improvement in access to improved rice storage techniques as a result of additional interventions.
Output 2.3: Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies. | 2.3.1 Number of sustainable alternative livelihood strategies developed – through a participatory approach with local communities where relevant – through the project. | No sustainable alternative livelihood strategies have been developed by experts at any of the five target intervention sites. |  | Consultants have been recruited to identify appropriate alternative livelihood strategies. The project team of Boeungper Wildlife Sanctuary has also started family livestock farming with 5 of the 15 identifed families for 2015. Targeted households were supplied with chickens and training on animal husbandry. | At least 3 alternative livelihood strategies developed per CPA by consultants contracted by the AF project. These will include: micro-finance insurance products and small-scale businesses for NTFPs identified in Component 1.
| 2.3.2 Percentage of target households adopting sustainable alternative livelihood strategies (dissagregated by gender). | 34% of household at Chorm Thlok and 45% of households at Skor Krouch derive income from labour. |  | Consultants have been recruited to identify appropriate alternative livelihood strategies. These consultants willl develop specific alternative livelihood strategies for each of the 5 CPAs. | 25% of households in the five target CPAs have adopted at least 1 sustainable alternative livelihood strategy or alternate source of income developed by the AF project. At least 30% of the beneficiaries of these alternative livelihood strategies should be women.
43% of households at Ronouk Khgneng derive income from livestock sales.
14% of household at Chorm Thlok, 12% of households at Chop Tasok and 31% at Ronouk Khgneng derive income from NTFP products.
< 10% of households at all CPAs derive income from any other sources.
Output 2.4: Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 2.4.1 Number of socio-economic and ecological monitoring reports and research protocols (for project duration and long-term) developed to measure impacts of the project: i) in the intervention sites; and ii) downstream of the intervention sites. | No formal specialist reports on socio-economic and ecological monitoring developed. |  | Both an International and a National Research and Monitoring Coordinator have been recruited to develop a research and monitoring plan and produce monitoring tools. Drafts of the plan and tools have been presented to the PMU. The coordinators are also guiding the MSc students regarding their research topics. The project team is also consistently collecting relevant monitoring data (for example informtation related to the climate-resilient rice trials) which willl be consolidated in the monitoring reports to be produced by the coordinators. | Mid-term: • At least 1 research/monitoring tool developed and implemented to measure the impact of AF project interventions in downstream communities. • At least 5 ecological and socio-economic baseline monitoring reports (1 per CPA). End of project: • Research/monitoring tool to measure the impact of AF project interventions in downstream communities implemented at least 3 times. • At least 10 ecological and socio-economic monitoring reports (2 per CPA, 1 for baseline values and 1 for end of project).
Outcome 3: Integration of climate change risks and ecoagriculture into Cambodia’s adaptation framework and related sector policies. | Outcome 3: No., type, and sector of policy revisions to address climate change risks proposed . | No proposed revisions to integrate climate change and ecoagriculture into agricultural, forestry and development policies, strategies and plans. |  | An Institutional Expert has been recruited to undertake an institutional mapping exercise. A final report has been submitted. This consultant, together with the project team, is also in the process of developing/updating CPA management plans for each of the target CPAs. This is expected to be completed by the end of 2015. | At least 3 revisions to incorporate climate change and ecoagriculture into relevant environmental, agricultural, forestry and/or development policies/plans proposed by the end of the AF project.
Output 3.1: Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities. | 3.1.1 Number of ‘events’ held and/or products developed to raise awareness on climate change and the benefits of adaptive agricultural techniques. | No previous ‘events’ to raise awareness, and no existing use of the ecoagriculture approach in Cambodia. |  | An Awareness Campaign Expert has been recruited to design an appropriate campaign. In addition, another consultant for training was also hired to design a relevant training course. As a result, to date 15 training events related to climate change and eco-agriculture interventions have been organized by May 2015. Furthermore, a project web site has been developed and is awaiting official approval from the MoE. One poster demonstrating the concept of ecoagriculture has been developed and copies have been distributed to the target CPAs. Three brochures about nursery management have also been developed and distributed. | At least 28 ‘events’ held and/or prodcuts developed to raise awareness of climate change and ecoagriculture, including workshops, campaigns, education initiatives at schools/universities, a web-based data network portal and a documentary film.
| 3.1.2 Percentage change in the climate change awareness index and understanding of ecoagriculture in the target communities. | The following table shows the current values for the climate change awareness index at each CPA (based on the results of the household survey). The climate change awareness index can vary between 0 and 100%. |  | A context-specific methodology to measure the climate change awareness index of target communities was developed during the baseline study. The baseline climate change awareness index scores where also collected. The index will be measured again (using the same methodology) at the mid-term and end of the project to assess progress towards to the target increase in awareness. | Mid-term: • Average awareness index score of 30% at the five target CPAs. • 30% of community members at the five target CPAs understand the concept of ecoagriculture. End of project: • Average awareness index score of 50% at the five target CPAs. • 50% of community members at the five target CPAs understand the concept of ecoagriculture.
|  | CPA | Climate change awareness index
|  | Chiork Boeungprey | 16%
|  | Chorm Thlok | 10%
|  | Skor Krouch | 30%
|  | Chop Tasok | 12%
|  | Ronouk Khgneng | 42%
The following table shows the percentage of households at each CPA that understand the concept of ecoagriculture.
Concept understood
|  | Chiork Boeungprey | 6%
|  | Chorm Thlok | 4%
|  | Skor Krouch | 6%
|  | Chop Tasok | 0%
|  | Ronouk Khgneng | 0%
| 3.1.3 Number and type of REDD+ feasibility studies and Project Idea Notes (if applicable). | No REDD+ feasibility study that investigating the potential to integrate/promote ecoagriculture or species from multi-use forests into REDD+ projects exists. |  | A consultant was recruited to undertke a REDD+ feasibility study. The final report has been submitted and approved. | At least 1 REDD+ feasibility study and Project Idea Note (if applicable) investigating the potential to integrate/promote ecoagriculture or species from multi-use forests into REDD+ projects developed in the first year of the AF project.
Output 3.2: Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation. | 3.2.1 Number of CPA management plans developed/revised to incorporate the ecoagriculture approach. | Ronouk Khgneng and Chiork Boeungprey (due to be revised) have a CPA management plans, but they do not include strategies for the implementation or maintenance of ecoagriculture interventions. CPA management plans have yet to be developed for Chorm Thlok, Skor Krouch and Chop Tasok. |  | A land tenure specialist and insitutional expert have been recruited to contribute to the development of CPA management plans. Final reports from both of these consultants have been submitted. The institutional expert, together with the project team, is also in the process of developing/updating CPA management plans for each of the target CPAs (updating the CPA management plan for Ronouk Khgeng and Chiork Beungprey and developing new plans for the other three CPAs). This is expected to be completed by the end of 2015. | At least 5 CPA management plans developed/revised to incorporate the ecoagriculture approach by the end of the AF project.
Output 3.3: National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia. | 3.3.1 Number of national ecoagriculture upscaling strategies developed. | No national ecoagriculture upscaling strategy exists in Cambodia. |  | This activity is expected to start in 2016. | 1 national ecoagriculture upscaling strategy developed by the end of the AF project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1) The involvement of high-level government staff in project activities (for instance the Minister of Environment inaugurated the first nursery constructed and planted the first trees for reforestation) has ensured political support for the project. 2) Implementing activities that show immediate, tangible benefits to local communities early in the project (for instance the construction of water supply infrastructure) encourages community participation. 3) Responding to community requests and knowledge (for example distributing sought-after fruit trees together with indigenous tree species) promotes community ownership and has encouraged additional households to become involved in the project activities. 4) Institutional reform within the minsitry of environment had the potential to affect project progress. However, frequent discussions within the department and political commitment to the project has ensured that while governemnt counterparts may have changed position/designation they have remained as part of the project team.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | (1) There was a delay in the construction of one of the nurseries because of land tenure issues, difficulty accessing water and a lack of consensus among local community members about where the nursery should be situated. This was resolved through extensive community engagement to reach consensus on the placement of the nursery and the construction of wells. The nursery has now beeen completed. 2) Changes in UNEP financial management systems resulted in a slightly increased processing time for cash advance reqests, leading to a temporary interruption in availability of funds for the project (about two weeks). The problem was primarily because of a lack of awareness from all sides on the actual time needed to process cash transfers in the new system. To prevent cash shortages from happening in the future UNEP and the MoE have agreed to start cash advance requests well ahead of planned project expenditures. It is expected that such measures will practically eliminate this potential delay going forward.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | As described in the first PPR, 10 Government Counterparts (serving as the Community Liaison Planting officers identified in the Project Document) were recruited to improve communication with the target communities and increasedtheir willingness to participate in project activities. Also as reported in the first PPR, based on the recommendations of the baseline study, and endorsed by the Project Steering Committee, the project restoration interventions (Output 2.2) have been adjusted to focus on agricultural land within CPAs in addition to the degraded forest areas which were initiatlly targeted by the project. No additional changes changes to project outputs have been made.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | (1) Gender considerations have been taken into account during the reporting period primarily through the encouragement of women participants for pilot activities, including the reforestation and homegardening activities. (2) Women have been encouraged to join the nursery management teams at each project site. Approximately 30% of members of the nursery management teams are women. (3) The project also encourage women participants to take part in project workshops and training. In general, the number of women attending training workshops held at the project intervention sites exceeds the number of men.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 5 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | i) At least 30 ha of degraded forest restored in Chorm Thlok CPA before the end of the project, ii) 800 intensified/diversified homegardens established at the five target CPA | i) No forest restoration has taken place at the five target CPAs, ii) there is 1 intensified/diversified homegarden at Chop Tasok and none in the other four CPA's
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | 4 | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | 1 national ecoagriculture upscaling strategy and at least 3 revisions to incorporate climate change and ecoagriculture into relevant environmental, agricultural, forestry and/or development policies/plans. | No upscaling strategy or revisions exist
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 1.1 | This project will undertake a risk and vulnerability assesment | 0
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.